## Index
20 CONSTRUCTION DATA ANALYSIS PROBLEMS — FOR WT PARTNERSHIP
Prepared by Gulzar ¦ Data Analyst ¦ Construction-Tech Domain
# | Problem Title | Domain | Sheet Name | Rows in Dataset
1 | Project Cost Overrun Analysis | Cost Management | P01-CostOverrun | 50
2 | Material Price Fluctuation Tracker | Procurement | P02-MaterialPrice | 90
3 | BOQ Variance Analysis | Quantity Surveying | P03-BOQVariance | 60
4 | Labour Productivity by Trade | Resource Management | P04-LabourProd | 80
5 | Tender Bid Comparison | Commercial | P05-TenderBid | 40
6 | Project Delay Root Cause | Project Management | P06-DelayRCA | 60
7 | Monthly Cash Flow Tracking | Financial Management | P07-CashFlow | 48
8 | Change Order Impact Analysis | Contract Management | P08-ChangeOrder | 45
9 | Subcontractor Performance Scorecard | Vendor Management | P09-SubconScore | 30
10 | Construction Cost Benchmarking | Cost Intelligence | P10-Benchmark | 40
11 | Risk Register & Probability Matrix | Risk Management | P11-RiskRegister | 35
12 | Earned Value Management (EVM) | Project Controls | P12-EVM | 36
13 | Material Wastage Analysis | Sustainability | P13-Wastage | 60
14 | Site Safety Incident Tracker | HSE | P14-Safety | 50
15 | Equipment Utilization Analysis | Asset Management | P15-Equipment | 40
16 | Procurement Lead Time Analysis | Supply Chain | P16-LeadTime | 50
17 | Defect & Snag List Analysis | Quality Management | P17-Defects | 70
18 | Carbon Footprint per Project | ESG / Sustainability | P18-Carbon | 30
19 | Client Payment Aging Tracker | Accounts Receivable | P19-PaymentAging | 40
20 | Multi-Project Portfolio Dashboard Data | Portfolio Management | P20-Portfolio | 25

## Analysis Dashboard
Sheet Name | P01-CostOverrun
Q1. Which country has the highest average cost overrun percentage?
Q2. What is the total budget vs actual cost for each project type? Which type has the worst variance?
Q3. Identify the Top 5 projects with the highest absolute cost overrun (in USD).
Q4. Is there a correlation between project duration and cost overrun percentage?
Q5. Create a pivot table showing average overrun % by Country × Project Type.
Q6. What percentage of projects came in under budget vs over budget?
Q7. Which city has the most cost-efficient project delivery?
Sheet Name | P02-MaterialPrice
Q1. Which material has shown the highest average price increase over 18 months?
Q2. Create a line chart showing monthly price trend for TMT Steel and Cement.
Q3. Which country has the most volatile material pricing? (Use standard deviation)
Q4. Identify the top 3 materials with price increase > 15% — flag them as procurement risk.
Q5. What is the average price change % by material across all months?
Q6. If WT needs 500 MT of steel next quarter, what is the projected cost based on the trend?
Sheet Name | P03-BOQVariance
Q1. Which project has the highest total BOQ variance (in USD)?
Q2. Which trade consistently exceeds BOQ quantities across all 3 projects?
Q3. Identify the top 5 BOQ items with the highest quantity variance %.
Q4. What is the total financial impact of quantity overruns per project?
Q5. Create a waterfall chart showing BOQ Amount vs Actual Amount per trade for Project WT-DC-MUM-01.
Q6. Which items have negative variance (came under BOQ)? What's the saving?
Sheet Name | P04-LabourProd
Q1. Which trade has the highest average productivity per man-hour?
Q2. Is there a productivity difference between projects in India vs Australia?
Q3. Create a box plot (or summary stats) of productivity by trade — which has the most variance?
Q4. On which dates did productivity drop below the 25th percentile? What was the trade?
Q5. What is the optimal crew size (workers count) that maximises productivity for Civil & Structure?
Q6. Calculate total man-hours consumed per project and rank them.
Sheet Name | P05-TenderBid
Q1. For each tender package, which contractor offers the lowest bid? Is the lowest bid always the best choice?
Q2. Create a weighted scoring model: 40% Price, 20% Time, 15% Experience, 15% Safety, 10% Defects. Rank contractors.
Q3. Which contractors appear in multiple packages? What is their average bid competitiveness?
Q4. Identify any contractor with Safety Rating < 3.5 AND Defect Rate > 8% — flag as HIGH RISK.
Q5. What is the total project cost if WT selects the lowest bidder for each package vs the highest-scored bidder?
Q6. Create a scatter plot of Bid Amount vs Completion Days — are cheaper bids slower?
Sheet Name | P06-DelayRCA
Q1. What is the most frequent delay cause category? Create a Pareto chart.
Q2. Which responsible party causes the most total delay days?
Q3. For Project WT-DC-MUM-01, what is the cumulative delay and the dominant cause?
Q4. Is there a seasonal pattern in delays? (Hint: check Weather delays by month)
Q5. Which activity is most delay-prone across all projects?
Q6. Calculate the estimated cost of delay per project if the daily burn rate is $15,000.
Sheet Name | P07-CashFlow
Q1. Which project had negative net cash flow for the most months?
Q2. What is the cumulative cash position for each project at end of December 2024?
Q3. Create a line chart of monthly net cash flow for all 4 projects.
Q4. In which months did actual inflow fall below 70% of planned? Flag as collection risk.
Q5. What is the total cash surplus/deficit across all projects?
Q6. Calculate the cash flow forecast accuracy: (Actual Inflow / Planned Inflow) × 100.
Sheet Name | P08-ChangeOrder
Q1. What is the total approved cost impact of all change orders per project?
Q2. Who initiates the most change orders — Client, Consultant, or Contractor?
Q3. What % of change orders are still Pending or Under Review? What is the potential cost exposure?
Q4. Is there a correlation between cost impact and time impact of VOs?
Q5. Which project has the highest change order frequency per month?
Q6. Create a stacked bar chart: Approved vs Pending vs Rejected VO costs per project.
Sheet Name | P09-SubconScore
Q1. Rank all subcontractors by their weighted score. Who are the top 3 and bottom 3?
Q2. Which trade has the lowest average quality score?
Q3. Is there a negative correlation between defect count and quality score?
Q4. Create a radar chart for the top-performing subcontractor showing all 5 dimensions.
Q5. Which subcontractors should be blacklisted (weighted score < 3.0 AND defects > 15)?
Q6. Compare subcontractor performance across the 3 projects — is any project a consistent outlier?
Sheet Name | P10-Benchmark
Q1. What is the average cost per sqm by country? Visualise as a bar chart.
Q2. Which project type has the highest and lowest cost per sqm globally?
Q3. Has cost per sqm increased year-over-year? Show the trend by country.
Q4. Create a benchmark table: Project Type × Country showing avg cost/sqm.
Q5. Identify outliers — projects where cost/sqm is >1.5× the country average for that type.
Q6. If WT pitches a 50,000 sqm Data Centre in Mumbai, what should the budget estimate be based on this data?
Sheet Name | P12-EVM
Q1. In which month does the project first show a negative Schedule Variance (SV)?
Q2. What is the CPI trend? Is the project getting more or less cost-efficient over time?
Q3. Based on EAC at Month 36, what is the projected cost overrun?
Q4. Create a line chart with PV, EV, and AC — the classic S-curve.
Q5. At what month does SPI drop below 0.90 (critical schedule delay)?
Q6. If management wants CPI ≥ 1.0 by Month 24, how much cost needs to be recovered?
Sheet Name | P13-LeadTime
Q1. What is the average lead time (order to delivery) by material?
Q2. Which supplier has the worst on-time delivery rate?
Q3. How many POs were delivered late? What is the average delay in days?
Q4. Is there a country-level difference in procurement lead times?
Q5. Which material has the longest and most unpredictable lead time (highest std deviation)?
Q6. Create a supplier reliability scorecard based on on-time delivery %.
Sheet Name | P14-PaymentAging
Q1. What is the total outstanding amount across all projects?
Q2. Which client has the highest overdue amount (paid after due date)?
Q3. Create an aging bucket analysis: 0–30 days, 31–60 days, 61–90 days, 90+ days.
Q4. What is the average days-to-pay by client?
Q5. Which project has the worst collection rate (Paid / Invoiced)?
Q6. If WT charges 1.5% monthly interest on overdue amounts, what is the total interest receivable?
Sheet Name | P15-Portfolio
Q1. How many projects are In Progress, On Hold, Completed, and Planning? Show as a pie chart.
Q2. What is the total portfolio budget and total spent? What is the overall budget variance?
Q3. Which projects have CPI < 0.90 AND SPI < 0.90? These are 'red zone' — list them.
Q4. Create a bubble chart: X = SPI, Y = CPI, Size = Budget. Which quadrant has the most projects?
Q5. What is the average completion % by country?
Q6. Build a traffic-light summary: Green (CPI≥1, SPI≥1), Amber (either <1), Red (both <0.9). Count per category.
Q7. If WT's board asks 'how is our portfolio doing?' — write a 3-line executive summary using this data.

## Data Story
THE STORY OF THE PORTFOLIO — 15 PROBLEMS, ONE NARRATIVE
WT Partnership construction data ¦ 50 projects, 25-project portfolio, 3 countries ¦ Every chapter below is tagged to one of the 15 analysed problems. Evidence column is a live link to the Analysis report.
THE STORY IN ONE SHOT
WT wins work in the cheapest-bid market and prices it off benchmarks that are already drifting (P05, P10). The job then leaks value in three places at once: quantities and variations grow beyond the BOQ (P01, P03, P08), the site loses days to other people's decisions and to its own productivity swings (P04, P06, P09, P12), and the supply chain delivers late and dearer than planned (P02, P13). By the time the work is built the money is still outside the business — cash is negative, invoices are ageing, the portfolio is amber (P07, P14, P15). Nine out of ten projects finish over budget, 2024 closed $7.3m cash-negative, $11.9m sits uncollected and 72% of live projects are amber. The cause is not one failure; it is one chain, and it breaks in the same order every time.
Ch | Tag | Chapter headline | The story — what the data is telling us | Evidence (live link to Analysis report) | So what - the move
ACT I — THE PROMISE: how the job is won and priced
1 | P05 | We buy the cheapest number, not the best bid | Across 5 packages and 13 contractors, the lowest bidder is not the best bidder on 2 of 5 packages. Cheap bids also quote longer programmes (r = -0.25), and 4 bids fail both the safety and defect screens - yet they price competitively enough to win. The discount we celebrate at award is a liability we inherit on site. | ANSWER: Awarding every package to the cheapest bid totals $1,01,30,539 (avg score 76.0/100). Awarding to the highest-scored bid totals $1,17,16,950 (avg score 79.1) — $15,86,411 (15.7%) more. That premium buys better programme, safety and defect performance. | Award on the weighted score, not price alone. Hard-gate any bid with safety < 3.5 or defects > 8% before commercial evaluation.
2 | P10 | The rate base we price from is a moving target | Benchmarks span $670/sqm in India to $3,677/sqm in Australia, and by type from $1,732/sqm (Data Centre) to $3,859/sqm (Hotel). Global rates look flat (-10.2% since 2022) but India has moved +81.6% in the same window. A single blended rate hides a 2.2x spread and an escalating market. | ANSWER: Australia is the most expensive market at $3,677/sqm, India the cheapest at $670/sqm — a 448.5% premium. Global average: $2,430/sqm. | Price every pursuit off the country x type cell, then add an explicit escalation line — never a portfolio average.
ACT II — THE BUILD-UP: where the budget quietly disappears
3 | P01 | Overrun is the norm, not the exception | 45 of 50 projects finished over budget — $2.15bn planned became $2.53bn spent, a 17.6% portfolio overrun. Residential Towers are worst at 26.3%; the single biggest hit is WT-1028 at $2.47cr (33.1%). Duration explains none of it (r = -0.16), so this is not 'long jobs drift' — it is estimating and control, not time. | ANSWER: Worst variance = Residential Tower at 26.3% ($6,26,62,924 over budget). Best = Shopping Mall at 3.4%. Portfolio total: $2,15,23,99,053 budget vs $2,53,19,47,246 actual (17.6%). | Stop treating overrun as project-specific. Re-baseline the estimating allowance by type, starting with Residential Tower and Hospital.
4 | P03 | The BOQ is measured out, line by line | 72 BOQ lines across 3 projects show $18.3L of gross overrun against only $2.4L of savings — net $15.9L, 9.9% above BOQ. MEP-Electrical is over BOQ on 3 of 3 projects; Plastering on the Auckland hospital is 28.9% over. This is the micro-version of Chapter 3: the overrun is assembled from trades, not accidents. | ANSWER: Gross overrun impact is $18,28,491 against $2,37,902 of savings, a net $15,90,589 across the three projects. Worst project: WT-OFF-SYD-02 at $7,16,910 net. | Put MEP-Electrical and wet trades on remeasure-and-report monthly, not at final account.
5 | P08 | Variations: a live book we have not closed | 45 VOs worth $1.43cr in total. $41.9L is approved, but 15 VOs (33%) worth $33.0L are still pending or under review — unquantified exposure sitting outside the forecast. Consultants raise the most VOs (36%); clients drive the most value ($53.0L). Cost and delay are unrelated (r = 0.12), so cheap variations still bite the programme. | ANSWER: 15 of 45 change orders (33.3%) are still Pending or Under Review, carrying $32,97,152 of unquantified cost exposure (23.0% of all VO value). That is the number to put in the risk register until these are determined. | Move the $33.0L undetermined VO book into the risk register this month and force a 30-day determination rule.
ACT III — THE GRIND: the site loses days it never gets back
6 | P04 | Productivity is not low — it is wildly inconsistent | Across 80 crew-days, Civil & Structure averages 3.54 units/man-hour but with the highest variance of any trade (CV 56.4%); the best crew band delivers 4.16 against 2.68 for the weakest. 20 of 80 days fall below the 25th percentile. The problem is not the workforce's ceiling, it is the floor — broken work fronts and unstable crew sizes. | ANSWER: Civil & Structure shows the most variance (std dev 2.00, CV 56.4%); the most consistent is MEP - HVAC (std dev 1.13). High variance points to unstable crew mix or interrupted work fronts. | Standardise crew size to the proven 11–15 band and protect work fronts; chase the bad days, not the average.
7 | P06 | 1,467 lost days — and most are decisions, not weather | 60 delay events cost 1,467 days, roughly $2.20cr at $15k/day. The top cause is RFI response delay (18.3% of events); consultants own 339 days, the most of any party. Weather accounts for only 10.8%, peaking in November. Testing & Commissioning absorbs 291 days — delay concentrates at the end, where there is no float left. | ANSWER: At $15,000/day the portfolio's 1,467 delay days cost roughly $2,20,05,000. The most exposed project is WT-DC-MUM-01 at $57,30,000 (382 days); the least is WT-HOS-AKL-03 at $30,75,000. | Put an SLA on RFI turnaround with the consultant, and start T&C planning at 60% completion, not at handover.
8 | P09 | Subcontractor scoring is not discriminating | 30 scorecards average 3.43 with only 0.08 points separating the best and worst project. Civil & Structure scores lowest on quality (2.45) and carries 48 defects, yet defect count barely correlates with the quality score (r = -0.09). Two subcontractors breach blacklist criteria. The scorecard is currently describing everyone as average. | ANSWER: 2 scorecard(s) breach both blacklist criteria and are listed above. Separately 4 score below 3.0 and 13 carry more than 15 defects. | Rewrite the scoring weights so defects actually move the score, and act on the two blacklist breaches.
9 | P12 | EVM confirms it: behind and getting worse | Over 36 months, SV is negative in 31 of them and CPI declines from 1.042 to 0.900 — efficiency is eroding, not recovering. SPI closes at 0.794. EAC lands at $2.78cr against a $2.50cr BAC, an 11.1% forecast overrun. Everything in Acts II and III shows up here as one number. | ANSWER: EAC at Month 36 is $2,77,85,221 against a BAC of $2,50,00,000 — a projected OVERRUN of $27,85,221 (11.1%). Variance at Completion is -$27,85,221. | Treat EAC vs BAC as the monthly board metric; a recovery plan is due while CPI is 0.90, not when it is 0.80.
ACT IV — THE SQUEEZE: the supply chain sets our programme
10 | P02 | Materials inflate faster than the contingency | Average material price movement is 7.5%, but RMC M30 (14.8%), Aggregate 20mm (14.6%) and Cement (11.9%) run at double that, and 20 of 90 monthly records exceed 15%. India is the most volatile market (9.8pp std dev). A fixed-price contract priced on a 5% allowance is under-funded before work starts. | ANSWER: No material's AVERAGE increase exceeds 15% (highest is RMC M30 at 14.8%), though 20 of 90 individual monthly records are above 15%. Treat the top 3 — RMC M30 (14.8%), Aggregate (20mm) (14.6%), Cement (OPC 53) (11.9%) — as procurement risk and forward-buy / lock rates. | Forward-buy or rate-lock the top 3 movers at award; index-link where the client will accept it.
11 | P13 | 70% of purchase orders land late | 35 of 50 POs arrive after the expected date, on an average 36.9-day lead time. Copper wiring takes 69 days; vitrified tiles swing between 18 and 74 days (sd 39.6). Not one of the 10 suppliers clears a 90% on-time rate — portfolio on-time performance is 30%. The delay days in Chapter 7 start in this chapter. | ANSWER: The scorecard above ranks all 10 suppliers. 0 rate A (90%+ on time), 0 rate B, 0 are watch-list and 10 should be replaced. Portfolio on-time performance is 30.0%. | Dual-source copper and tiles, carry buffer stock, and rebuild the procurement schedule on actual — not quoted — lead times.
ACT V — THE RECKONING: the work is built, the money is not in
12 | P07 | 2024 closed $7.3m cash-negative | Collected $4.30cr against $5.03cr spent — a $73.2L deficit, with 3 of 4 projects individually negative and the deepest trough in Sep-2024. 17 of 48 project-months collected under 70% of plan, and forecast accuracy is only 76.9%. We are not just collecting badly; we are forecasting badly. | ANSWER: At 31-Dec-2024 the portfolio sits at -$73,16,487 cumulative cash. 3 of 4 projects are cash-negative. Best: WT-DC-MUM-01 at $8,39,758; worst: WT-HOS-AKL-03 at -$38,67,202. Collections came in $1,28,96,910 below plan. | Re-forecast cash monthly off actual certification history, and escalate any project-month below 70% of plan within the week.
13 | P14 | $11.9m outstanding — and most of it is old | $1.19cr remains unpaid on $4.17cr invoiced (71.6% collection). $1.09cr of that is past due and 62.7% of it sits in the 90+ day bucket. Average time to payment is 58 days against ~30-day terms; Brookfield alone holds $41.4L. At 1.5%/month the overdue book has earned $7.98L of claimable interest. | ANSWER: Of $1,18,56,858 outstanding, $1,09,01,155 is past due and splits as: $9,98,469 (9.2%) 0–30 days, $30,71,180 (28.2%) 31–60 days, $0 (0.0%) 61–90 days and $68,31,506 (62.7%) 90+ days. The remaining $9,55,703 is not yet due. Average age of past-due debt: 80 days. | Escalate the 90+ bucket to formal recovery and start charging contractual interest — $7.98L is already claimable.
14 | P15 | The portfolio verdict: amber, and standing still | Of 25 projects, 4 are green, 18 amber and 3 red. 8 are On Hold — tying up $50.6cr of budget doing nothing. 11 projects (44%) sit in the 'late and over cost' quadrant against only 4 true performers. Spend is 48.5% against 49.8% completion, so the portfolio looks on track on paper while the indices say otherwise. | ANSWER: The busiest quadrant is "Late and over cost" with 11 of 25 projects (44.0%) and $63,55,84,316 of budget. Only 4 projects are true stars (both indices at or above 1.00). | Force a decision on the 8 on-hold projects (restart or release capital) and put the 3 red projects on recovery plans before taking new work.
15 | P11 | The missing chapter: risk was never registered | P11 — Risk Register & Probability Matrix — is the one problem of the fifteen with no data sheet in this workbook. That is not a formatting gap, it is the reason the other fourteen chapters read the way they do: the $33.0L of undetermined VOs, the 90+ day debt, the 8 on-hold projects and the 3 red projects are all live risks that nobody scored, owned or priced in advance. Every chapter above is a risk that was managed after it happened. | Index lists 20 problems; 14 have data sheets, P11 (Risk Register) does not. P16-P20 are out of scope for this story. | Stand up the risk register first: score the exposures already named in Chapters 5, 12, 13 and 14 and give each one an owner and a number.
THE CHAIN, IN ONE LINE
Cheap bid (P05) + drifting rate base (P10) → quantities and variations grow (P01, P03, P08) → site loses 1,467 days to RFIs, suppliers and unstable crews (P04, P06, P09, P13) → materials inflate past the allowance (P02) → EVM confirms 11% overrun (P12) → cash goes negative and debt ages (P07, P14) → portfolio turns amber (P15) — and none of it was ever on a risk register (P11).
THE FIVE MOVES THAT BREAK THE CHAIN
1. Award on weighted score with a safety/defect hard gate — stop importing the problem at tender (P05, P09).
2. Re-baseline estimating by country x type and index the top 3 material movers — price the market we are actually in (P10, P02).
3. Determine the $33.0L VO book within 30 days and remeasure MEP/wet trades monthly — close the leak while it is small (P08, P03, P01).
4. SLA the RFI turnaround, dual-source the two worst-lead-time materials and fix crew size at the proven band — buy back the 1,467 days (P06, P13, P04, P12).
5. Re-forecast cash monthly, charge interest on the 90+ bucket and force a restart-or-release call on the 8 on-hold projects (P07, P14, P15, P11).
Sources: every figure traces to the 'Analysis report' sheet (live formulas in column E) and the charts on 'Q&A Chart Dashboard'. Currency shown as in source (Indian digit grouping; cr = crore, L = lakh).

## KPI Dashboard
WT PARTNERSHIP ¦ CONSTRUCTION ANALYTICS DASHBOARD |  |  |  | CHART DATA — live links to 'Analysis report'. Do not delete; every chart on this dashboard reads from these tables.
T1 Cost variance by project type (P01 Q2)
Every KPI and chart below is a live formula link to the 'Analysis report' sheet (15 problems, 20 source datasets). Change the source data and this dashboard refreshes automatically. |  |  |  | Project Type | Variance %
|  |  |  | Residential Tower | 0.26303
PORTFOLIO BUDGET (USD) | SPEND TO DATE (USD) | AVG PORTFOLIO COMPLETION | RED-ZONE PROJECTS | IT Park | 0.21567
1425725823 | 690772336 | 49.76% | 3 | University Campus | 0.21727
25 live projects ¦ India · Australia · New Zealand | 48.5% of budget drawn | Avg CPI 0.93 (target 1.00) | CPI & SPI < 0.90 ¦ $8,75,29,465 budget at risk | Industrial Warehouse | 0.14692
|  |  |  | Data Centre | 0.12161
PORTFOLIO COST OVERRUN % | PROJECTS OVER BUDGET | TOTAL DELAY DAYS | NET CASH POSITION (2024) | Hospital | 0.24715
17.63% | 90% | 1467 | -7316487 | Commercial Office | 0.14563
$37,95,48,193 over budget on 50 projects | 45 of 50 projects exceeded budget | Cost of delay $2,20,05,000 @ $15k/day | Collection forecast accuracy 76.9% | Hotel | 0.13721
|  |  |  | Metro Station | 0.13531
OUTSTANDING RECEIVABLES | UNRESOLVED VO EXPOSURE | SUPPLIER ON-TIME DELIVERY | EVM PROJECTED OVERRUN | Shopping Mall | 0.033803
11856858 | 3297152 | 30% | 11.14%
$68,31,506 of it is 90+ days overdue (57.6%) | 15 of 45 variations pending / under review | 35 of 50 POs late, avg 5.9 days | EAC $2,77,85,221 vs BAC $2,50,00,000 | T2 Top 5 cost overruns (P01 Q3)
|  |  |  | Project | Absolute Overrun USD
|  |  |  | Residential Tower Per-29 | 24654239
1. COST & BUDGET PERFORMANCE — where the overrun is coming from |  |  |  | Residential Tower Hyd-33 | 21628203
|  |  |  | IT Park Syd-34 | 19739335
|  |  |  | University Campus Kol-35 | 19335358
|  |  |  | Industrial Warehouse Can-44 | 19116067
T3 Cost per sqm by country (P10 Q1)
|  |  |  | Country | Avg Cost per sqm USD
|  |  |  | Australia | 3677.1111
|  |  |  | India | 670.4
|  |  |  | New Zealand | 2993
T4 Cost overrun by country (P01 Q1)
|  |  |  | Country | Avg Cost Overrun %
|  |  |  | Australia | 0.16732
|  |  |  | India | 0.15764
|  |  |  | New Zealand | 0.19748
T5 Delay cause Pareto (P06 Q1)
|  |  |  | Delay Cause | Events | Cumulative %
|  |  |  | RFI Response Delay | 11 | 0.18333
|  |  |  | Permit Delay | 8 | 0.31667
2. GEOGRAPHY — cost levels and overrun by country |  |  |  | Material Delay | 8 | 0.45
|  |  |  | Client Decision Pending | 6 | 0.55
|  |  |  | Labour Shortage | 5 | 0.63333
|  |  |  | Equipment Breakdown | 5 | 0.71667
|  |  |  | Rework | 5 | 0.8
|  |  |  | Weather | 5 | 0.88333
|  |  |  | Design Change | 4 | 0.95
|  |  |  | Subcontractor Default | 3 | 1
T6 Delay days by activity (P06 Q5)
|  |  |  | Activity | Delay Days
|  |  |  | Foundation | 128
|  |  |  | Superstructure | 84
|  |  |  | MEP Rough-In | 201
|  |  |  | Facade Installation | 133
|  |  |  | Interior Works | 182
|  |  |  | External Works | 143
|  |  |  | Landscape | 183
|  |  |  | Testing & Commissioning | 291
|  |  |  | Handover Prep | 122
3. SCHEDULE & DELAY ROOT CAUSE — 1,467 delay days explained |  |  |  | T7 EVM S-curve (P12 Q4)
|  |  |  | Month | PV | EV | AC
|  |  |  | Month 1 | 713955 | 583077 | 559427
|  |  |  | Month 2 | 1375080 | 1314419 | 1552686
|  |  |  | Month 3 | 1996674 | 1848591 | 2172516
|  |  |  | Month 4 | 2659718 | 2790438 | 2676937
|  |  |  | Month 5 | 3522912 | 3497510 | 3244267
|  |  |  | Month 6 | 4311364 | 4279745 | 4009086
|  |  |  | Month 7 | 5076108 | 3884193 | 4572625
|  |  |  | Month 8 | 5518420 | 5338129 | 5598832
|  |  |  | Month 9 | 6176705 | 5423142 | 5456673
|  |  |  | Month 10 | 7227989 | 6017261 | 6220665
|  |  |  | Month 11 | 7370482 | 6885739 | 7471668
|  |  |  | Month 12 | 8456065 | 7607646 | 8861641
|  |  |  | Month 13 | 9008847 | 6993716 | 7097954
|  |  |  | Month 14 | 9643700 | 9092039 | 10357281
|  |  |  | Month 15 | 10155362 | 10645116 | 11316790
|  |  |  | Month 16 | 10577255 | 9146675 | 10189498
|  |  |  | Month 17 | 11781571 | 11598138 | 11635370
|  |  |  | Month 18 | 12582063 | 10650481 | 10449513
|  |  |  | Month 19 | 12569110 | 11678398 | 10613223
4. EARNED VALUE & PROJECT HEALTH — are we on cost and on time? |  |  |  | Month 20 | 14320401 | 11947221 | 13650848
|  |  |  | Month 21 | 14542039 | 12465870 | 13403261
|  |  |  | Month 22 | 14869497 | 11864184 | 11559952
|  |  |  | Month 23 | 15558785 | 14160157 | 16105354
|  |  |  | Month 24 | 17061766 | 16707135 | 19786940
|  |  |  | Month 25 | 17492521 | 18276175 | 18578220
|  |  |  | Month 26 | 18841344 | 19735602 | 18790535
|  |  |  | Month 27 | 18256033 | 15433674 | 17307808
|  |  |  | Month 28 | 19169856 | 17779442 | 19753597
|  |  |  | Month 29 | 19840193 | 18258838 | 17211341
|  |  |  | Month 30 | 21767434 | 21789398 | 24907904
|  |  |  | Month 31 | 22540417 | 20571227 | 19597529
|  |  |  | Month 32 | 21195474 | 16253757 | 17562165
|  |  |  | Month 33 | 21816501 | 19490789 | 19481437
|  |  |  | Month 34 | 23880595 | 23687965 | 23740734
|  |  |  | Month 35 | 23521603 | 23303495 | 27042893
|  |  |  | Month 36 | 23898889 | 18983212 | 21098110
T8 SPI vs CPI bubble (P15 Q4)
|  |  |  | SPI | CPI | Budget USD
|  |  |  | 0.91 | 0.79 | 95528859
5. CASH FLOW & RECEIVABLES — the liquidity problem |  |  |  | 1 | 1.12 | 93252435
|  |  |  | 1.06 | 0.99 | 60343779
|  |  |  | 0.9 | 1.04 | 53319528
|  |  |  | 0.81 | 1.09 | 45512501
|  |  |  | 0.78 | 0.86 | 17655004
|  |  |  | 1.16 | 1.04 | 17335296
|  |  |  | 1.11 | 0.79 | 97555887
|  |  |  | 1.16 | 0.88 | 15533057
|  |  |  | 1.02 | 1 | 92614538
|  |  |  | 0.86 | 1.03 | 47857940
|  |  |  | 0.75 | 0.92 | 84877290
|  |  |  | 0.72 | 0.91 | 16079017
|  |  |  | 0.77 | 0.97 | 98666595
|  |  |  | 0.96 | 0.85 | 80318641
|  |  |  | 0.88 | 0.83 | 20103503
|  |  |  | 1.1 | 1 | 51938140
|  |  |  | 1.06 | 0.78 | 96987358
|  |  |  | 1.1 | 0.87 | 43612439
|  |  |  | 0.96 | 0.85 | 77209870
|  |  |  | 0.96 | 0.85 | 83249598
|  |  |  | 0.7 | 0.91 | 12124981
6. PROCUREMENT & SUBCONTRACTOR PERFORMANCE — the supply-side risk |  |  |  | 1.19 | 0.95 | 44258091
|  |  |  | 0.93 | 1.12 | 30020518
|  |  |  | 0.78 | 0.89 | 49770958
T9 Monthly net cash flow (P07 Q3)
|  |  |  | Month | WT-DC-MUM-01 | WT-OFF-SYD-02 | WT-HOS-AKL-03 | WT-ITP-BLR-04 | All Projects
|  |  |  | 2024-01 | -574274 | -1317584 | -595005 | 545759 | -1941104
|  |  |  | 2024-02 | -868853 | 836765 | -533153 | -3935 | -569176
|  |  |  | 2024-03 | -221231 | 586100 | 61735 | -186915 | 239689
|  |  |  | 2024-04 | 1074695 | -455351 | -572862 | -1331420 | -1284938
|  |  |  | 2024-05 | 389471 | 502180 | 579339 | -107332 | 1363658
|  |  |  | 2024-06 | 676310 | 767572 | -68464 | -1097039 | 278379
|  |  |  | 2024-07 | 147369 | -195047 | 102073 | 103162 | 157557
|  |  |  | 2024-08 | -30373 | -1056516 | -436762 | 596012 | -927639
|  |  |  | 2024-09 | -576106 | 226548 | -958914 | -810634 | -2119106
|  |  |  | 2024-10 | 701779 | 73497 | -345897 | -1038711 | -609332
|  |  |  | 2024-11 | 674262 | -824642 | -106806 | 447192 | 190006
|  |  |  | 2024-12 | -553291 | -533709 | -992486 | -14995 | -2094481
T10 Receivables aging (P14 Q3)
|  |  |  | Aging Bucket | Outstanding USD
7. VARIATIONS & PORTFOLIO MIX — exposure and where projects sit |  |  |  | 0–30 days | 998469
|  |  |  | 31–60 days | 3071180
|  |  |  | 61–90 days | 0
|  |  |  | 90+ days | 6831506
T11 Supplier on-time delivery (P13 Q2)
|  |  |  | Supplier | On-time %
|  |  |  | Supplier-A | 0.33333
|  |  |  | Supplier-B | 0
|  |  |  | Supplier-C | 0.4
|  |  |  | Supplier-D | 0.4
|  |  |  | Supplier-E | 0.28571
|  |  |  | Supplier-F | 0.375
|  |  |  | Supplier-G | 0.16667
|  |  |  | Supplier-H | 0
|  |  |  | Supplier-I | 0.14286
|  |  |  | Supplier-J | 0.42857
T12 Top subcontractor profile (P09 Q4)
|  |  |  | Dimension | Score (out of 5)
|  |  |  | Quality | 4
8. KEY FINDINGS & ACTIONS — what the analysis report proves |  |  |  | Time | 3.2
|  |  |  | Safety | 4.2
COST — 90.0% of projects (45 of 50) finished over budget; portfolio overrun 17.6% = $37,95,48,193. Worst type: Residential Tower at 26.3%. ACTION: re-baseline estimates for tower / campus / hospital typologies. |  |  |  | Cost | 4.6
GEOGRAPHY — Australia builds at $3,677/sqm vs India at $670/sqm; New Zealand carries the highest average overrun at 19.7%. ACTION: use the P10 benchmark grid as the rate base for new pursuits. |  |  |  | Communication | 3.3
SCHEDULE — 1,467 delay days cost $2,20,05,000 at $15k/day. Top cause: RFI Response Delay (11 events); worst activity: Testing & Commissioning. ACTION: 7-day RFI SLA and early commissioning mobilisation.
EARNED VALUE — CPI has fallen to 0.90 with 25 of 36 months below 1.00; EAC $2,77,85,221 vs BAC $2,50,00,000 = 11.1% overrun. ACTION: value-engineering to recover $30,79,805. |  |  |  | T13 Variation order value by status (P08 Q6)
CASH — 2024 closed at ($73,16,487) net, collections only 76.9% of forecast and 17 project-months below 70% of plan. ACTION: milestone-linked billing and a rolling 13-week cash forecast. |  |  |  | Project | Approved | Pending | Under Review | Rejected
RECEIVABLES — $1,18,56,858 outstanding, of which $68,31,506 (57.6%) is 90+ days overdue; interest claimable $7,97,715. ACTION: escalate Brookfield and Tata Realty balances now. |  |  |  | WT-DC-MUM-01 | 791101 | 758642 | 675467 | -142038
PROCUREMENT — 70.0% of POs delivered late (avg 5.9 days); no supplier rates A on on-time delivery. ACTION: dual-source Copper Wiring and Tiles, add buffer float to long-lead packages. |  |  |  | WT-OFF-SYD-02 | 583674 | 0 | 577493 | 3723549
PORTFOLIO — 11 of 25 projects are late AND over cost ($63,55,84,316 of budget), 3 are red-zone and 8 on hold tie up $50,58,48,491. ACTION: recovery plans before taking new work. |  |  |  | WT-HOS-AKL-03 | 1919398 | 449749 | 158155 | 1081459
|  |  |  | WT-RES-MEL-05 | 892260 | 114455 | 563191 | 2200179
T14 Portfolio status mix (P15 Q1)
|  |  |  | Status | Projects
|  |  |  | In Progress | 4
|  |  |  | On Hold | 8
|  |  |  | Completed | 8
|  |  |  | Planning | 5
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## P01-CostOverrun
c
Scenario: WT manages 50 projects across India, Australia & NZ. Analyse which projects exceeded budget and why.
Project_ID | Project_Name | City | Country | Type | Budgeted_Cost_USD | Actual_Cost_USD | Duration_Months | Variance_USD | Variance_% | Absolute_Variance_USD
WT-1028 | Residential Tower Per-29 | Perth | Australia | Residential Tower | 74394227 | 99048466 | 39 | 24654239 | 33.14% | 24654239
WT-1032 | Residential Tower Hyd-33 | Hyderabad | India | Residential Tower | 65791320 | 87419523 | 16 | 21628203 | 32.87% | 21628203
WT-1033 | IT Park Syd-34 | Sydney | Australia | IT Park | 58792612 | 78531947 | 40 | 19739335 | 33.57% | 19739335
WT-1034 | University Campus Kol-35 | Kolkata | India | University Campus | 55551839 | 74887197 | 47 | 19335358 | 34.81% | 19335358
WT-1043 | Industrial Warehouse Can-44 | Canberra | Australia | Industrial Warehouse | 64682989 | 83799056 | 9 | 19116067 | 29.55% | 19116067
WT-1031 | Data Centre Del-32 | Delhi | India | Data Centre | 67228535 | 85811127 | 40 | 18582592 | 27.64% | 18582592
WT-1024 | Data Centre Mum-25 | Mumbai | India | Data Centre | 74070937 | 92614679 | 47 | 18543742 | 25.04% | 18543742
WT-1026 | University Campus Mum-27 | Mumbai | India | University Campus | 69187530 | 86815466 | 38 | 17627936 | 25.48% | 17627936
WT-1049 | Hospital Auc-50 | Auckland | New Zealand | Hospital | 55826716 | 73187548 | 16 | 17360832 | 31.1% | 17360832
WT-1027 | University Campus Che-28 | Chennai | India | University Campus | 70137358 | 83715114 | 15 | 13577756 | 19.36% | 13577756
WT-1044 | Commercial Office Che-45 | Chennai | India | Commercial Office | 56038913 | 69560286 | 12 | 13521373 | 24.13% | 13521373
WT-1015 | Hospital Chr-16 | Christchurch | New Zealand | Hospital | 45524491 | 58596428 | 9 | 13071937 | 28.71% | 13071937
WT-1011 | University Campus Ade-12 | Adelaide | Australia | University Campus | 62855700 | 75695471 | 29 | 12839771 | 20.43% | 12839771
WT-1004 | Hospital Can-5 | Canberra | Australia | Hospital | 62291817 | 73859798 | 6 | 11567981 | 18.57% | 11567981
WT-1022 | Residential Tower Hyd-23 | Hyderabad | India | Residential Tower | 58661351 | 69722747 | 30 | 11061396 | 18.86% | 11061396
WT-1023 | Hotel Ade-24 | Adelaide | Australia | Hotel | 64820592 | 75298564 | 41 | 10477972 | 16.16% | 10477972
WT-1007 | Hotel Per-8 | Perth | Australia | Hotel | 37503389 | 47736237 | 35 | 10232848 | 27.29% | 10232848
WT-1035 | Metro Station Per-36 | Perth | Australia | Metro Station | 71467853 | 80801158 | 21 | 9333305 | 13.06% | 9333305
WT-1019 | IT Park Chr-20 | Christchurch | New Zealand | IT Park | 37264581 | 46536214 | 33 | 9271633 | 24.88% | 9271633
WT-1041 | Metro Station Ham-42 | Hamilton | New Zealand | Metro Station | 34614537 | 43747505 | 32 | 9132968 | 26.38% | 9132968
WT-1003 | IT Park Mum-4 | Mumbai | India | IT Park | 28687537 | 35469495 | 40 | 6781958 | 23.64% | 6781958
WT-1029 | Hotel Mum-30 | Mumbai | India | Hotel | 45507489 | 52126202 | 13 | 6618713 | 14.54% | 6618713
WT-1009 | Hotel Per-10 | Perth | Australia | Hotel | 27808537 | 34255354 | 8 | 6446817 | 23.18% | 6446817
WT-1046 | Residential Tower Can-47 | Canberra | Australia | Residential Tower | 39385696 | 44704782 | 10 | 5319086 | 13.51% | 5319086
WT-1025 | Data Centre Bri-26 | Brisbane | Australia | Data Centre | 41392920 | 46521755 | 35 | 5128835 | 12.39% | 5128835
WT-1016 | Commercial Office Ahm-17 | Ahmedabad | India | Commercial Office | 44339391 | 49237382 | 10 | 4897991 | 11.05% | 4897991
WT-1040 | IT Park Kol-41 | Kolkata | India | IT Park | 19758595 | 24487637 | 42 | 4729042 | 23.93% | 4729042
WT-1045 | Hospital Ahm-46 | Ahmedabad | India | Hospital | 27529407 | 32058388 | 14 | 4528981 | 16.45% | 4528981
WT-1013 | Hotel Del-14 | Delhi | India | Hotel | 24969840 | 29056302 | 21 | 4086462 | 16.37% | 4086462
WT-1010 | University Campus Ahm-11 | Ahmedabad | India | University Campus | 12709497 | 16422285 | 12 | 3712788 | 29.21% | 3712788
WT-1021 | Metro Station Wel-22 | Wellington | New Zealand | Metro Station | 14201654 | 17784913 | 13 | 3583259 | 25.23% | 3583259
WT-1038 | Hospital Ban-39 | Bangalore | India | Hospital | 11046318 | 14494625 | 27 | 3448307 | 31.22% | 3448307
WT-1042 | Data Centre Kol-43 | Kolkata | India | Data Centre | 15009833 | 18215829 | 28 | 3205996 | 21.36% | 3205996
WT-1014 | Metro Station Pun-15 | Pune | India | Metro Station | 52929647 | 55998461 | 46 | 3068814 | 5.798% | 3068814
WT-1005 | Industrial Warehouse Pun-6 | Pune | India | Industrial Warehouse | 47667651 | 50582458 | 19 | 2914807 | 6.115% | 2914807
WT-1001 | IT Park Che-2 | Chennai | India | IT Park | 13668732 | 16213808 | 8 | 2545076 | 18.62% | 2545076
WT-1039 | IT Park Del-40 | Delhi | India | IT Park | 33944441 | 36028320 | 37 | 2083879 | 6.139% | 2083879
WT-1036 | Data Centre Ahm-37 | Ahmedabad | India | Data Centre | 47377076 | 45406838 | 41 | -1970238 | -4.159% | 1970238
WT-1020 | Industrial Warehouse Ham-21 | Hamilton | New Zealand | Industrial Warehouse | 50586340 | 52494876 | 14 | 1908536 | 3.773% | 1908536
WT-1000 | Commercial Office Che-1 | Chennai | India | Commercial Office | 38913810 | 40779989 | 14 | 1866179 | 4.796% | 1866179
WT-1012 | Shopping Mall Pun-13 | Pune | India | Shopping Mall | 49683626 | 51363072 | 23 | 1679446 | 3.38% | 1679446
WT-1017 | Hotel Kol-18 | Kolkata | India | Hotel | 44235350 | 45785826 | 37 | 1550476 | 3.505% | 1550476
WT-1037 | Hotel Ahm-38 | Ahmedabad | India | Hotel | 31557077 | 30069991 | 46 | -1487086 | -4.712% | 1487086
WT-1006 | Data Centre Bri-7 | Brisbane | Australia | Data Centre | 14448136 | 15921425 | 28 | 1473289 | 10.2% | 1473289
WT-1002 | Data Centre Mum-3 | Mumbai | India | Data Centre | 31345092 | 32694948 | 44 | 1349856 | 4.306% | 1349856
WT-1018 | Metro Station Ade-19 | Adelaide | Australia | Metro Station | 21175900 | 22360735 | 21 | 1184835 | 5.595% | 1184835
WT-1008 | Data Centre Chr-9 | Christchurch | New Zealand | Data Centre | 52806024 | 51830172 | 24 | -975852 | -1.848% | 975852
WT-1030 | University Campus Per-31 | Perth | Australia | University Campus | 34138745 | 33222804 | 42 | -915941 | -2.683% | 915941
WT-1048 | Data Centre Mum-49 | Mumbai | India | Data Centre | 33726318 | 34283626 | 37 | 557308 | 1.652% | 557308
WT-1047 | IT Park Gol-48 | Gold Coast | Australia | IT Park | 15141087 | 14690417 | 40 | -450670 | -2.976% | 450670
ANALYSIS QUESTIONS
Q1. Which country has the highest average cost overrun percentage?
Q2. What is the total budget vs actual cost for each project type? Which type has the worst variance?
Q3. Identify the Top 5 projects with the highest absolute cost overrun (in USD).
Q4. Is there a correlation between project duration and cost overrun percentage?
Q5. Create a pivot table showing average overrun % by Country × Project Type.
Q6. What percentage of projects came in under budget vs over budget?
Q7. Which city has the most cost-efficient project delivery?

## P01
Cost Over Run Analysis
Q1
Country | Average of Variance_%
Australia | 16.73%
India | 15.76%
New Zealand | 19.75%
Grand Total | 16.61%
The Country with the highest average cost overrun percentage is Newzealand, with an average overrun of 19.75%
Q2
Project Type | Total Budget | Actual Cost | Total Variance | Average of Variance_%
Commercial Office | 139292114 | 159577657 | 20285543 | 13.32%
Data Centre | 377404871 | 423300399 | 45895528 | 10.73%
Hospital | 202218749 | 252196787 | 49978038 | 25.21%
Hotel | 276402274 | 314328476 | 37926202 | 13.76%
Industrial Warehouse | 162936980 | 186876390 | 23939410 | 13.15%
IT Park | 207257585 | 251957838 | 44700253 | 18.26%
Metro Station | 194389591 | 220692772 | 26303181 | 15.21%
Residential Tower | 238232594 | 300895518 | 62662924 | 24.59%
Shopping Mall | 49683626 | 51363072 | 1679446 | 3.38%
University Campus | 304580669 | 370758337 | 66177668 | 21.1%
Grand Total | 2152399053 | 2531947246 | 379548193 | 16.61%
Hospital has the worst variance percentage with an average cost overrun of 25.21%. But university campus has the highest total cost variance at USD 66,177,668.
Q3
Residential Tower Per-29
Residential Tower Hyd-33 | This Five project are having highest absolute cost over run variance in USD, this found by sorting and highlighted via conditional formatting of top 5.
IT Park Syd-34
University Campus Kol-35
Industrial Warehouse Can-44
Q4
-0.15638
There is a weak negative correlation (-0.156) between project duration and cost overrun percentage. This suggests that longer project durations are slightly associated with lower cost overrun percentages in this dataset. However, the relationship is very weak and does not establish causation.
Q5
Average of Variance_% | Column Labels
Row Labels | Commercial Office | Data Centre | Hospital | Hotel | Industrial Warehouse | IT Park | Metro Station | Residential Tower | Shopping Mall | University Campus | Grand Total
Australia |  | 11.29% | 18.57% | 22.21% | 29.55% | 15.3% | 9.327% | 23.32% |  | 8.872% | 16.73%
India | 13.32% | 12.64% | 23.83% | 7.426% | 6.115% | 18.08% | 5.798% | 25.87% | 3.38% | 27.21% | 15.76%
New Zealand |  | -1.848% | 29.91% |  | 3.773% | 24.88% | 25.81% |  |  |  | 19.75%
Grand Total | 13.32% | 10.73% | 25.21% | 13.76% | 13.15% | 18.26% | 15.21% | 24.59% | 3.38% | 21.1% | 16.61%
New Zealand has the highest overall average cost overrun (19.75%). Hospital projects in New Zealand show the highest country-type average (29.91%).
Q6
Total Project | Over Budget | Under Budget | On Budget
50 | 90% | 10% | 0%
Out of 50 projects, 90% (45 projects) exceeded their budget, while 10% (5 projects) were completed under budget. No projects were completed exactly on budget.
City | Average of Variance_%
Gold Coast | -2.976%
Pune | 5.098%
Ahmedabad | 9.568%
Brisbane | 11.29%
Adelaide | 14.06% | The city with the lowest average cost overrun percentage is Gold coast and Pune, with an average overrun of -2.98% and 5.10% respectively.
Hamilton | 15.08%
Mumbai | 15.78%
Delhi | 16.72%
Chennai | 16.73%
Christchurch | 17.25%
Perth | 18.8%
Canberra | 20.54%
Kolkata | 20.9%
Wellington | 25.23%
Hyderabad | 25.87%
Auckland | 31.1%
Bangalore | 31.22%
Sydney | 33.57%
Grand Total | 16.61%

## P02-MaterialPrice
PROBLEM 2: Material Price Fluctuation Tracker
Scenario: Track monthly prices of 15 key construction materials over 18 months to forecast procurement budgets.
Month | Material | Unit | Base_Price_USD | Current_Price_USD | Supplier_City | Country | Price_Change_% | Procurement Risk
2024-04 | Waterproofing Membrane | sqm | 15 | 18.73 | Delhi | India | 24.87% | high risk
2024-09 | Cement (OPC 53) | MT | 85 | 105.52 | Hyderabad | India | 24.14% | high risk
2025-01 | Aluminium Facade | sqm | 120 | 147.98 | Brisbane | Australia | 23.32% | high risk
2024-03 | Bricks (AAC) | 1000 nos | 380 | 467.68 | Hamilton | New Zealand | 23.07% | high risk
2024-05 | Tiles (Vitrified) | sqm | 18 | 22.1 | Delhi | India | 22.78% | high risk
2024-09 | PVC Conduits | m | 3 | 3.68 | Ahmedabad | India | 22.67% | high risk
2024-02 | Sand (River) | cum | 25 | 30.58 | Wellington | New Zealand | 22.32% | high risk
2024-05 | Structural Steel | MT | 950 | 1149.65 | Perth | Australia | 21.02% | high risk
2024-11 | Aggregate (20mm) | cum | 22 | 26.52 | Sydney | Australia | 20.55% | high risk
2025-05 | Cement (OPC 53) | MT | 85 | 102.04 | Delhi | India | 20.05% | high risk
2024-05 | Aluminium Facade | sqm | 120 | 143.42 | Melbourne | Australia | 19.52% | high risk
2025-03 | MS Pipes | m | 12 | 14.34 | Melbourne | Australia | 19.5% | high risk
2024-07 | Aluminium Facade | sqm | 120 | 143.24 | Bangalore | India | 19.37% | high risk
2025-04 | RMC M30 | cum | 75 | 88.96 | Hyderabad | India | 18.61% | high risk
2024-10 | Aggregate (20mm) | cum | 22 | 26.06 | Ahmedabad | India | 18.45% | high risk
2025-03 | Aluminium Facade | sqm | 120 | 141.52 | Brisbane | Australia | 17.93% | high risk
2024-10 | RMC M30 | cum | 75 | 88.36 | Canberra | Australia | 17.81% | high risk
2024-09 | Aggregate (20mm) | cum | 22 | 25.9 | Canberra | Australia | 17.73% | high risk
2024-06 | Tiles (Vitrified) | sqm | 18 | 20.97 | Hyderabad | India | 16.5% | high risk
2024-06 | PVC Conduits | m | 3 | 3.47 | Kolkata | India | 15.67% | high risk
2025-01 | MS Pipes | m | 12 | 13.76 | Kolkata | India | 14.67% | Normal
2025-02 | Aluminium Facade | sqm | 120 | 137.22 | Pune | India | 14.35% | Normal
2025-03 | Tiles (Vitrified) | sqm | 18 | 20.57 | Wellington | New Zealand | 14.28% | Normal
2025-04 | Sand (River) | cum | 25 | 28.55 | Ahmedabad | India | 14.2% | Normal
2024-04 | Bricks (AAC) | 1000 nos | 380 | 433.83 | Melbourne | Australia | 14.17% | Normal
2025-06 | Glass (DGU) | sqm | 95 | 108.33 | Christchurch | New Zealand | 14.03% | Normal
2024-09 | Copper Wiring | m | 8 | 9.12 | Perth | Australia | 14% | Normal
2024-01 | Cement (OPC 53) | MT | 85 | 96.77 | Auckland | New Zealand | 13.85% | Normal
2025-04 | Plywood (Marine) | sheet | 45 | 51.18 | Melbourne | Australia | 13.73% | Normal
2024-03 | Glass (DGU) | sqm | 95 | 108.01 | Hamilton | New Zealand | 13.69% | Normal
2024-07 | Plywood (Marine) | sheet | 45 | 50.86 | Sydney | Australia | 13.02% | Normal
2024-03 | Structural Steel | MT | 950 | 1068.18 | Canberra | Australia | 12.44% | Normal
2024-05 | RMC M30 | cum | 75 | 84.14 | Wellington | New Zealand | 12.19% | Normal
2024-02 | Cement (OPC 53) | MT | 85 | 94.59 | Wellington | New Zealand | 11.28% | Normal
2024-08 | Tiles (Vitrified) | sqm | 18 | 20.02 | Hyderabad | India | 11.22% | Normal
2024-01 | Plywood (Marine) | sheet | 45 | 50 | Christchurch | New Zealand | 11.11% | Normal
2024-08 | RMC M30 | cum | 75 | 82.88 | Chennai | India | 10.51% | Normal
2025-02 | Bricks (AAC) | 1000 nos | 380 | 419.12 | Kolkata | India | 10.29% | Normal
2024-08 | Plywood (Marine) | sheet | 45 | 49.5 | Perth | Australia | 10% | Normal
2024-03 | TMT Steel (Fe500) | MT | 650 | 710.14 | Sydney | Australia | 9.252% | Normal
2025-04 | Aggregate (20mm) | cum | 22 | 23.98 | Brisbane | Australia | 9% | Normal
2025-02 | MS Pipes | m | 12 | 13.05 | Canberra | Australia | 8.75% | Normal
2025-05 | Plywood (Marine) | sheet | 45 | 48.74 | Ahmedabad | India | 8.311% | Normal
2025-03 | Glass (DGU) | sqm | 95 | 101.98 | Gold Coast | Australia | 7.347% | Normal
2025-06 | Aggregate (20mm) | cum | 22 | 23.61 | Christchurch | New Zealand | 7.318% | Normal
2024-04 | Sand (River) | cum | 25 | 26.77 | Delhi | India | 7.08% | Normal
2025-06 | TMT Steel (Fe500) | MT | 650 | 695.91 | Gold Coast | Australia | 7.063% | Normal
2025-05 | Waterproofing Membrane | sqm | 15 | 16.05 | Hamilton | New Zealand | 7% | Normal
2024-12 | Cement (OPC 53) | MT | 85 | 90.44 | Wellington | New Zealand | 6.4% | Normal
2024-08 | Glass (DGU) | sqm | 95 | 100.87 | Bangalore | India | 6.179% | Normal
2025-02 | TMT Steel (Fe500) | MT | 650 | 688.19 | Adelaide | Australia | 5.875% | Normal
2024-11 | Structural Steel | MT | 950 | 998.92 | Sydney | Australia | 5.149% | Normal
2024-10 | Glass (DGU) | sqm | 95 | 99.39 | Bangalore | India | 4.621% | Normal
2025-01 | Structural Steel | MT | 950 | 988.18 | Delhi | India | 4.019% | Normal
2024-11 | PVC Conduits | m | 3 | 3.11 | Ahmedabad | India | 3.667% | Normal
2024-11 | Waterproofing Membrane | sqm | 15 | 15.54 | Wellington | New Zealand | 3.6% | Normal
2024-12 | Copper Wiring | m | 8 | 8.27 | Brisbane | Australia | 3.375% | Normal
2025-02 | Copper Wiring | m | 8 | 8.22 | Melbourne | Australia | 2.75% | Normal
2025-03 | Waterproofing Membrane | sqm | 15 | 15.22 | Canberra | Australia | 1.467% | Normal
2024-01 | Glass (DGU) | sqm | 95 | 96.34 | Christchurch | New Zealand | 1.411% | Normal
2024-05 | Waterproofing Membrane | sqm | 15 | 15.21 | Gold Coast | Australia | 1.4% | Normal
2024-06 | Aluminium Facade | sqm | 120 | 121.18 | Kolkata | India | 0.9833% | Normal
2024-10 | Waterproofing Membrane | sqm | 15 | 15.12 | Chennai | India | 0.8% | Normal
2024-04 | Structural Steel | MT | 950 | 957.27 | Hyderabad | India | 0.7653% | Normal
2024-06 | Bricks (AAC) | 1000 nos | 380 | 382.76 | Chennai | India | 0.7263% | Normal
2025-06 | PVC Conduits | m | 3 | 3.01 | Chennai | India | 0.3333% | Normal
2024-07 | Bricks (AAC) | 1000 nos | 380 | 381.09 | Bangalore | India | 0.2868% | Normal
2024-03 | PVC Conduits | m | 3 | 3 | Bangalore | India | 0% | Normal
2024-11 | Plywood (Marine) | sheet | 45 | 44.71 | Kolkata | India | -0.6444% | Normal
2025-06 | Waterproofing Membrane | sqm | 15 | 14.88 | Wellington | New Zealand | -0.8% | Normal
2024-01 | Aluminium Facade | sqm | 120 | 119.02 | Bangalore | India | -0.8167% | Normal
2024-09 | Aluminium Facade | sqm | 120 | 118.72 | Ahmedabad | India | -1.067% | Normal
2025-05 | Structural Steel | MT | 950 | 934.96 | Adelaide | Australia | -1.583% | Normal
2024-12 | Bricks (AAC) | 1000 nos | 380 | 371.99 | Sydney | Australia | -2.108% | Normal
2024-02 | Copper Wiring | m | 8 | 7.78 | Wellington | New Zealand | -2.75% | Normal
2024-01 | Waterproofing Membrane | sqm | 15 | 14.57 | Melbourne | Australia | -2.867% | Normal
2025-05 | MS Pipes | m | 12 | 11.62 | Mumbai | India | -3.167% | Normal
2024-12 | Glass (DGU) | sqm | 95 | 91.02 | Sydney | Australia | -4.189% | Normal
2024-06 | Cement (OPC 53) | MT | 85 | 81.11 | Hyderabad | India | -4.576% | Normal
2024-07 | Waterproofing Membrane | sqm | 15 | 14.26 | Canberra | Australia | -4.933% | Normal
2025-04 | PVC Conduits | m | 3 | 2.85 | Ahmedabad | India | -5% | Normal
2024-02 | Waterproofing Membrane | sqm | 15 | 14.2 | Pune | India | -5.333% | Normal
2024-08 | Sand (River) | cum | 25 | 23.62 | Hyderabad | India | -5.52% | Normal
2024-02 | PVC Conduits | m | 3 | 2.83 | Delhi | India | -5.667% | Normal
2025-01 | TMT Steel (Fe500) | MT | 650 | 607.52 | Canberra | Australia | -6.535% | Normal
2024-12 | Tiles (Vitrified) | sqm | 18 | 16.79 | Canberra | Australia | -6.722% | Normal
2024-10 | PVC Conduits | m | 3 | 2.78 | Brisbane | Australia | -7.333% | Normal
2024-04 | Copper Wiring | m | 8 | 7.38 | Hamilton | New Zealand | -7.75% | Normal
2024-07 | Tiles (Vitrified) | sqm | 18 | 16.58 | Hyderabad | India | -7.889% | Normal
2025-01 | Glass (DGU) | sqm | 95 | 87.45 | Christchurch | New Zealand | -7.947% | Normal
ANALYSIS QUESTIONS
Q1. Which material has shown the highest average price increase over 18 months?
Q2. Create a line chart showing monthly price trend for TMT Steel and Cement.
Q3. Which country has the most volatile material pricing? (Use standard deviation)
Q4. Identify the top 3 materials with price increase > 15% — flag them as procurement risk.
Q5. What is the average price change % by material across all months?
Q6. If WT needs 500 MT of steel next quarter, what is the projected cost based on the trend?

## P02
Material Price Fluctuation
Q1
Materials | Average of Price_Change_%
Aggregate (20mm) | 14.61%
Aluminium Facade | 11.7%
Bricks (AAC) | 7.74%
Cement (OPC 53) | 11.86%
Copper Wiring | 1.925%
Glass (DGU) | 4.393% | RMC M30 has shown the highest average price increase over the 18 month period, with an average price increase of 14.78%.
MS Pipes | 9.938%
Plywood (Marine) | 9.256%
PVC Conduits | 3.042%
RMC M30 | 14.78%
Sand (River) | 9.52%
Structural Steel | 6.968%
Tiles (Vitrified) | 8.361%
TMT Steel (Fe500) | 3.914%
Waterproofing Membrane | 2.52%
Grand Total | 7.54%
Q2
Average of Current_Price_USD | Material Filter
Month timeline | Cement (OPC 53) | TMT Steel (Fe500) | Grand Total
2024-01 | 96.77 | 1 | 96.77
2024-02 | 94.59 | 1 | 94.59
2024-03 | 1 | 710.14 | 710.14
2024-06 | 81.11 | 1 | 81.11
2024-09 | 105.52 | 1 | 105.52
2024-12 | 90.44 | 1 | 90.44
2025-01 | 1 | 607.52 | 607.52
2025-02 | 1 | 688.19 | 688.19 | The line chart illustrates the monthly price trends of TMT Steel and Cement over the 18-month period. It helps identify price fluctuations and changes in procurement costs over time.
2025-05 | 102.04 | 1 | 102.04
2025-06 | 1 | 695.91 | 695.91
Grand Total | 95.0783 | 675.44 | 327.223
Q3
Country | StdDev of Price_Change_%
Australia | 9.21% | India has the most volatile material prices, with a standard deviation of 9.79%, indicating greater fluctuations in price changes compared to other countries.
India | 9.792%
New Zealand | 8.992%
Grand Total | 9.33%
Q4
Row Labels | Max of Price_Change_%
Waterproofing Membrane | 24.87%
Cement (OPC 53) | 24.14%
Aluminium Facade | 23.32% | The top 3 materials with price increases exceeding 15% are Waterproffing, Cement, and Alluminium. These materials are flagged as procurement risks due to significant price increases.
Bricks (AAC) | 23.07%
Tiles (Vitrified) | 22.78%
PVC Conduits | 22.67%
Sand (River) | 22.32%
Structural Steel | 21.02%
Aggregate (20mm) | 20.55%
MS Pipes | 19.5%
RMC M30 | 18.61%
Glass (DGU) | 14.03%
Copper Wiring | 14%
Plywood (Marine) | 13.73%
TMT Steel (Fe500) | 9.252%
Grand Total | 24.87%
Q5
Materials | Average of Price_Change_%
RMC M30 | 14.78%
Aggregate (20mm) | 14.61%
Cement (OPC 53) | 11.86%
Aluminium Facade | 11.7% | The average price change for each material was calculated across the 18-month period using the Average function in a Pivot Table. RMC M30 experienced the highest average price change, while Copper wiring experienced the lowest.
MS Pipes | 9.938%
Sand (River) | 9.52%
Plywood (Marine) | 9.256%
Tiles (Vitrified) | 8.361%
Bricks (AAC) | 7.74%
Structural Steel | 6.968%
Glass (DGU) | 4.393%
TMT Steel (Fe500) | 3.914%
PVC Conduits | 3.042%
Waterproofing Membrane | 2.52%
Copper Wiring | 1.925%
Grand Total | 7.54%
Q6
Average of Current_Price_USD | TMT Steel Material
Month | TMT Steel (Fe500) | Grand Total
2024-03 | 710.14 | 710.14
2025-01 | 607.52 | 607.52
2025-02 | 688.19 | 688.19
2025-06 | 695.91 | 695.91
Grand Total | 675.44 | 675.44
Month Index | Month | AVG TMT Price | forecast
1 | 2024-01 |  | 662.1343
2 | 2024-02 |  | 684.9441
3 | 2024-03 | 710.14 | 658.3326
4 | 2024-04
5 | 2024-05
6 | 2024-06 |  |  | 334235.1639
7 | 2024-07
8 | 2024-08
9 | 2024-09 |  |  | Based on the historical TMT Steel price trend, the projected average price for the next quarter is approximately $668.47 per MT. For a requirement of 500 MT, the estimated procurement cost is approximately $334,235.16.
10 | 2024-10
11 | 2024-11
12 | 2024-12
13 | 2025-01 | 607.52
14 | 2025-02 | 688.19
15 | 2025-03
16 | 2025-04
17 | 2025-05
18 | 2025-06 | 695.91
Formulas:
Cement (OPC 53) = TEXT(EDATE(DATE(2024,1,1),[Month timeline]-1),"yyyy-mm")

## P03-BOQVariance
PROBLEM 3: BOQ (Bill of Quantities) Variance Analysis
Scenario: Compare original BOQ quantities vs actual measured quantities for 3 projects across 20 trade items each.
Project_ID | Trade | BOQ_Item | Unit | BOQ_Qty | Actual_Qty | Rate_USD | BOQ_Amount_USD | Actual_Amount_USD | Qty_Variance | Qty_Variance_% | Qty_Status | Overrun_Imapact_USD
WT-HOS-AKL-03 | Civil & Structure | Plastering | rmt | 4879 | 6291 | 107.3 | 523516.7 | 675024.3 | 1412 | 28.94% | Over BOQ | 151507.6
WT-OFF-SYD-02 | MEP - Electrical | LT Panels | set | 4324 | 5554 | 57.67 | 249365.08 | 320299.18 | 1230 | 28.45% | Over BOQ | 70934.1
WT-DC-MUM-01 | Civil & Structure | Excavation | kg | 2649 | 3384 | 178.83 | 473720.67 | 605160.72 | 735 | 27.75% | Over BOQ | 131440.05
WT-HOS-AKL-03 | MEP - Electrical | Conduit Laying | sqm | 4660 | 5951 | 21.61 | 100702.6 | 128601.11 | 1291 | 27.7% | Over BOQ | 27898.51
WT-HOS-AKL-03 | Interior Fit-out | False Ceiling | set | 862 | 1100 | 45.52 | 39238.24 | 50072 | 238 | 27.61% | Over BOQ | 10833.76
WT-OFF-SYD-02 | MEP - Plumbing | CPVC Piping | cum | 2334 | 2909 | 52.55 | 122651.7 | 152867.95 | 575 | 24.64% | Over BOQ | 30216.25
WT-HOS-AKL-03 | MEP - Plumbing | Sanitary Fixtures | nos | 2485 | 3074 | 198.06 | 492179.1 | 608836.44 | 589 | 23.7% | Over BOQ | 116657.34
WT-DC-MUM-01 | MEP - Electrical | Cable Trays | set | 210 | 259 | 154.29 | 32400.9 | 39961.11 | 49 | 23.33% | Over BOQ | 7560.21
WT-OFF-SYD-02 | MEP - Plumbing | Sanitary Fixtures | cum | 4099 | 5053 | 40.46 | 165845.54 | 204444.38 | 954 | 23.27% | Over BOQ | 38598.84
WT-OFF-SYD-02 | MEP - HVAC | Ductwork | cum | 2520 | 3106 | 122.08 | 307641.6 | 379180.48 | 586 | 23.25% | Over BOQ | 71538.88
WT-DC-MUM-01 | MEP - Plumbing | CPVC Piping | nos | 1402 | 1721 | 184.31 | 258402.62 | 317197.51 | 319 | 22.75% | Over BOQ | 58794.89
WT-DC-MUM-01 | Civil & Structure | RCC Slabs | rmt | 2075 | 2547 | 59.08 | 122591 | 150476.76 | 472 | 22.75% | Over BOQ | 27885.76
WT-HOS-AKL-03 | MEP - HVAC | AHU Supply | rmt | 873 | 1069 | 62.77 | 54798.21 | 67101.13 | 196 | 22.45% | Over BOQ | 12302.92
WT-OFF-SYD-02 | MEP - Electrical | Cable Trays | cum | 3491 | 4259 | 25.58 | 89299.78 | 108945.22 | 768 | 22% | Over BOQ | 19645.44
WT-HOS-AKL-03 | MEP - Electrical | LT Panels | nos | 984 | 1200 | 83.14 | 81809.76 | 99768 | 216 | 21.95% | Over BOQ | 17958.24
WT-OFF-SYD-02 | MEP - Plumbing | Drainage Piping | sqm | 2956 | 3573 | 71.37 | 210969.72 | 255005.01 | 617 | 20.87% | Over BOQ | 44035.29
WT-OFF-SYD-02 | Interior Fit-out | Painting | nos | 3721 | 4490 | 23.15 | 86141.15 | 103943.5 | 769 | 20.67% | Over BOQ | 17802.35
WT-OFF-SYD-02 | MEP - HVAC | Chilled Water Piping | cum | 4686 | 5633 | 72.7 | 340672.2 | 409519.1 | 947 | 20.21% | Over BOQ | 68846.9
WT-OFF-SYD-02 | Civil & Structure | RCC Slabs | kg | 988 | 1185 | 36.93 | 36486.84 | 43762.05 | 197 | 19.94% | Over BOQ | 7275.21
WT-HOS-AKL-03 | MEP - Plumbing | GI Piping | kg | 1898 | 2275 | 79.17 | 150264.66 | 180111.75 | 377 | 19.86% | Over BOQ | 29847.09
WT-OFF-SYD-02 | Civil & Structure | RCC Columns | set | 2149 | 2568 | 37.72 | 81060.28 | 96864.96 | 419 | 19.5% | Over BOQ | 15804.68
WT-DC-MUM-01 | Interior Fit-out | Partition Walls | nos | 2329 | 2767 | 167.23 | 389478.67 | 462725.41 | 438 | 18.81% | Over BOQ | 73246.74
WT-DC-MUM-01 | Interior Fit-out | Joinery Work | set | 379 | 450 | 190.17 | 72074.43 | 85576.5 | 71 | 18.73% | Over BOQ | 13502.07
WT-DC-MUM-01 | Civil & Structure | RCC Columns | nos | 1353 | 1602 | 97.56 | 131998.68 | 156291.12 | 249 | 18.4% | Over BOQ | 24292.44
WT-OFF-SYD-02 | MEP - Electrical | HT Cables | rmt | 3816 | 4458 | 89.92 | 343134.72 | 400863.36 | 642 | 16.82% | Over BOQ | 57728.64
WT-DC-MUM-01 | MEP - HVAC | Ductwork | set | 1301 | 1519 | 17.52 | 22793.52 | 26612.88 | 218 | 16.76% | Over BOQ | 3819.36
WT-HOS-AKL-03 | Interior Fit-out | Joinery Work | rmt | 2366 | 2759 | 93.54 | 221315.64 | 258076.86 | 393 | 16.61% | Over BOQ | 36761.22
WT-OFF-SYD-02 | Interior Fit-out | Joinery Work | sqm | 3362 | 3904 | 64.71 | 217555.02 | 252627.84 | 542 | 16.12% | Over BOQ | 35072.82
WT-OFF-SYD-02 | MEP - HVAC | AHU Supply | cum | 4900 | 5687 | 127.31 | 623819 | 724011.97 | 787 | 16.06% | Over BOQ | 100192.97
WT-OFF-SYD-02 | Interior Fit-out | Flooring | kg | 2018 | 2342 | 130.95 | 264257.1 | 306684.9 | 324 | 16.06% | Over BOQ | 42427.8
WT-HOS-AKL-03 | Interior Fit-out | Partition Walls | sqm | 2217 | 2543 | 35.63 | 78991.71 | 90607.09 | 326 | 14.7% | Over BOQ | 11615.38
WT-HOS-AKL-03 | MEP - HVAC | Insulation | rmt | 1084 | 1232 | 151.79 | 164540.36 | 187005.28 | 148 | 13.65% | Over BOQ | 22464.92
WT-HOS-AKL-03 | MEP - Electrical | DB Boards | cum | 4776 | 5412 | 15.45 | 73789.2 | 83615.4 | 636 | 13.32% | Over BOQ | 9826.2
WT-DC-MUM-01 | Civil & Structure | Brickwork | kg | 4019 | 4549 | 58.55 | 235312.45 | 266343.95 | 530 | 13.19% | Over BOQ | 31031.5
WT-HOS-AKL-03 | MEP - Plumbing | Drainage Piping | rmt | 4708 | 5317 | 123.88 | 583227.04 | 658669.96 | 609 | 12.94% | Over BOQ | 75442.92
WT-OFF-SYD-02 | Civil & Structure | Excavation | sqm | 216 | 243 | 51.52 | 11128.32 | 12519.36 | 27 | 12.5% | Over BOQ | 1391.04
WT-OFF-SYD-02 | MEP - Plumbing | GI Piping | nos | 4718 | 5306 | 78.9 | 372250.2 | 418643.4 | 588 | 12.46% | Over BOQ | 46393.2
WT-OFF-SYD-02 | Civil & Structure | Brickwork | rmt | 935 | 1038 | 186.13 | 174031.55 | 193202.94 | 103 | 11.02% | Over BOQ | 19171.39
WT-HOS-AKL-03 | MEP - Electrical | Cable Trays | cum | 150 | 166 | 96.53 | 14479.5 | 16023.98 | 16 | 10.67% | Over BOQ | 1544.48
WT-OFF-SYD-02 | Civil & Structure | PCC | nos | 987 | 1089 | 47.5 | 46882.5 | 51727.5 | 102 | 10.33% | Over BOQ | 4845
WT-HOS-AKL-03 | MEP - Plumbing | CPVC Piping | sqm | 1020 | 1123 | 86.15 | 87873 | 96746.45 | 103 | 10.1% | Over BOQ | 8873.45
WT-OFF-SYD-02 | Interior Fit-out | False Ceiling | kg | 2313 | 2544 | 105.74 | 244576.62 | 269002.56 | 231 | 9.987% | Over BOQ | 24425.94
WT-DC-MUM-01 | MEP - HVAC | Chilled Water Piping | nos | 2760 | 3019 | 86.08 | 237580.8 | 259875.52 | 259 | 9.384% | Over BOQ | 22294.72
WT-DC-MUM-01 | MEP - Electrical | LT Panels | nos | 3482 | 3803 | 148.25 | 516206.5 | 563794.75 | 321 | 9.219% | Over BOQ | 47588.25
WT-DC-MUM-01 | MEP - Electrical | DB Boards | kg | 1856 | 1985 | 58.22 | 108056.32 | 115566.7 | 129 | 6.95% | Over BOQ | 7510.38
WT-HOS-AKL-03 | Civil & Structure | Excavation | kg | 3073 | 3266 | 108.53 | 333512.69 | 354458.98 | 193 | 6.281% | Over BOQ | 20946.29
WT-HOS-AKL-03 | Interior Fit-out | Painting | nos | 4914 | 5216 | 11.36 | 55823.04 | 59253.76 | 302 | 6.146% | Over BOQ | 3430.72
WT-DC-MUM-01 | Interior Fit-out | Flooring | rmt | 720 | 764 | 151.06 | 108763.2 | 115409.84 | 44 | 6.111% | Over BOQ | 6646.64
WT-OFF-SYD-02 | MEP - Electrical | DB Boards | kg | 4010 | 4247 | 166.02 | 665740.2 | 705086.94 | 237 | 5.91% | Over BOQ | 39346.74
WT-DC-MUM-01 | Civil & Structure | PCC | kg | 4185 | 4360 | 181.84 | 761000.4 | 792822.4 | 175 | 4.182% | Over BOQ | 31822
WT-OFF-SYD-02 | Civil & Structure | Plastering | kg | 3124 | 3213 | 144.43 | 451199.32 | 464053.59 | 89 | 2.849% | Over BOQ | 12854.27
WT-DC-MUM-01 | MEP - HVAC | Insulation | sqm | 3491 | 3579 | 155.11 | 541489.01 | 555138.69 | 88 | 2.521% | Over BOQ | 13649.68
WT-DC-MUM-01 | MEP - Electrical | Conduit Laying | nos | 287 | 294 | 135.43 | 38868.41 | 39816.42 | 7 | 2.439% | Over BOQ | 948.01
WT-HOS-AKL-03 | Civil & Structure | PCC | nos | 4558 | 4552 | 142.06 | 647509.48 | 646657.12 | -6 | -0.1316% | Within BOQ | 0
WT-DC-MUM-01 | Interior Fit-out | False Ceiling | sqm | 3774 | 3762 | 153.44 | 579082.56 | 577241.28 | -12 | -0.318% | Within BOQ | 0
WT-OFF-SYD-02 | MEP - Electrical | Conduit Laying | kg | 2248 | 2236 | 52.87 | 118851.76 | 118217.32 | -12 | -0.5338% | Within BOQ | 0
WT-HOS-AKL-03 | MEP - HVAC | Ductwork | rmt | 1519 | 1497 | 143.06 | 217308.14 | 214160.82 | -22 | -1.448% | Within BOQ | 0
WT-HOS-AKL-03 | Civil & Structure | RCC Columns | rmt | 2561 | 2466 | 28.53 | 73065.33 | 70354.98 | -95 | -3.709% | Within BOQ | 0
WT-OFF-SYD-02 | Interior Fit-out | Partition Walls | sqm | 751 | 719 | 84.25 | 63271.75 | 60575.75 | -32 | -4.261% | Within BOQ | 0
WT-DC-MUM-01 | Civil & Structure | Plastering | cum | 2390 | 2283 | 70.49 | 168471.1 | 160928.67 | -107 | -4.477% | Within BOQ | 0
WT-DC-MUM-01 | Interior Fit-out | Painting | cum | 2916 | 2772 | 18.38 | 53596.08 | 50949.36 | -144 | -4.938% | Within BOQ | 0
WT-HOS-AKL-03 | Civil & Structure | Brickwork | set | 1566 | 1466 | 149.03 | 233380.98 | 218477.98 | -100 | -6.386% | Within BOQ | 0
WT-HOS-AKL-03 | MEP - Electrical | HT Cables | nos | 2841 | 2650 | 15.02 | 42671.82 | 39803 | -191 | -6.723% | Within BOQ | 0
WT-DC-MUM-01 | MEP - HVAC | AHU Supply | kg | 710 | 647 | 50.1 | 35571 | 32414.7 | -63 | -8.873% | Within BOQ | 0
WT-HOS-AKL-03 | Civil & Structure | RCC Slabs | sqm | 2634 | 2380 | 109.49 | 288396.66 | 260586.2 | -254 | -9.643% | Within BOQ | 0
WT-DC-MUM-01 | MEP - Plumbing | Sanitary Fixtures | kg | 272 | 241 | 88.58 | 24093.76 | 21347.78 | -31 | -11.4% | Within BOQ | 0
WT-HOS-AKL-03 | Interior Fit-out | Flooring | sqm | 4571 | 4039 | 5.52 | 25231.92 | 22295.28 | -532 | -11.64% | Within BOQ | 0
WT-OFF-SYD-02 | MEP - HVAC | Insulation | nos | 3085 | 2717 | 131.27 | 404967.95 | 356660.59 | -368 | -11.93% | Within BOQ | 0
WT-DC-MUM-01 | MEP - Plumbing | Drainage Piping | nos | 1538 | 1342 | 78.93 | 121394.34 | 105924.06 | -196 | -12.74% | Within BOQ | 0
WT-HOS-AKL-03 | MEP - HVAC | Chilled Water Piping | sqm | 2297 | 1999 | 15.63 | 35902.11 | 31244.37 | -298 | -12.97% | Within BOQ | 0
WT-DC-MUM-01 | MEP - Plumbing | GI Piping | kg | 4425 | 3814 | 81.83 | 362097.75 | 312099.62 | -611 | -13.81% | Within BOQ | 0
WT-DC-MUM-01 | MEP - Electrical | HT Cables | nos | 3957 | 3373 | 73.59 | 291195.63 | 248219.07 | -584 | -14.76% | Within BOQ | 0
ANALYSIS QUESTIONS
Q1. Which project has the highest total BOQ variance (in USD)? | [5 empty] | PCC in civil structure has the highest BOQ variance in USD
Q2. Which trade consistently exceeds BOQ quantities across all 3 projects?
Q3. Identify the top 5 BOQ items with the highest quantity variance %.
Q4. What is the total financial impact of quantity overruns per project?
Q5. Create a waterfall chart showing BOQ Amount vs Actual Amount per trade for Project WT-DC-MUM-01.
Q6. Which items have negative variance (came under BOQ)? What's the saving?
375655.02

## P03
BOQ Variance Analysis
Q1
Project ID | Sum of BOQ_Amount_USD | Sum of Actual_Amount_USD | Total Variance (USD)
WT-DC-MUM-01 | 5686239.8 | 6061894.82 | 375655.02
WT-HOS-AKL-03 | 4619527.89 | 5117552.24 | 498024.35
WT-OFF-SYD-02 | 5691799.9 | 6408709.85 | 716909.95
Grand Total | 15997567.59 | 17588156.91 | 1590589.32
Project ID WT-DC-MUM-01 has the highest BOQ Variance
Q2
Sum of Qty_Variance | Project ID
Row Labels | WT-DC-MUM-01 | WT-HOS-AKL-03 | WT-OFF-SYD-02 | Grand Total
Civil & Structure | 2054 | 1150 | 937 | 4141
Interior Fit-out | 397 | 727 | 1834 | 2958
MEP - Electrical | -78 | 1968 | 2865 | 4755
MEP - HVAC | 502 | 24 | 1952 | 2478
MEP - Plumbing | -519 | 1678 | 2734 | 3893
Grand Total | 2356 | 5547 | 10322 | 18225
Civil & Structure, Interior Fit-Out, and MEP - HVAC consistently exceeded BOQ quantities across all three projects, recording positive quantity variances in each project.
Q3
BOQ_Item | Qty_Variance_%
Plastering | 28.94% | The top 5 BOQ items with the highest quantity variance percentages were identified by sorting the quantity variance percentage in descending order.
LT Panels | 28.45%
Excavation | 27.75%
Conduit Laying | 27.7%
False Ceiling | 27.61%
Q4
Project ID | Sum of Overrun_Imapact_USD
WT-DC-MUM-01 | 502032.7 | The total financial impact of quantity overruns across all three projects is $1,828,491.49. WT-OFF-SYD-02 had the highest overrun impact at $768,547.75, followed by WT-HOS-AKL-03 at $557,911.04 and WT-DC-MUM-01 at $502,032.70.
WT-HOS-AKL-03 | 557911.04
WT-OFF-SYD-02 | 768547.75
Grand Total | 1828491.49
Q5
Trade | BOQ Amount | variance | Actual Amount |  | Category | Amount
Civil & Structure | 1893094.3 | 238929.32 | 2132023.62 |  | Civil & Structure | 238929.32
MEP - Electrical | 986727.76 | 20630.29 | 1007358.05 |  | MEP - Electrical | 20630.29
Interior Fit-out | 1202994.94 | 88907.45 | 1291902.39 |  | Interior Fit-out | 88907.45
MEP - Plumbing | 765988.47 | -9419.5 | 756568.97 |  | MEP - Plumbing | -9419.5
MEP - HVAC | 837434.33 | 36607.46 | 874041.79 |  | MEP - HVAC | 36607.46
Actual Total |  |  | 6061894.82 |  | Actual Total | 6061894.82
BOQ baseline | 5686239.8 |  |  |  | BOQ baseline | 5686239.8
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## P04-LabourProd
PROBLEM 4: Labour Productivity by Trade
Scenario: Track daily output of workers across trades to identify low-productivity areas.
Date | Project_ID | Trade | Workers_Count | Hours_Worked | Output_Qty | Output_Unit | City | Productivity_per_ManHour
2025-03-01 | WT-HOS-AKL-03 | Facade & Cladding | 17 | 7.7 | 470.6 | cum | Hyderabad | 3.5951
2025-02-06 | WT-DC-MUM-01 | Civil & Structure | 15 | 9.2 | 452.4 | rmt | Ahmedabad | 3.2783
2025-02-01 | WT-ITP-BLR-04 | Facade & Cladding | 24 | 8.8 | 1132.6 | nos | Ahmedabad | 5.3627
2025-01-21 | WT-DC-MUM-01 | MEP - Plumbing | 25 | 8.4 | 56.7 | cum | Mumbai | 0.27
2025-03-10 | WT-DC-MUM-01 | MEP - HVAC | 35 | 8.1 | 793.4 | rmt | Delhi | 2.7986
2025-05-30 | WT-ITP-BLR-04 | Facade & Cladding | 36 | 9.9 | 865.1 | nos | Pune | 2.4273
2025-03-24 | WT-DC-MUM-01 | MEP - HVAC | 26 | 7.6 | 657.2 | nos | Mumbai | 3.3259
2025-04-27 | WT-DC-MUM-01 | MEP - Electrical | 21 | 7.3 | 1019.3 | nos | Mumbai | 6.6491
2025-05-19 | WT-ITP-BLR-04 | MEP - Plumbing | 8 | 6.8 | 149.8 | nos | Ahmedabad | 2.7537
2025-01-14 | WT-OFF-SYD-02 | MEP - Electrical | 40 | 6.5 | 604.5 | nos | Bangalore | 2.325
2025-01-08 | WT-OFF-SYD-02 | Facade & Cladding | 15 | 7.2 | 25.1 | nos | Bangalore | 0.23241
2025-02-27 | WT-DC-MUM-01 | MEP - Plumbing | 12 | 8.6 | 102.5 | rmt | Hyderabad | 0.99322
2025-04-17 | WT-ITP-BLR-04 | MEP - Plumbing | 20 | 7.8 | 161.7 | cum | Delhi | 1.0365
2025-01-18 | WT-HOS-AKL-03 | MEP - Plumbing | 26 | 9.7 | 672.9 | sqm | Hyderabad | 2.6681
2025-03-18 | WT-ITP-BLR-04 | MEP - HVAC | 33 | 8.2 | 591.1 | nos | Ahmedabad | 2.1844
2025-03-24 | WT-OFF-SYD-02 | Facade & Cladding | 20 | 8.3 | 248.9 | nos | Mumbai | 1.4994
2025-03-23 | WT-ITP-BLR-04 | Facade & Cladding | 29 | 7.5 | 972.1 | cum | Ahmedabad | 4.4694
2025-01-10 | WT-OFF-SYD-02 | Interior Fit-out | 26 | 9.5 | 1139.7 | nos | Bangalore | 4.6142
2025-05-15 | WT-ITP-BLR-04 | Civil & Structure | 14 | 7.6 | 463.2 | cum | Bangalore | 4.3534
2025-05-01 | WT-HOS-AKL-03 | MEP - Electrical | 30 | 8.6 | 1282.1 | nos | Pune | 4.9694
2025-05-05 | WT-DC-MUM-01 | Interior Fit-out | 9 | 6.9 | 310.8 | rmt | Chennai | 5.0048
2025-01-24 | WT-ITP-BLR-04 | Civil & Structure | 11 | 7.8 | 385.1 | sqm | Mumbai | 4.4883
2025-03-25 | WT-DC-MUM-01 | MEP - Electrical | 27 | 7.5 | 219.6 | nos | Delhi | 1.0844
2025-02-13 | WT-OFF-SYD-02 | Civil & Structure | 29 | 8.5 | 371.2 | cum | Chennai | 1.5059
2025-04-29 | WT-HOS-AKL-03 | MEP - Plumbing | 21 | 8.7 | 946 | nos | Hyderabad | 5.1779
2025-05-20 | WT-OFF-SYD-02 | Civil & Structure | 33 | 9.8 | 1630 | rmt | Kolkata | 5.0402
2025-03-06 | WT-ITP-BLR-04 | MEP - Electrical | 17 | 10 | 727.8 | sqm | Chennai | 4.2812
2025-04-08 | WT-HOS-AKL-03 | Interior Fit-out | 23 | 10 | 355.7 | nos | Hyderabad | 1.5465
2025-01-03 | WT-DC-MUM-01 | Interior Fit-out | 36 | 9.3 | 1628.8 | cum | Pune | 4.865
2025-02-26 | WT-OFF-SYD-02 | Interior Fit-out | 21 | 8.7 | 762.8 | cum | Bangalore | 4.1752
2025-01-11 | WT-HOS-AKL-03 | MEP - Plumbing | 7 | 8.3 | 258.2 | sqm | Hyderabad | 4.4441
2025-03-25 | WT-ITP-BLR-04 | MEP - HVAC | 17 | 6.5 | 466.3 | rmt | Hyderabad | 4.2199
2025-02-12 | WT-HOS-AKL-03 | MEP - Plumbing | 23 | 9 | 404.7 | sqm | Ahmedabad | 1.9551
2025-01-20 | WT-OFF-SYD-02 | MEP - HVAC | 30 | 9.9 | 1212.7 | rmt | Bangalore | 4.0832
2025-04-12 | WT-DC-MUM-01 | MEP - Electrical | 39 | 6.5 | 743.4 | rmt | Kolkata | 2.9325
2025-04-06 | WT-DC-MUM-01 | Facade & Cladding | 19 | 7.9 | 595.8 | rmt | Chennai | 3.9694
2025-01-17 | WT-ITP-BLR-04 | Facade & Cladding | 24 | 8.6 | 161.2 | sqm | Mumbai | 0.78101
2025-03-19 | WT-ITP-BLR-04 | Civil & Structure | 11 | 6.9 | 300.7 | nos | Ahmedabad | 3.9618
2025-04-05 | WT-ITP-BLR-04 | Interior Fit-out | 14 | 9.5 | 463.3 | nos | Kolkata | 3.4835
2025-03-13 | WT-DC-MUM-01 | Facade & Cladding | 28 | 6.9 | 638.1 | cum | Pune | 3.3028
2025-01-26 | WT-HOS-AKL-03 | Interior Fit-out | 27 | 6.2 | 392 | sqm | Ahmedabad | 2.3417
2025-01-24 | WT-OFF-SYD-02 | Facade & Cladding | 6 | 6.2 | 104.1 | cum | Chennai | 2.7984
2025-01-18 | WT-OFF-SYD-02 | Interior Fit-out | 18 | 9.3 | 223.5 | cum | Mumbai | 1.3351
2025-03-12 | WT-OFF-SYD-02 | MEP - HVAC | 39 | 7 | 372.5 | sqm | Delhi | 1.3645
2025-01-04 | WT-HOS-AKL-03 | MEP - HVAC | 25 | 6.1 | 350.1 | cum | Kolkata | 2.2957
2025-05-15 | WT-DC-MUM-01 | Facade & Cladding | 9 | 7.9 | 352.1 | sqm | Ahmedabad | 4.9522
2025-05-09 | WT-OFF-SYD-02 | Interior Fit-out | 7 | 8.9 | 318.7 | rmt | Ahmedabad | 5.1156
2025-01-08 | WT-DC-MUM-01 | MEP - Plumbing | 30 | 7.7 | 188.7 | nos | Bangalore | 0.81688
2025-01-21 | WT-HOS-AKL-03 | Interior Fit-out | 14 | 6.3 | 202.7 | rmt | Kolkata | 2.2982
2025-05-16 | WT-HOS-AKL-03 | MEP - Plumbing | 37 | 8.4 | 216.8 | sqm | Chennai | 0.69755
2025-04-21 | WT-ITP-BLR-04 | MEP - HVAC | 31 | 7.4 | 719.9 | nos | Bangalore | 3.1382
2025-03-22 | WT-ITP-BLR-04 | MEP - Electrical | 21 | 7.5 | 178.1 | nos | Bangalore | 1.1308
2025-01-24 | WT-DC-MUM-01 | Civil & Structure | 32 | 6.4 | 1190.4 | cum | Mumbai | 5.8125
2025-05-31 | WT-HOS-AKL-03 | Facade & Cladding | 12 | 7.6 | 525.7 | nos | Mumbai | 5.7643
2025-03-15 | WT-HOS-AKL-03 | MEP - Electrical | 11 | 8.3 | 125.7 | nos | Chennai | 1.3768
2025-01-28 | WT-HOS-AKL-03 | Interior Fit-out | 28 | 6.5 | 410.2 | cum | Kolkata | 2.2538
2025-05-24 | WT-DC-MUM-01 | Interior Fit-out | 22 | 6.1 | 316.6 | rmt | Pune | 2.3592
2025-03-31 | WT-DC-MUM-01 | MEP - HVAC | 14 | 8.3 | 288.9 | cum | Mumbai | 2.4862
2025-01-24 | WT-OFF-SYD-02 | MEP - Plumbing | 31 | 7.8 | 270.1 | rmt | Pune | 1.117
2025-05-26 | WT-DC-MUM-01 | Civil & Structure | 14 | 6.6 | 437.8 | sqm | Hyderabad | 4.7381
2025-04-24 | WT-ITP-BLR-04 | MEP - Plumbing | 33 | 7.7 | 381.6 | sqm | Pune | 1.5018
2025-04-21 | WT-DC-MUM-01 | MEP - Electrical | 36 | 8.1 | 580.1 | cum | Kolkata | 1.9894
2025-01-15 | WT-DC-MUM-01 | MEP - HVAC | 24 | 9.8 | 926.4 | rmt | Hyderabad | 3.9388
2025-03-25 | WT-DC-MUM-01 | Civil & Structure | 36 | 9 | 345.9 | nos | Chennai | 1.0676
2025-05-09 | WT-HOS-AKL-03 | Civil & Structure | 30 | 9.4 | 92.2 | sqm | Ahmedabad | 0.32695
2025-01-20 | WT-HOS-AKL-03 | Interior Fit-out | 32 | 8.3 | 1144.5 | nos | Hyderabad | 4.3091
2025-01-30 | WT-ITP-BLR-04 | Civil & Structure | 25 | 6.7 | 1185.8 | nos | Pune | 7.0794
2025-01-23 | WT-ITP-BLR-04 | Civil & Structure | 20 | 7.7 | 412.4 | sqm | Kolkata | 2.6779
2025-03-21 | WT-HOS-AKL-03 | MEP - HVAC | 26 | 9.1 | 123.3 | sqm | Chennai | 0.52113
2025-03-31 | WT-HOS-AKL-03 | Facade & Cladding | 14 | 6.9 | 114.5 | cum | Delhi | 1.1853
2025-02-09 | WT-DC-MUM-01 | MEP - HVAC | 36 | 7.9 | 1030.4 | nos | Pune | 3.6231
2025-03-22 | WT-OFF-SYD-02 | MEP - Plumbing | 9 | 7.9 | 287.4 | rmt | Mumbai | 4.0422
2025-04-01 | WT-DC-MUM-01 | MEP - Electrical | 34 | 7.8 | 128.8 | rmt | Bangalore | 0.48567
2025-01-24 | WT-ITP-BLR-04 | MEP - Plumbing | 40 | 9.8 | 1488.3 | sqm | Ahmedabad | 3.7967
2025-05-27 | WT-OFF-SYD-02 | MEP - Electrical | 35 | 8 | 1677.5 | nos | Bangalore | 5.9911
2025-03-29 | WT-DC-MUM-01 | Interior Fit-out | 16 | 6.2 | 570.8 | nos | Delhi | 5.754
2025-04-04 | WT-HOS-AKL-03 | MEP - Electrical | 29 | 7.6 | 509.8 | sqm | Pune | 2.3131
2025-01-17 | WT-HOS-AKL-03 | Civil & Structure | 40 | 8.7 | 596.9 | cum | Pune | 1.7152
2025-01-21 | WT-OFF-SYD-02 | MEP - Electrical | 24 | 9.9 | 845.4 | nos | Delhi | 3.5581
2025-01-22 | WT-HOS-AKL-03 | Interior Fit-out | 29 | 8.6 | 495.8 | cum | Bangalore | 1.988
ANALYSIS QUESTIONS
Q1. Which trade has the highest average productivity per man-hour?
Q2. Is there a productivity difference between projects in India vs Australia?
Q3. Create a box plot (or summary stats) of productivity by trade — which has the most variance?
Q4. On which dates did productivity drop below the 25th percentile? What was the trade?
Q5. What is the optimal crew size (workers count) that maximises productivity for Civil & Structure?
Q6. Calculate total man-hours consumed per project and rank them.

## P05-TenderBid
PROBLEM 5: Tender Bid Comparison Analysis
Scenario: WT received bids from multiple contractors for 5 trade packages. Evaluate and rank.
Tender_Package | Contractor | Bid_Amount_USD | Completion_Days | Experience_Years | Safety_Rating | Past_Defect_Rate_% | Financial_Score
Structural Works | Contractor-K | 6124192 | 306 | 18 | 3.4 | 4.7 | 59
Structural Works | Contractor-D | 3366658 | 338 | 8 | 3.1 | 2.1 | 53.9
Structural Works | Contractor-N | 7111231 | 141 | 18 | 4.4 | 10.1 | 94.2
Structural Works | Contractor-A | 6052664 | 262 | 21 | 2.8 | 4.8 | 58.1
Structural Works | Contractor-N | 6312010 | 174 | 25 | 3.6 | 5.2 | 83.8
Structural Works | Contractor-D | 4226208 | 235 | 25 | 4.5 | 3.2 | 62
Structural Works | Contractor-M | 7079774 | 330 | 8 | 3.4 | 11.4 | 99.2
Structural Works | Contractor-H | 6954518 | 234 | 14 | 3.8 | 5.3 | 58.1
MEP Package | Contractor-D | 7221449 | 160 | 10 | 2.6 | 6 | 68.6
MEP Package | Contractor-O | 1360585 | 354 | 5 | 3.2 | 9.3 | 63.6
MEP Package | Contractor-O | 4806314 | 165 | 15 | 2.7 | 11 | 90.8
MEP Package | Contractor-O | 3432532 | 103 | 15 | 2.6 | 6.3 | 61.8
MEP Package | Contractor-B | 3644995 | 204 | 2 | 3.3 | 1.6 | 85.7
MEP Package | Contractor-F | 7138581 | 164 | 6 | 2.6 | 11.1 | 73.6
MEP Package | Contractor-N | 1664277 | 330 | 16 | 4 | 10.9 | 51
MEP Package | Contractor-D | 7504178 | 166 | 19 | 4.9 | 7.5 | 71.2
Facade & Glazing | Contractor-M | 2916771 | 211 | 11 | 2.8 | 3.2 | 81.9
Facade & Glazing | Contractor-J | 4334546 | 122 | 5 | 4.6 | 6.2 | 76.8
Facade & Glazing | Contractor-K | 4823284 | 213 | 24 | 2.9 | 5.4 | 80.7
Facade & Glazing | Contractor-D | 5287074 | 303 | 7 | 4.2 | 1.5 | 98.7
Facade & Glazing | Contractor-B | 4912906 | 349 | 18 | 3.9 | 5 | 73.5
Facade & Glazing | Contractor-K | 3745395 | 281 | 10 | 4.4 | 4.6 | 53.4
Facade & Glazing | Contractor-D | 6648354 | 143 | 20 | 4.3 | 4.3 | 52.2
Facade & Glazing | Contractor-I | 3339940 | 179 | 23 | 3.7 | 8.5 | 81.6
Interior Fit-out | Contractor-M | 1631225 | 122 | 24 | 4.4 | 5.8 | 64.7
Interior Fit-out | Contractor-A | 7136305 | 192 | 3 | 3.3 | 4.1 | 69.9
Interior Fit-out | Contractor-N | 5055271 | 332 | 10 | 2.6 | 7.9 | 64.3
Interior Fit-out | Contractor-N | 7050173 | 114 | 22 | 3.3 | 1.9 | 68.4
Interior Fit-out | Contractor-O | 3855625 | 315 | 14 | 3.3 | 2.6 | 84.6
Interior Fit-out | Contractor-F | 7188160 | 355 | 10 | 4.5 | 8.9 | 53.9
Interior Fit-out | Contractor-J | 7398298 | 182 | 19 | 3.2 | 1.7 | 66.4
Interior Fit-out | Contractor-E | 3071073 | 318 | 21 | 4.3 | 2.4 | 72.2
Landscaping | Contractor-H | 855300 | 270 | 21 | 5 | 3.7 | 99
Landscaping | Contractor-A | 1129490 | 297 | 13 | 3.8 | 9.1 | 58
Landscaping | Contractor-A | 1697720 | 314 | 3 | 2.8 | 3.2 | 82.3
Landscaping | Contractor-F | 3711615 | 106 | 21 | 2.9 | 5.7 | 68.5
Landscaping | Contractor-H | 6901216 | 129 | 20 | 2.8 | 4.7 | 65.7
Landscaping | Contractor-E | 2593894 | 148 | 2 | 4.3 | 6.2 | 69.3
Landscaping | Contractor-I | 1487850 | 224 | 10 | 4.3 | 3 | 80.6
Landscaping | Contractor-L | 4620485 | 192 | 5 | 2.8 | 1.4 | 58.6
ANALYSIS QUESTIONS
Q1. For each tender package, which contractor offers the lowest bid? Is the lowest bid always the best choice?
Q2. Create a weighted scoring model: 40% Price, 20% Time, 15% Experience, 15% Safety, 10% Defects. Rank contractors.
Q3. Which contractors appear in multiple packages? What is their average bid competitiveness?
Q4. Identify any contractor with Safety Rating < 3.5 AND Defect Rate > 8% — flag as HIGH RISK.
Q5. What is the total project cost if WT selects the lowest bidder for each package vs the highest-scored bidder?
Q6. Create a scatter plot of Bid Amount vs Completion Days — are cheaper bids slower?

## P06-DelayRCA
PROBLEM 6: Project Delay Root Cause Analysis
Scenario: Analyse delay events across projects to find systemic causes.
Delay_ID | Project_ID | Activity | Planned_Start | Actual_Start | Delay_Days | Cause_Category | Responsible_Party
DLY-100 | WT-RES-MEL-05 | Superstructure | 2024-08-11 | 2024-09-23 | 43 | Permit Delay | Force Majeure
DLY-101 | WT-DC-MUM-01 | Handover Prep | 2024-12-03 | 2024-12-22 | 19 | Client Decision Pending | Contractor
DLY-102 | WT-OFF-SYD-02 | Testing & Commissioning | 2024-11-16 | 2024-12-01 | 15 | Material Delay | Contractor
DLY-103 | WT-OFF-SYD-02 | Facade Installation | 2024-11-08 | 2024-11-10 | 2 | Permit Delay | Authority
DLY-104 | WT-MAL-DEL-06 | Testing & Commissioning | 2024-10-26 | 2024-12-01 | 36 | Labour Shortage | Authority
DLY-105 | WT-DC-MUM-01 | Superstructure | 2024-08-06 | 2024-09-01 | 26 | Equipment Breakdown | Authority
DLY-106 | WT-RES-MEL-05 | Landscape | 2024-12-20 | 2024-12-25 | 5 | Labour Shortage | Consultant
DLY-107 | WT-DC-MUM-01 | External Works | 2024-10-25 | 2024-12-08 | 44 | RFI Response Delay | Consultant
DLY-108 | WT-OFF-SYD-02 | Handover Prep | 2024-12-26 | 2025-01-07 | 12 | Labour Shortage | Subcontractor
DLY-109 | WT-MAL-DEL-06 | Foundation | 2024-05-03 | 2024-06-06 | 34 | Labour Shortage | Consultant
DLY-110 | WT-OFF-SYD-02 | MEP Rough-In | 2024-08-13 | 2024-08-28 | 15 | Permit Delay | Authority
DLY-111 | WT-HOS-AKL-03 | Superstructure | 2024-07-07 | 2024-07-20 | 13 | RFI Response Delay | Consultant
DLY-112 | WT-OFF-SYD-02 | Interior Works | 2024-11-29 | 2024-12-05 | 6 | RFI Response Delay | Force Majeure
DLY-113 | WT-OFF-SYD-02 | MEP Rough-In | 2024-05-27 | 2024-07-09 | 43 | Rework | Force Majeure
DLY-114 | WT-MAL-DEL-06 | Testing & Commissioning | 2024-12-14 | 2024-12-17 | 3 | Design Change | Client
DLY-115 | WT-DC-MUM-01 | Interior Works | 2024-06-16 | 2024-07-23 | 37 | Subcontractor Default | Authority
DLY-116 | WT-DC-MUM-01 | External Works | 2024-12-05 | 2024-12-24 | 19 | Client Decision Pending | Subcontractor
DLY-117 | WT-OFF-SYD-02 | Landscape | 2024-07-31 | 2024-08-30 | 30 | Material Delay | Force Majeure
DLY-118 | WT-DC-MUM-01 | MEP Rough-In | 2024-10-12 | 2024-11-08 | 27 | Equipment Breakdown | Subcontractor
DLY-119 | WT-OFF-SYD-02 | Testing & Commissioning | 2024-05-13 | 2024-06-03 | 21 | Permit Delay | Force Majeure
DLY-120 | WT-HOS-AKL-03 | Landscape | 2024-05-06 | 2024-05-30 | 24 | RFI Response Delay | Authority
DLY-121 | WT-DC-MUM-01 | Testing & Commissioning | 2024-07-02 | 2024-08-01 | 30 | Material Delay | Consultant
DLY-122 | WT-RES-MEL-05 | Facade Installation | 2024-05-12 | 2024-05-19 | 7 | Design Change | Consultant
DLY-123 | WT-RES-MEL-05 | Landscape | 2024-07-06 | 2024-07-17 | 11 | Permit Delay | Authority
DLY-124 | WT-HOS-AKL-03 | Facade Installation | 2024-05-21 | 2024-06-22 | 32 | RFI Response Delay | Subcontractor
DLY-125 | WT-RES-MEL-05 | Interior Works | 2024-11-10 | 2024-11-12 | 2 | Material Delay | Subcontractor
DLY-126 | WT-MAL-DEL-06 | External Works | 2024-07-02 | 2024-07-16 | 14 | Rework | Consultant
DLY-127 | WT-DC-MUM-01 | Foundation | 2024-07-23 | 2024-08-24 | 32 | Rework | Force Majeure
DLY-128 | WT-RES-MEL-05 | Interior Works | 2024-11-30 | 2024-12-01 | 1 | Material Delay | Subcontractor
DLY-129 | WT-OFF-SYD-02 | Interior Works | 2024-09-04 | 2024-09-30 | 26 | Permit Delay | Client
DLY-130 | WT-RES-MEL-05 | Foundation | 2024-12-17 | 2025-01-22 | 36 | Weather | Consultant
DLY-131 | WT-MAL-DEL-06 | Interior Works | 2024-04-07 | 2024-05-02 | 25 | RFI Response Delay | Subcontractor
DLY-132 | WT-MAL-DEL-06 | Interior Works | 2024-04-30 | 2024-05-09 | 9 | Material Delay | Subcontractor
DLY-133 | WT-HOS-AKL-03 | Testing & Commissioning | 2024-12-11 | 2025-01-04 | 24 | Labour Shortage | Contractor
DLY-134 | WT-MAL-DEL-06 | Handover Prep | 2024-09-22 | 2024-10-25 | 33 | Design Change | Client
DLY-135 | WT-DC-MUM-01 | MEP Rough-In | 2024-08-18 | 2024-09-18 | 31 | RFI Response Delay | Subcontractor
DLY-136 | WT-OFF-SYD-02 | Handover Prep | 2024-05-11 | 2024-06-01 | 21 | Rework | Consultant
DLY-137 | WT-OFF-SYD-02 | Landscape | 2024-08-01 | 2024-09-08 | 38 | Permit Delay | Authority
DLY-138 | WT-MAL-DEL-06 | Handover Prep | 2024-11-06 | 2024-12-13 | 37 | Client Decision Pending | Subcontractor
DLY-139 | WT-DC-MUM-01 | Testing & Commissioning | 2024-08-17 | 2024-09-30 | 44 | Material Delay | Subcontractor
DLY-140 | WT-MAL-DEL-06 | Interior Works | 2024-03-14 | 2024-04-22 | 39 | Equipment Breakdown | Consultant
DLY-141 | WT-MAL-DEL-06 | Facade Installation | 2024-03-27 | 2024-05-04 | 38 | Equipment Breakdown | Contractor
DLY-142 | WT-MAL-DEL-06 | Landscape | 2024-05-15 | 2024-06-28 | 44 | Weather | Client
DLY-143 | WT-MAL-DEL-06 | Superstructure | 2024-06-06 | 2024-06-08 | 2 | Equipment Breakdown | Consultant
DLY-144 | WT-RES-MEL-05 | MEP Rough-In | 2024-09-28 | 2024-11-12 | 45 | Weather | Subcontractor
DLY-145 | WT-MAL-DEL-06 | External Works | 2024-04-01 | 2024-04-10 | 9 | RFI Response Delay | Contractor
DLY-146 | WT-MAL-DEL-06 | Testing & Commissioning | 2024-10-31 | 2024-12-04 | 34 | Subcontractor Default | Consultant
DLY-147 | WT-OFF-SYD-02 | External Works | 2024-11-28 | 2024-12-20 | 22 | RFI Response Delay | Consultant
DLY-148 | WT-HOS-AKL-03 | External Works | 2024-06-07 | 2024-06-23 | 16 | Client Decision Pending | Authority
DLY-149 | WT-HOS-AKL-03 | Facade Installation | 2024-07-31 | 2024-08-19 | 19 | Weather | Force Majeure
DLY-150 | WT-RES-MEL-05 | Testing & Commissioning | 2024-11-01 | 2024-11-24 | 23 | RFI Response Delay | Force Majeure
DLY-151 | WT-HOS-AKL-03 | Interior Works | 2024-05-02 | 2024-06-08 | 37 | RFI Response Delay | Subcontractor
DLY-152 | WT-RES-MEL-05 | Testing & Commissioning | 2024-05-14 | 2024-06-02 | 19 | Design Change | Consultant
DLY-153 | WT-DC-MUM-01 | Testing & Commissioning | 2024-10-13 | 2024-11-24 | 42 | Client Decision Pending | Force Majeure
DLY-154 | WT-RES-MEL-05 | Facade Installation | 2024-06-12 | 2024-07-17 | 35 | Client Decision Pending | Authority
DLY-155 | WT-HOS-AKL-03 | MEP Rough-In | 2024-04-25 | 2024-06-04 | 40 | Rework | Contractor
DLY-156 | WT-OFF-SYD-02 | Foundation | 2024-11-27 | 2024-12-12 | 15 | Weather | Client
DLY-157 | WT-DC-MUM-01 | Landscape | 2024-08-17 | 2024-09-17 | 31 | Material Delay | Force Majeure
DLY-158 | WT-OFF-SYD-02 | Foundation | 2024-12-07 | 2024-12-18 | 11 | Subcontractor Default | Force Majeure
DLY-159 | WT-RES-MEL-05 | External Works | 2024-06-11 | 2024-06-30 | 19 | Permit Delay | Consultant
ANALYSIS QUESTIONS
Q1. What is the most frequent delay cause category? Create a Pareto chart.
Q2. Which responsible party causes the most total delay days?
Q3. For Project WT-DC-MUM-01, what is the cumulative delay and the dominant cause?
Q4. Is there a seasonal pattern in delays? (Hint: check Weather delays by month)
Q5. Which activity is most delay-prone across all projects?
Q6. Calculate the estimated cost of delay per project if the daily burn rate is $15,000.

## P07-CashFlow
PROBLEM 7: Monthly Cash Flow Tracking
Scenario: Track planned vs actual cash inflow/outflow for 4 projects over 12 months.
Month | Project_ID | Planned_Inflow_USD | Actual_Inflow_USD | Planned_Outflow_USD | Actual_Outflow_USD | Net_CashFlow_USD
2024-01 | WT-DC-MUM-01 | 1554546 | 978713 | 1762133 | 1552987 | -574274
2024-02 | WT-DC-MUM-01 | 1404044 | 1005450 | 1699137 | 1874303 | -868853
2024-03 | WT-DC-MUM-01 | 278220 | 293971 | 517137 | 515202 | -221231
2024-04 | WT-DC-MUM-01 | 1956584 | 1345923 | 226210 | 271228 | 1074695
2024-05 | WT-DC-MUM-01 | 1032557 | 1026341 | 540723 | 636870 | 389471
2024-06 | WT-DC-MUM-01 | 807056 | 838024 | 169434 | 161714 | 676310
2024-07 | WT-DC-MUM-01 | 1464127 | 957027 | 852634 | 809658 | 147369
2024-08 | WT-DC-MUM-01 | 1544929 | 1346637 | 1185809 | 1377010 | -30373
2024-09 | WT-DC-MUM-01 | 481437 | 493728 | 1131510 | 1069834 | -576106
2024-10 | WT-DC-MUM-01 | 1896205 | 1244523 | 490775 | 542744 | 701779
2024-11 | WT-DC-MUM-01 | 1559552 | 1136340 | 540487 | 462078 | 674262
2024-12 | WT-DC-MUM-01 | 906975 | 902788 | 1340723 | 1456079 | -553291
2024-01 | WT-OFF-SYD-02 | 605088 | 416147 | 1489505 | 1733731 | -1317584
2024-02 | WT-OFF-SYD-02 | 1934323 | 1574251 | 837712 | 737486 | 836765
2024-03 | WT-OFF-SYD-02 | 1603531 | 1038595 | 444884 | 452495 | 586100
2024-04 | WT-OFF-SYD-02 | 720192 | 434574 | 954413 | 889925 | -455351
2024-05 | WT-OFF-SYD-02 | 1780742 | 1306169 | 841274 | 803989 | 502180
2024-06 | WT-OFF-SYD-02 | 1715994 | 1521123 | 698516 | 753551 | 767572
2024-07 | WT-OFF-SYD-02 | 1652841 | 1186989 | 1550448 | 1382036 | -195047
2024-08 | WT-OFF-SYD-02 | 843419 | 573405 | 1588800 | 1629921 | -1056516
2024-09 | WT-OFF-SYD-02 | 1675466 | 1650200 | 1597643 | 1423652 | 226548
2024-10 | WT-OFF-SYD-02 | 818738 | 641703 | 613154 | 568206 | 73497
2024-11 | WT-OFF-SYD-02 | 480114 | 402859 | 1104159 | 1227501 | -824642
2024-12 | WT-OFF-SYD-02 | 1470326 | 1156870 | 1622076 | 1690579 | -533709
2024-01 | WT-HOS-AKL-03 | 1187398 | 1162077 | 1542706 | 1757082 | -595005
2024-02 | WT-HOS-AKL-03 | 1797735 | 1301079 | 1732803 | 1834232 | -533153
2024-03 | WT-HOS-AKL-03 | 1851236 | 1186522 | 1086898 | 1124787 | 61735
2024-04 | WT-HOS-AKL-03 | 958717 | 612669 | 1333147 | 1185531 | -572862
2024-05 | WT-HOS-AKL-03 | 1938065 | 1693528 | 1210083 | 1114189 | 579339
2024-06 | WT-HOS-AKL-03 | 1325457 | 894585 | 838112 | 963049 | -68464
2024-07 | WT-HOS-AKL-03 | 1126606 | 741441 | 580758 | 639368 | 102073
2024-08 | WT-HOS-AKL-03 | 1225146 | 790795 | 1220334 | 1227557 | -436762
2024-09 | WT-HOS-AKL-03 | 316676 | 261801 | 1226358 | 1220715 | -958914
2024-10 | WT-HOS-AKL-03 | 1382607 | 869477 | 1119677 | 1215374 | -345897
2024-11 | WT-HOS-AKL-03 | 846278 | 813814 | 980364 | 920620 | -106806
2024-12 | WT-HOS-AKL-03 | 206323 | 200732 | 1362806 | 1193218 | -992486
2024-01 | WT-ITP-BLR-04 | 1088557 | 840653 | 283714 | 294894 | 545759
2024-02 | WT-ITP-BLR-04 | 326365 | 348326 | 294743 | 352261 | -3935
2024-03 | WT-ITP-BLR-04 | 1190005 | 732885 | 1007456 | 919800 | -186915
2024-04 | WT-ITP-BLR-04 | 484014 | 475744 | 1679430 | 1807164 | -1331420
2024-05 | WT-ITP-BLR-04 | 1081562 | 851438 | 952117 | 958770 | -107332
2024-06 | WT-ITP-BLR-04 | 991667 | 781257 | 1581789 | 1878296 | -1097039
2024-07 | WT-ITP-BLR-04 | 1330994 | 887100 | 879326 | 783938 | 103162
2024-08 | WT-ITP-BLR-04 | 1326712 | 1056765 | 417066 | 460753 | 596012
2024-09 | WT-ITP-BLR-04 | 667015 | 678628 | 1735823 | 1489262 | -810634
2024-10 | WT-ITP-BLR-04 | 825712 | 686581 | 1658049 | 1725292 | -1038711
2024-11 | WT-ITP-BLR-04 | 1315545 | 1038804 | 631640 | 591612 | 447192
2024-12 | WT-ITP-BLR-04 | 925949 | 627386 | 545272 | 642381 | -14995
ANALYSIS QUESTIONS
Q1. Which project had negative net cash flow for the most months?
Q2. What is the cumulative cash position for each project at end of December 2024?
Q3. Create a line chart of monthly net cash flow for all 4 projects.
Q4. In which months did actual inflow fall below 70% of planned? Flag as collection risk.
Q5. What is the total cash surplus/deficit across all projects?
Q6. Calculate the cash flow forecast accuracy: (Actual Inflow / Planned Inflow) × 100.

## P08-ChangeOrder
PROBLEM 8: Change Order Impact Analysis
Scenario: Evaluate cost and time impact of change orders (VOs) on ongoing projects.
VO_Number | Project_ID | Description | Initiated_By | Cost_Impact_USD | Time_Impact_Days | Status | Date_Raised
VO-200 | WT-DC-MUM-01 | Additional MEP riser | Architect | 444793 | -4 | Pending | 2024-04-15
VO-201 | WT-DC-MUM-01 | Design revision - column grid | Client | 268127 | -2 | Pending | 2025-01-14
VO-202 | WT-DC-MUM-01 | Upgraded HVAC system | Architect | 45722 | 29 | Pending | 2025-01-21
VO-203 | WT-DC-MUM-01 | Client-requested floor upgrade | Contractor | 45536 | 15 | Rejected | 2024-05-01
VO-204 | WT-HOS-AKL-03 | Basement depth increase | Consultant | 492282 | 28 | Pending | 2024-07-30
VO-205 | WT-HOS-AKL-03 | Scope reduction - parking level | Client | 383761 | 6 | Under Review | 2024-10-11
VO-206 | WT-RES-MEL-05 | Additional MEP riser | Contractor | 787324 | 19 | Rejected | 2024-12-22
VO-207 | WT-RES-MEL-05 | Upgraded HVAC system | Consultant | 114455 | 19 | Pending | 2025-01-21
VO-208 | WT-RES-MEL-05 | Regulatory compliance addition | Consultant | 115344 | 4 | Under Review | 2024-01-30
VO-209 | WT-RES-MEL-05 | Upgraded HVAC system | Consultant | 207286 | 10 | Rejected | 2024-04-14
VO-210 | WT-HOS-AKL-03 | Revised electrical layout | Client | 767024 | 23 | Rejected | 2024-02-17
VO-211 | WT-OFF-SYD-02 | Additional MEP riser | Contractor | 195489 | -3 | Approved | 2024-04-06
VO-212 | WT-OFF-SYD-02 | Extra waterproofing layer | Consultant | 711709 | 16 | Rejected | 2024-01-08
VO-213 | WT-OFF-SYD-02 | Basement depth increase | Consultant | 577493 | 2 | Under Review | 2024-05-04
VO-214 | WT-OFF-SYD-02 | Upgraded HVAC system | Consultant | 378897 | 15 | Rejected | 2024-07-13
VO-215 | WT-RES-MEL-05 | Facade material change | Contractor | 123404 | 11 | Rejected | 2024-09-19
VO-216 | WT-RES-MEL-05 | Extra waterproofing layer | Client | 641814 | 25 | Rejected | 2024-04-14
VO-217 | WT-HOS-AKL-03 | Added fire escape staircase | Architect | -152064 | 9 | Pending | 2024-01-09
VO-218 | WT-HOS-AKL-03 | Facade material change | Architect | 109531 | 4 | Pending | 2024-06-17
VO-219 | WT-OFF-SYD-02 | Upgraded HVAC system | Consultant | 323555 | 30 | Rejected | 2024-05-11
VO-220 | WT-RES-MEL-05 | Green roof addition | Architect | 283214 | 5 | Rejected | 2024-03-27
VO-221 | WT-OFF-SYD-02 | Green roof addition | Architect | -7012 | 29 | Approved | 2024-09-25
VO-222 | WT-DC-MUM-01 | Solar panel installation | Client | 791101 | -2 | Approved | 2024-07-30
VO-223 | WT-OFF-SYD-02 | Solar panel installation | Consultant | -128731 | 4 | Approved | 2024-04-21
VO-224 | WT-RES-MEL-05 | Added fire escape staircase | Client | 447847 | 25 | Under Review | 2024-01-09
VO-225 | WT-DC-MUM-01 | Facade material change | Architect | -187574 | -4 | Rejected | 2024-10-01
VO-226 | WT-HOS-AKL-03 | Additional MEP riser | Architect | 645328 | 6 | Approved | 2024-02-19
VO-227 | WT-OFF-SYD-02 | Regulatory compliance addition | Consultant | 449887 | 28 | Rejected | 2024-06-30
VO-228 | WT-HOS-AKL-03 | Extra server room cooling | Architect | -117143 | 18 | Under Review | 2024-08-23
VO-229 | WT-OFF-SYD-02 | Green roof addition | Consultant | 114546 | 0 | Approved | 2024-02-17
VO-230 | WT-RES-MEL-05 | Upgraded HVAC system | Architect | 379549 | 25 | Approved | 2024-11-22
VO-231 | WT-DC-MUM-01 | Green roof addition | Consultant | -113298 | 26 | Under Review | 2024-11-26
VO-232 | WT-HOS-AKL-03 | Additional lift shaft | Client | 738256 | 28 | Approved | 2024-04-27
VO-233 | WT-OFF-SYD-02 | Basement depth increase | Architect | 84263 | -3 | Approved | 2024-12-16
VO-234 | WT-HOS-AKL-03 | Basement depth increase | Client | -11934 | 15 | Approved | 2024-04-16
VO-235 | WT-OFF-SYD-02 | Extra server room cooling | Architect | 773995 | -1 | Rejected | 2024-03-24
VO-236 | WT-OFF-SYD-02 | Additional lift shaft | Architect | 509922 | 29 | Rejected | 2024-07-15
VO-237 | WT-OFF-SYD-02 | Extra server room cooling | Client | 325119 | 17 | Approved | 2024-02-20
VO-238 | WT-RES-MEL-05 | Regulatory compliance addition | Client | 157137 | 20 | Rejected | 2024-01-16
VO-239 | WT-HOS-AKL-03 | Extra server room cooling | Architect | 314435 | 9 | Rejected | 2024-10-10
VO-240 | WT-RES-MEL-05 | Upgraded HVAC system | Consultant | 512711 | 19 | Approved | 2025-01-30
VO-241 | WT-HOS-AKL-03 | Extra server room cooling | Consultant | 547748 | -1 | Approved | 2024-05-17
VO-242 | WT-OFF-SYD-02 | Upgraded HVAC system | Consultant | 575584 | 19 | Rejected | 2024-07-03
VO-243 | WT-DC-MUM-01 | Design revision - column grid | Client | 788765 | 14 | Under Review | 2024-07-03
VO-244 | WT-HOS-AKL-03 | Design revision - column grid | Consultant | -108463 | 6 | Under Review | 2024-08-17
ANALYSIS QUESTIONS
Q1. What is the total approved cost impact of all change orders per project?
Q2. Who initiates the most change orders — Client, Consultant, or Contractor?
Q3. What % of change orders are still Pending or Under Review? What is the potential cost exposure?
Q4. Is there a correlation between cost impact and time impact of VOs?
Q5. Which project has the highest change order frequency per month?
Q6. Create a stacked bar chart: Approved vs Pending vs Rejected VO costs per project.

## P09-SubconScore
PROBLEM 9: Subcontractor Performance Scorecard
Scenario: Rate subcontractors on Quality, Time, Safety, Cost, and Communication for vendor management.
Subcontractor | Trade | Project_ID | Quality_Score | Time_Score | Safety_Score | Cost_Score | Communication_Score | Defect_Count | Weighted_Score
Contractor-I | Elevator Installation | WT-HOS-AKL-03 | 3.2 | 2.1 | 3.1 | 2.3 | 3.8 | 10 | 2.83
Contractor-N | Landscaping | WT-DC-MUM-01 | 2.9 | 3.2 | 2.3 | 4.7 | 4.7 | 7 | 3.305
Contractor-J | Elevator Installation | WT-DC-MUM-01 | 4.1 | 2.5 | 2.8 | 2.8 | 2.4 | 5 | 3.075
Contractor-G | Interior Fit-out | WT-OFF-SYD-02 | 2.9 | 4.3 | 3.1 | 4.8 | 4.2 | 15 | 3.705
Contractor-J | IT & Low Current | WT-DC-MUM-01 | 3.4 | 2.4 | 2 | 3.2 | 4.5 | 12 | 2.95
Contractor-M | Facade & Cladding | WT-OFF-SYD-02 | 3 | 4.4 | 4.6 | 4.9 | 2.4 | 10 | 3.895
Contractor-J | MEP - Plumbing | WT-OFF-SYD-02 | 2.9 | 4.9 | 4.9 | 2.9 | 4.1 | 15 | 3.92
Contractor-J | MEP - Plumbing | WT-OFF-SYD-02 | 3.1 | 4.4 | 3.2 | 2.3 | 3.7 | 18 | 3.385
Contractor-I | MEP - Electrical | WT-HOS-AKL-03 | 4.3 | 2.1 | 4.2 | 4.8 | 2.6 | 25 | 3.635
Contractor-E | MEP - HVAC | WT-OFF-SYD-02 | 4 | 2.4 | 2.9 | 2.8 | 2.5 | 13 | 3.05
Contractor-M | Landscaping | WT-DC-MUM-01 | 3.3 | 3.8 | 3.7 | 3.6 | 4.8 | 22 | 3.7
Contractor-G | Elevator Installation | WT-DC-MUM-01 | 4.4 | 3.1 | 4.7 | 3.6 | 3.9 | 2 | 3.965
Contractor-B | MEP - Plumbing | WT-HOS-AKL-03 | 4 | 2.5 | 3.8 | 3.7 | 3.9 | 20 | 3.53
Contractor-G | Facade & Cladding | WT-OFF-SYD-02 | 2.3 | 2.3 | 2.7 | 4.2 | 3.7 | 22 | 2.805
Contractor-J | MEP - Plumbing | WT-OFF-SYD-02 | 3.1 | 3.4 | 4 | 4.1 | 2.5 | 0 | 3.445
Contractor-H | MEP - HVAC | WT-OFF-SYD-02 | 3.2 | 4.9 | 2.3 | 4.8 | 2.4 | 9 | 3.605
Contractor-F | Fire Safety | WT-DC-MUM-01 | 3.6 | 3 | 2.3 | 4.2 | 3.4 | 2 | 3.26
Contractor-E | Civil & Structure | WT-HOS-AKL-03 | 2.3 | 4.5 | 3.9 | 4 | 2.5 | 23 | 3.445
Contractor-D | Elevator Installation | WT-DC-MUM-01 | 3.7 | 3 | 3.3 | 3.4 | 4.4 | 20 | 3.47
Contractor-C | MEP - Electrical | WT-HOS-AKL-03 | 4 | 3.2 | 4.2 | 4.6 | 3.3 | 13 | 3.86
Contractor-G | Civil & Structure | WT-HOS-AKL-03 | 2.6 | 2.8 | 4.1 | 4.4 | 3.7 | 25 | 3.33
Contractor-N | Elevator Installation | WT-DC-MUM-01 | 3.1 | 2.6 | 2.3 | 4 | 3.5 | 20 | 2.99
Contractor-F | IT & Low Current | WT-OFF-SYD-02 | 3.8 | 3.8 | 3 | 4.5 | 3.9 | 21 | 3.755
Contractor-L | Interior Fit-out | WT-HOS-AKL-03 | 3.8 | 4 | 2.9 | 2.7 | 2.4 | 11 | 3.365
Contractor-L | MEP - Electrical | WT-HOS-AKL-03 | 3.2 | 3.8 | 3.7 | 3.3 | 3.5 | 17 | 3.495
Contractor-L | MEP - Electrical | WT-HOS-AKL-03 | 2.5 | 2.9 | 2.6 | 4.5 | 3.9 | 11 | 3.06
Contractor-A | Fire Safety | WT-DC-MUM-01 | 2.6 | 3.2 | 3.7 | 4 | 3.2 | 15 | 3.24
Contractor-G | Fire Safety | WT-OFF-SYD-02 | 2.5 | 3.7 | 4.4 | 2.7 | 2.1 | 7 | 3.17
Contractor-I | Interior Fit-out | WT-DC-MUM-01 | 4.3 | 3.7 | 4.3 | 3.5 | 3.5 | 18 | 3.95
Contractor-B | Interior Fit-out | WT-HOS-AKL-03 | 4.5 | 3.1 | 4.5 | 2.1 | 4.2 | 17 | 3.76
ANALYSIS QUESTIONS
Q1. Rank all subcontractors by their weighted score. Who are the top 3 and bottom 3?
Q2. Which trade has the lowest average quality score?
Q3. Is there a negative correlation between defect count and quality score?
Q4. Create a radar chart for the top-performing subcontractor showing all 5 dimensions.
Q5. Which subcontractors should be blacklisted (weighted score < 3.0 AND defects > 15)?
Q6. Compare subcontractor performance across the 3 projects — is any project a consistent outlier?

## P10-Benchmark
PROBLEM 10: Construction Cost Benchmarking
Scenario: Compare cost per sqm across project types, cities, and countries for WT's portfolio.
Project_ID | Project_Type | City | Country | GFA_sqm | Total_Cost_USD | Cost_per_sqm_USD | Year
WT-BM-100 | Hospital | Canberra | Australia | 31847 | 148948419 | 4677 | 2024
WT-BM-101 | Commercial Office | Gold Coast | Australia | 73895 | 174096620 | 2356 | 2022
WT-BM-102 | Hospital | Kolkata | India | 96915 | 81408600 | 840 | 2025
WT-BM-103 | Residential Tower | Hyderabad | India | 59164 | 48277824 | 816 | 2024
WT-BM-104 | IT Park | Sydney | Australia | 146234 | 486228050 | 3325 | 2024
WT-BM-105 | Hotel | Sydney | Australia | 139850 | 668762700 | 4782 | 2023
WT-BM-106 | Industrial Warehouse | Bangalore | India | 77698 | 65499414 | 843 | 2023
WT-BM-107 | Hospital | Hyderabad | India | 89435 | 73694440 | 824 | 2025
WT-BM-108 | Residential Tower | Hamilton | New Zealand | 75442 | 251674512 | 3336 | 2025
WT-BM-109 | Data Centre | Delhi | India | 110604 | 73330452 | 663 | 2025
WT-BM-110 | Metro Station | Brisbane | Australia | 5648 | 13447888 | 2381 | 2024
WT-BM-111 | Data Centre | Christchurch | New Zealand | 109258 | 291391086 | 2667 | 2025
WT-BM-112 | University Campus | Brisbane | Australia | 79342 | 336489422 | 4241 | 2023
WT-BM-113 | Hotel | Auckland | New Zealand | 95109 | 190027782 | 1998 | 2022
WT-BM-114 | Data Centre | Gold Coast | Australia | 9268 | 24532396 | 2647 | 2025
WT-BM-115 | Commercial Office | Canberra | Australia | 58036 | 147411440 | 2540 | 2024
WT-BM-116 | Residential Tower | Sydney | Australia | 29468 | 102430768 | 3476 | 2022
WT-BM-117 | Shopping Mall | Pune | India | 18575 | 11182150 | 602 | 2023
WT-BM-118 | Industrial Warehouse | Delhi | India | 29951 | 11980400 | 400 | 2022
WT-BM-119 | Residential Tower | Hamilton | New Zealand | 64294 | 232872868 | 3622 | 2022
WT-BM-120 | Commercial Office | Brisbane | Australia | 36612 | 136526148 | 3729 | 2025
WT-BM-121 | Data Centre | Ahmedabad | India | 105419 | 46911455 | 445 | 2022
WT-BM-122 | Shopping Mall | Perth | Australia | 83447 | 297655449 | 3567 | 2023
WT-BM-123 | Data Centre | Wellington | New Zealand | 7221 | 17850312 | 2472 | 2025
WT-BM-124 | Shopping Mall | Kolkata | India | 44681 | 38872470 | 870 | 2025
WT-BM-125 | Hospital | Delhi | India | 31336 | 14759256 | 471 | 2025
WT-BM-126 | Shopping Mall | Canberra | Australia | 87445 | 224908540 | 2572 | 2024
WT-BM-127 | Data Centre | Ahmedabad | India | 79690 | 63592620 | 798 | 2024
WT-BM-128 | Hospital | Wellington | New Zealand | 138568 | 417089680 | 3010 | 2022
WT-BM-129 | Hospital | Auckland | New Zealand | 106157 | 408279822 | 3846 | 2022
WT-BM-130 | IT Park | Mumbai | India | 99659 | 87500602 | 878 | 2025
WT-BM-131 | Hotel | Canberra | Australia | 100790 | 483489630 | 4797 | 2025
WT-BM-132 | Data Centre | Mumbai | India | 22703 | 9240121 | 407 | 2022
WT-BM-133 | Commercial Office | Adelaide | Australia | 137804 | 630315496 | 4574 | 2025
WT-BM-134 | Industrial Warehouse | Adelaide | Australia | 26607 | 111669579 | 4197 | 2023
WT-BM-135 | University Campus | Delhi | India | 86240 | 37945600 | 440 | 2023
WT-BM-136 | IT Park | Brisbane | Australia | 107427 | 493949346 | 4598 | 2022
WT-BM-137 | University Campus | Canberra | Australia | 67557 | 202738557 | 3001 | 2025
WT-BM-138 | Data Centre | Gold Coast | Australia | 19425 | 91841400 | 4728 | 2023
WT-BM-139 | Data Centre | Mumbai | India | 40969 | 31095471 | 759 | 2025
ANALYSIS QUESTIONS
Q1. What is the average cost per sqm by country? Visualise as a bar chart.
Q2. Which project type has the highest and lowest cost per sqm globally?
Q3. Has cost per sqm increased year-over-year? Show the trend by country.
Q4. Create a benchmark table: Project Type × Country showing avg cost/sqm.
Q5. Identify outliers — projects where cost/sqm is >1.5× the country average for that type.
Q6. If WT pitches a 50,000 sqm Data Centre in Mumbai, what should the budget estimate be based on this data?

## P12-EVM
PROBLEM 12: Earned Value Management (EVM)
Scenario: Track EVM metrics for a $25M data centre project over 36 months.
Month | BAC_USD | PV_Planned_USD | EV_Earned_USD | AC_Actual_USD | SV_USD | CV_USD | SPI | CPI | EAC_USD | ETC_USD
Month 1 | 25000000 | 713955 | 583077 | 559427 | -130878 | 23650 | 0.81669 | 1.0423 | 23985982.9834 | 23426555.9834
Month 2 | 25000000 | 1375080 | 1314419 | 1552686 | -60661 | -238267 | 0.95589 | 0.84655 | 29531793.1345 | 27979107.1345
Month 3 | 25000000 | 1996674 | 1848591 | 2172516 | -148083 | -323925 | 0.92584 | 0.8509 | 29380701.3017 | 27208185.3017
Month 4 | 25000000 | 2659718 | 2790438 | 2676937 | 130720 | 113501 | 1.0491 | 1.0424 | 23983125.5882 | 21306188.5882
Month 5 | 25000000 | 3522912 | 3497510 | 3244267 | -25402 | 253243 | 0.99279 | 1.0781 | 23189833.6245 | 19945566.6245
Month 6 | 25000000 | 4311364 | 4279745 | 4009086 | -31619 | 270659 | 0.99267 | 1.0675 | 23418953.6993 | 19409867.6993
Month 7 | 25000000 | 5076108 | 3884193 | 4572625 | -1191915 | -688432 | 0.76519 | 0.84944 | 29430984.7631 | 24858359.7631
Month 8 | 25000000 | 5518420 | 5338129 | 5598832 | -180291 | -260703 | 0.96733 | 0.95344 | 26220947.4518 | 20622115.4518
Month 9 | 25000000 | 6176705 | 5423142 | 5456673 | -753563 | -33531 | 0.878 | 0.99386 | 25154573.677 | 19697900.677
Month 10 | 25000000 | 7227989 | 6017261 | 6220665 | -1210728 | -203404 | 0.83249 | 0.9673 | 25845085.4965 | 19624420.4965
Month 11 | 25000000 | 7370482 | 6885739 | 7471668 | -484743 | -585929 | 0.93423 | 0.92158 | 27127327.9455 | 19655659.9455
Month 12 | 25000000 | 8456065 | 7607646 | 8861641 | -848419 | -1253995 | 0.89967 | 0.85849 | 29120837.7729 | 20259196.7729
Month 13 | 25000000 | 9008847 | 6993716 | 7097954 | -2015131 | -104238 | 0.77632 | 0.98531 | 25372613.0715 | 18274659.0715
Month 14 | 25000000 | 9643700 | 9092039 | 10357281 | -551661 | -1265242 | 0.9428 | 0.87784 | 28478983.0972 | 18121702.0972
Month 15 | 25000000 | 10155362 | 10645116 | 11316790 | 489754 | -671674 | 1.0482 | 0.94065 | 26577422.9233 | 15260632.9233
Month 16 | 25000000 | 10577255 | 9146675 | 10189498 | -1430580 | -1042823 | 0.86475 | 0.89766 | 27850278.9265 | 17660780.9265
Month 17 | 25000000 | 11781571 | 11598138 | 11635370 | -183433 | -37232 | 0.98443 | 0.9968 | 25080254.2615 | 13444884.2615
Month 18 | 25000000 | 12582063 | 10650481 | 10449513 | -1931582 | 200968 | 0.84648 | 1.0192 | 24528265.437 | 14078752.437
Month 19 | 25000000 | 12569110 | 11678398 | 10613223 | -890712 | 1065175 | 0.92913 | 1.1004 | 22719775.0068 | 12106552.0068
Month 20 | 25000000 | 14320401 | 11947221 | 13650848 | -2373180 | -1703627 | 0.83428 | 0.8752 | 28564902.248 | 14914054.248
Month 21 | 25000000 | 14542039 | 12465870 | 13403261 | -2076169 | -937391 | 0.85723 | 0.93006 | 26879914.9197 | 13476653.9197
Month 22 | 25000000 | 14869497 | 11864184 | 11559952 | -3005313 | 304232 | 0.79789 | 1.0263 | 24358927.6768 | 12798975.6768
Month 23 | 25000000 | 15558785 | 14160157 | 16105354 | -1398628 | -1945197 | 0.91011 | 0.87922 | 28434278.6595 | 12328924.6595
Month 24 | 25000000 | 17061766 | 16707135 | 19786940 | -354631 | -3079805 | 0.97921 | 0.84435 | 29608517.5585 | 9821577.5585
Month 25 | 25000000 | 17492521 | 18276175 | 18578220 | 783654 | -302045 | 1.0448 | 0.98374 | 25413167.6896 | 6834947.6896
Month 26 | 25000000 | 18841344 | 19735602 | 18790535 | 894258 | 945067 | 1.0475 | 1.0503 | 23802839.9134 | 5012304.9134
Month 27 | 25000000 | 18256033 | 15433674 | 17307808 | -2822359 | -1874134 | 0.8454 | 0.89172 | 28035787.2014 | 10727979.2014
Month 28 | 25000000 | 19169856 | 17779442 | 19753597 | -1390414 | -1974155 | 0.92747 | 0.90006 | 27775895.6102 | 8022298.6102
Month 29 | 25000000 | 19840193 | 18258838 | 17211341 | -1581355 | 1047497 | 0.9203 | 1.0609 | 23565767.1644 | 6354426.1644
Month 30 | 25000000 | 21767434 | 21789398 | 24907904 | 21964 | -3118506 | 1.001 | 0.8748 | 28578008.4425 | 3670104.4425
Month 31 | 25000000 | 22540417 | 20571227 | 19597529 | -1969190 | 973698 | 0.91264 | 1.0497 | 23816674.8634 | 4219145.8634
Month 32 | 25000000 | 21195474 | 16253757 | 17562165 | -4941717 | -1308408 | 0.76685 | 0.9255 | 27012470.1015 | 9450305.1015
Month 33 | 25000000 | 21816501 | 19490789 | 19481437 | -2325712 | 9352 | 0.8934 | 1.0005 | 24988004.5903 | 5506567.5903
Month 34 | 25000000 | 23880595 | 23687965 | 23740734 | -192630 | -52769 | 0.99193 | 0.99778 | 25055691.7827 | 1314957.7827
Month 35 | 25000000 | 23521603 | 23303495 | 27042893 | -218108 | -3739398 | 0.99073 | 0.86172 | 29011627.8696 | 1968734.8696
Month 36 | 25000000 | 23898889 | 18983212 | 21098110 | -4915677 | -2114898 | 0.79431 | 0.89976 | 27785221.4894 | 6687111.4894
ANALYSIS QUESTIONS
Q1. In which month does the project first show a negative Schedule Variance (SV)?
Q2. What is the CPI trend? Is the project getting more or less cost-efficient over time?
Q3. Based on EAC at Month 36, what is the projected cost overrun?
Q4. Create a line chart with PV, EV, and AC — the classic S-curve.
Q5. At what month does SPI drop below 0.90 (critical schedule delay)?
Q6. If management wants CPI ≥ 1.0 by Month 24, how much cost needs to be recovered?

## P13-LeadTime
PROBLEM 16: Procurement Lead Time Analysis
Scenario: Analyse procurement cycle times to reduce supply chain delays.
PO_Number | Material | Supplier | Order_Date | Expected_Date | Actual_Delivery | Project_ID | Country
PO-600 | Aluminium Facade | Supplier-E | 2024-03-15 | 2024-05-14 | 2024-05-10 | WT-HOS-AKL-03 | India
PO-601 | Aggregate (20mm) | Supplier-I | 2024-01-17 | 2024-02-15 | 2024-02-24 | WT-DC-MUM-01 | New Zealand
PO-602 | PVC Conduits | Supplier-D | 2024-11-27 | 2025-01-08 | 2025-01-15 | WT-OFF-SYD-02 | New Zealand
PO-603 | Aggregate (20mm) | Supplier-E | 2024-12-06 | 2024-12-16 | 2024-12-23 | WT-ITP-BLR-04 | Australia
PO-604 | Aggregate (20mm) | Supplier-F | 2024-10-09 | 2024-10-19 | 2024-10-14 | WT-HOS-AKL-03 | India
PO-605 | MS Pipes | Supplier-H | 2024-04-25 | 2024-06-11 | 2024-06-28 | WT-HOS-AKL-03 | New Zealand
PO-606 | Tiles (Vitrified) | Supplier-J | 2024-04-10 | 2024-06-05 | 2024-06-23 | WT-OFF-SYD-02 | Australia
PO-607 | Plywood (Marine) | Supplier-C | 2024-12-15 | 2024-12-26 | 2024-12-26 | WT-OFF-SYD-02 | New Zealand
PO-608 | TMT Steel (Fe500) | Supplier-G | 2024-01-21 | 2024-02-24 | 2024-02-27 | WT-HOS-AKL-03 | India
PO-609 | RMC M30 | Supplier-J | 2024-05-10 | 2024-05-17 | 2024-05-22 | WT-ITP-BLR-04 | India
PO-610 | Cement (OPC 53) | Supplier-C | 2024-06-14 | 2024-07-29 | 2024-07-25 | WT-HOS-AKL-03 | New Zealand
PO-611 | Aggregate (20mm) | Supplier-J | 2024-10-08 | 2024-11-06 | 2024-11-03 | WT-HOS-AKL-03 | New Zealand
PO-612 | Structural Steel | Supplier-C | 2024-09-23 | 2024-10-04 | 2024-10-24 | WT-OFF-SYD-02 | Australia
PO-613 | Tiles (Vitrified) | Supplier-I | 2024-07-25 | 2024-08-06 | 2024-08-12 | WT-OFF-SYD-02 | India
PO-614 | Bricks (AAC) | Supplier-F | 2024-06-18 | 2024-07-18 | 2024-07-22 | WT-OFF-SYD-02 | New Zealand
PO-615 | Plywood (Marine) | Supplier-I | 2024-11-28 | 2024-12-05 | 2024-12-03 | WT-HOS-AKL-03 | Australia
PO-616 | Structural Steel | Supplier-J | 2024-11-14 | 2024-12-06 | 2024-12-02 | WT-HOS-AKL-03 | Australia
PO-617 | Waterproofing Membrane | Supplier-B | 2024-07-16 | 2024-08-08 | 2024-08-20 | WT-HOS-AKL-03 | India
PO-618 | Waterproofing Membrane | Supplier-I | 2024-07-10 | 2024-08-18 | 2024-09-07 | WT-ITP-BLR-04 | New Zealand
PO-619 | Cement (OPC 53) | Supplier-E | 2024-11-29 | 2024-12-18 | 2024-12-23 | WT-DC-MUM-01 | India
PO-620 | RMC M30 | Supplier-I | 2024-09-30 | 2024-10-07 | 2024-10-22 | WT-DC-MUM-01 | India
PO-621 | Bricks (AAC) | Supplier-D | 2024-12-16 | 2025-01-19 | 2025-01-17 | WT-OFF-SYD-02 | New Zealand
PO-622 | PVC Conduits | Supplier-G | 2024-11-27 | 2025-01-25 | 2025-01-22 | WT-OFF-SYD-02 | India
PO-623 | Plywood (Marine) | Supplier-F | 2024-01-20 | 2024-02-01 | 2024-01-29 | WT-DC-MUM-01 | India
PO-624 | Aggregate (20mm) | Supplier-E | 2024-10-12 | 2024-10-23 | 2024-11-05 | WT-OFF-SYD-02 | Australia
PO-625 | Glass (DGU) | Supplier-G | 2024-08-18 | 2024-10-04 | 2024-10-11 | WT-ITP-BLR-04 | Australia
PO-626 | Cement (OPC 53) | Supplier-G | 2024-12-10 | 2024-12-24 | 2025-01-05 | WT-DC-MUM-01 | India
PO-627 | Aggregate (20mm) | Supplier-J | 2024-01-24 | 2024-03-15 | 2024-03-12 | WT-HOS-AKL-03 | New Zealand
PO-628 | TMT Steel (Fe500) | Supplier-E | 2024-06-03 | 2024-07-18 | 2024-07-15 | WT-HOS-AKL-03 | Australia
PO-629 | Glass (DGU) | Supplier-G | 2024-12-04 | 2024-12-12 | 2024-12-22 | WT-OFF-SYD-02 | New Zealand
PO-630 | Structural Steel | Supplier-C | 2024-07-19 | 2024-09-14 | 2024-10-04 | WT-HOS-AKL-03 | India
PO-631 | Aluminium Facade | Supplier-F | 2024-01-06 | 2024-02-17 | 2024-02-29 | WT-OFF-SYD-02 | India
PO-632 | Cement (OPC 53) | Supplier-A | 2024-10-20 | 2024-12-04 | 2024-12-11 | WT-DC-MUM-01 | Australia
PO-633 | Structural Steel | Supplier-F | 2024-04-18 | 2024-05-21 | 2024-06-05 | WT-OFF-SYD-02 | India
PO-634 | RMC M30 | Supplier-D | 2024-11-11 | 2025-01-10 | 2025-01-13 | WT-OFF-SYD-02 | India
PO-635 | RMC M30 | Supplier-J | 2024-01-28 | 2024-03-23 | 2024-04-04 | WT-ITP-BLR-04 | New Zealand
PO-636 | TMT Steel (Fe500) | Supplier-E | 2024-12-09 | 2024-12-20 | 2024-12-23 | WT-DC-MUM-01 | India
PO-637 | Sand (River) | Supplier-J | 2024-09-06 | 2024-10-04 | 2024-10-10 | WT-OFF-SYD-02 | India
PO-638 | TMT Steel (Fe500) | Supplier-E | 2024-11-13 | 2024-11-24 | 2024-11-25 | WT-HOS-AKL-03 | New Zealand
PO-639 | Plywood (Marine) | Supplier-F | 2024-11-11 | 2024-12-30 | 2025-01-03 | WT-OFF-SYD-02 | New Zealand
PO-640 | MS Pipes | Supplier-F | 2024-06-10 | 2024-07-14 | 2024-07-14 | WT-DC-MUM-01 | Australia
PO-641 | Structural Steel | Supplier-D | 2024-11-24 | 2024-12-28 | 2024-12-31 | WT-HOS-AKL-03 | India
PO-642 | Bricks (AAC) | Supplier-F | 2024-09-02 | 2024-10-08 | 2024-10-17 | WT-HOS-AKL-03 | Australia
PO-643 | Plywood (Marine) | Supplier-I | 2024-02-25 | 2024-03-14 | 2024-03-29 | WT-DC-MUM-01 | Australia
PO-644 | PVC Conduits | Supplier-C | 2024-10-02 | 2024-10-21 | 2024-10-24 | WT-DC-MUM-01 | India
PO-645 | Waterproofing Membrane | Supplier-A | 2024-09-16 | 2024-11-02 | 2024-10-28 | WT-ITP-BLR-04 | New Zealand
PO-646 | Structural Steel | Supplier-A | 2024-10-09 | 2024-11-01 | 2024-11-13 | WT-ITP-BLR-04 | India
PO-647 | Copper Wiring | Supplier-G | 2024-04-24 | 2024-06-19 | 2024-07-02 | WT-HOS-AKL-03 | India
PO-648 | Plywood (Marine) | Supplier-I | 2024-09-18 | 2024-09-30 | 2024-10-07 | WT-HOS-AKL-03 | New Zealand
PO-649 | Cement (OPC 53) | Supplier-D | 2024-11-10 | 2024-12-30 | 2024-12-30 | WT-OFF-SYD-02 | Australia
ANALYSIS QUESTIONS
Q1. What is the average lead time (order to delivery) by material?
Q2. Which supplier has the worst on-time delivery rate?
Q3. How many POs were delivered late? What is the average delay in days?
Q4. Is there a country-level difference in procurement lead times?
Q5. Which material has the longest and most unpredictable lead time (highest std deviation)?
Q6. Create a supplier reliability scorecard based on on-time delivery %.

## P14-PaymentAging
PROBLEM 19: Client Payment Aging Tracker
Scenario: Track client invoice payments to manage cash flow and flag overdue accounts.
Invoice_No | Project_ID | Client_Name | Invoice_Date | Due_Date | Amount_USD | Paid_Amount_USD | Payment_Date | Outstanding_USD
INV-700 | WT-HOS-AKL-03 | GPT Group | 2024-06-08 | 2024-07-08 | 1697785 | 1697785 | 2024-08-14 | 0
INV-701 | WT-ITP-BLR-04 | Ascendas REIT | 2024-06-18 | 2024-07-18 | 218240 | 109120 | 2024-07-15 | 109120
INV-702 | WT-HOS-AKL-03 | GPT Group | 2024-02-06 | 2024-03-07 | 1189156 | 1189156 | 2024-03-20 | 0
INV-703 | WT-OFF-SYD-02 | Goodman Group | 2025-02-22 | 2025-03-24 | 850225 | 0 |  | 850225 | WT-HOS-AKL-03
INV-704 | WT-DC-MUM-01 | Tata Realty | 2024-07-16 | 2024-08-15 | 1667376 | 1667376 | 2024-09-05 | 0
INV-705 | WT-DC-MUM-01 | Tata Realty | 2024-08-23 | 2024-09-22 | 1592083 | 0 |  | 1592083
INV-706 | WT-RES-MEL-05 | Tata Realty | 2024-08-30 | 2024-09-29 | 866049 | 866049 | 2024-10-28 | 0 | #VALUE!
INV-707 | WT-HOS-AKL-03 | Brookfield | 2024-11-18 | 2024-12-18 | 1577223 | 0 |  | 1577223
INV-708 | WT-RES-MEL-05 | Dexus | 2024-03-03 | 2024-04-02 | 581235 | 581235 | 2024-04-30 | 0
INV-709 | WT-OFF-SYD-02 | Stockland | 2024-01-27 | 2024-02-26 | 1861221 | 1861221 | 2024-03-14 | 0
INV-710 | WT-DC-MUM-01 | Tata Realty | 2024-11-20 | 2024-12-20 | 960502 | 720376 | 2024-12-11 | 240126
INV-711 | WT-OFF-SYD-02 | Goodman Group | 2024-10-26 | 2024-11-25 | 300923 | 300923 | 2024-12-16 | 0
INV-712 | WT-DC-MUM-01 | Ascendas REIT | 2024-10-24 | 2024-11-23 | 1693066 | 1693066 | 2025-01-12 | 0
INV-713 | WT-RES-MEL-05 | Brookfield | 2024-07-09 | 2024-08-08 | 1666478 | 0 |  | 1666478
INV-714 | WT-OFF-SYD-02 | Brookfield | 2024-09-12 | 2024-10-12 | 241682 | 241682 | 2024-11-14 | 0
INV-715 | WT-DC-MUM-01 | Ascendas REIT | 2024-07-01 | 2024-07-31 | 1401771 | 700885 | 2024-09-27 | 700886
INV-716 | WT-DC-MUM-01 | Brookfield | 2024-09-06 | 2024-10-06 | 537954 | 403465 | 2024-11-09 | 134489
INV-717 | WT-ITP-BLR-04 | Tata Realty | 2024-01-11 | 2024-02-10 | 1495461 | 1495461 | 2024-03-16 | 0
INV-718 | WT-OFF-SYD-02 | Goodman Group | 2024-01-21 | 2024-02-20 | 1067752 | 1067752 | 2024-04-06 | 0
INV-719 | WT-RES-MEL-05 | Goodman Group | 2024-10-04 | 2024-11-03 | 1511794 | 1511794 | 2024-11-17 | 0
INV-720 | WT-RES-MEL-05 | Brookfield | 2024-10-05 | 2024-11-04 | 779105 | 584328 | 2024-12-23 | 194777
INV-721 | WT-HOS-AKL-03 | Embassy Group | 2025-03-16 | 2025-04-15 | 1212913 | 606456 | 2025-04-13 | 606457
INV-722 | WT-RES-MEL-05 | Brookfield | 2024-08-18 | 2024-09-17 | 670070 | 502552 | 2024-11-15 | 167518
INV-723 | WT-HOS-AKL-03 | Mirvac | 2024-01-01 | 2024-01-31 | 1677217 | 1677217 | 2024-03-25 | 0
INV-724 | WT-ITP-BLR-04 | Brookfield | 2024-01-10 | 2024-02-09 | 1349677 | 1012257 | 2024-02-29 | 337420
INV-725 | WT-HOS-AKL-03 | Lendlease | 2024-12-03 | 2025-01-02 | 1180273 | 1180273 | 2025-01-16 | 0
INV-726 | WT-RES-MEL-05 | Mirvac | 2025-01-27 | 2025-02-26 | 1206511 | 603255 | 2025-03-24 | 603256
INV-727 | WT-HOS-AKL-03 | GPT Group | 2024-11-24 | 2024-12-24 | 725333 | 0 |  | 725333
INV-728 | WT-DC-MUM-01 | Dexus | 2024-12-03 | 2025-01-02 | 189837 | 0 |  | 189837
INV-729 | WT-OFF-SYD-02 | Brookfield | 2025-03-23 | 2025-04-22 | 115585 | 57792 | 2025-04-25 | 57793
INV-730 | WT-ITP-BLR-04 | Tata Realty | 2024-02-20 | 2024-03-21 | 116725 | 116725 | 2024-04-29 | 0
INV-731 | WT-ITP-BLR-04 | Dexus | 2024-11-15 | 2024-12-15 | 1520762 | 1520762 | 2025-01-06 | 0
INV-732 | WT-DC-MUM-01 | Stockland | 2024-04-23 | 2024-05-23 | 1320776 | 1320776 | 2024-05-22 | 0
INV-733 | WT-DC-MUM-01 | Tata Realty | 2024-12-01 | 2024-12-31 | 1080552 | 0 |  | 1080552
INV-734 | WT-ITP-BLR-04 | Ascendas REIT | 2024-07-03 | 2024-08-02 | 1220252 | 1220252 | 2024-09-14 | 0
INV-735 | WT-HOS-AKL-03 | Ascendas REIT | 2025-02-25 | 2025-03-27 | 1343802 | 1007851 | 2025-05-23 | 335951
INV-736 | WT-DC-MUM-01 | Lendlease | 2025-03-03 | 2025-04-02 | 687334 | 0 |  | 687334
INV-737 | WT-OFF-SYD-02 | Dexus | 2024-02-19 | 2024-03-20 | 262284 | 262284 | 2024-04-08 | 0
INV-738 | WT-RES-MEL-05 | GPT Group | 2024-04-07 | 2024-05-07 | 455000 | 455000 | 2024-05-28 | 0
INV-739 | WT-RES-MEL-05 | Brookfield | 2024-10-12 | 2024-11-11 | 1621174 | 1621174 | 2024-12-24 | 0
ANALYSIS QUESTIONS
Q1. What is the total outstanding amount across all projects?
Q2. Which client has the highest overdue amount (paid after due date)?
Q3. Create an aging bucket analysis: 0–30 days, 31–60 days, 61–90 days, 90+ days.
Q4. What is the average days-to-pay by client?
Q5. Which project has the worst collection rate (Paid / Invoiced)?
Q6. If WT charges 1.5% monthly interest on overdue amounts, what is the total interest receivable?

## P15-Portfolio
PROBLEM 20: Multi-Project Portfolio Dashboard Data
Scenario: Build a portfolio-level dashboard summarising all WT projects for executive reporting.
Project_ID | Project_Name | Country | Type | Status | Budget_USD | Spent_USD | Completion_% | SPI | CPI | Risk_Level | Budget_Variance_USD
WT-2000 | Hotel Chennai | India | Hotel | Completed | 95528859 | 71188774 | 68 | 0.91 | 0.79 | Medium | 6229149.88
WT-2001 | Industrial Warehouse Christchurch | New Zealand | Industrial Warehouse | Completed | 93252435 | 29007060 | 30 | 1 | 1.12 | High | 1031329.5
WT-2002 | Shopping Mall Christchurch | New Zealand | Shopping Mall | Completed | 60343779 | 54951597 | 91 | 1.06 | 0.99 | Medium | 38758.11
WT-2003 | IT Park Adelaide | Australia | IT Park | Completed | 53319528 | 35960753 | 67 | 0.9 | 1.04 | High | 236669.24
WT-2004 | IT Park Mumbai | India | IT Park | On Hold | 45512501 | 4346975 | 10 | 0.81 | 1.09 | Low | -204275.1
WT-2005 | IT Park Sydney | Australia | IT Park | On Hold | 17655004 | 2499209 | 14 | 0.78 | 0.86 | Medium | 27508.44
WT-2006 | University Campus Ahmedabad | India | University Campus | Completed | 17335296 | 14243396 | 83 | 1.16 | 1.04 | High | -144899.68
WT-2007 | Residential Tower Auckland | New Zealand | Residential Tower | Planning | 97555887 | 0 | 0 | 1.11 | 0.79 | High | 0
WT-2008 | Hotel Bangalore | India | Hotel | Planning | 15533057 | 0 | 0 | 1.16 | 0.88 | Critical | 0
WT-2009 | Data Centre Canberra | Australia | Data Centre | On Hold | 92614538 | 94677516 | 87 | 1.02 | 1 | Low | 14102867.94
WT-2010 | IT Park Melbourne | Australia | IT Park | In Progress | 47857940 | 39611941 | 79 | 0.86 | 1.03 | Medium | 1804168.4
WT-2011 | Industrial Warehouse Bangalore | India | Industrial Warehouse | Planning | 84877290 | 0 | 0 | 0.75 | 0.92 | Critical | 0
WT-2012 | Residential Tower Hyderabad | India | Residential Tower | Completed | 16079017 | 11818124 | 70 | 0.72 | 0.91 | Low | 562812.1
WT-2013 | IT Park Adelaide | Australia | IT Park | Planning | 98666595 | 0 | 0 | 0.77 | 0.97 | Critical | 0
WT-2014 | Hotel Adelaide | Australia | Hotel | On Hold | 80318641 | 84744219 | 88 | 0.96 | 0.85 | High | 14063814.92
WT-2015 | Shopping Mall Canberra | Australia | Shopping Mall | In Progress | 20103503 | 18998132 | 95 | 0.88 | 0.83 | High | -100195.85
WT-2016 | University Campus Mumbai | India | University Campus | On Hold | 51938140 | 51992565 | 88 | 1.1 | 1 | Critical | 6287001.8
WT-2017 | Hospital Bangalore | India | Hospital | On Hold | 96987358 | 50008645 | 57 | 1.06 | 0.78 | Low | -5274149.06
WT-2018 | Hotel Ahmedabad | India | Hotel | On Hold | 43612439 | 4654142 | 11 | 1.1 | 0.87 | Critical | -143226.29
WT-2019 | Shopping Mall Mumbai | India | Shopping Mall | On Hold | 77209870 | 26320248 | 37 | 0.96 | 0.85 | Critical | -2247403.9
WT-2020 | Commercial Office Hyderabad | India | Commercial Office | Planning | 83249598 | 0 | 0 | 0.96 | 0.85 | Low | 0
WT-2021 | Hospital Melbourne | Australia | Hospital | Completed | 12124981 | 9028552 | 69 | 0.7 | 0.91 | High | 662315.11
WT-2022 | Data Centre Perth | Australia | Data Centre | In Progress | 44258091 | 40554277 | 93 | 1.19 | 0.95 | Low | -605747.63
WT-2023 | Metro Station Brisbane | Australia | Metro Station | In Progress | 30020518 | 10772254 | 35 | 0.93 | 1.12 | Low | 265072.7
WT-2024 | Hospital Bangalore | India | Hospital | Completed | 49770958 | 35393957 | 72 | 0.78 | 0.89 | High | -441132.76
ANALYSIS QUESTIONS
Q1. How many projects are In Progress, On Hold, Completed, and Planning? Show as a pie chart.
Q2. What is the total portfolio budget and total spent? What is the overall budget variance?
Q3. Which projects have CPI < 0.90 AND SPI < 0.90? These are 'red zone' — list them.
Q4. Create a bubble chart: X = SPI, Y = CPI, Size = Budget. Which quadrant has the most projects?
Q5. What is the average completion % by country?
Q6. Build a traffic-light summary: Green (CPI≥1, SPI≥1), Amber (either <1), Red (both <0.9). Count per category.
Q7. If WT's board asks 'how is our portfolio doing?' — write a 3-line executive summary using this data.

## Analysis report
ANALYSIS REPORT — WT PARTNERSHIP CONSTRUCTION DATA (20 PROBLEMS)
Every figure below is a live formula referencing the source sheets. Update source data and answers refresh automatically.
PROBLEM 01 — Project Cost Overrun Analysis ¦ Source sheet: P01-CostOverrun (50 projects) | [6 empty] | CONTENTS — jump to row
Q1. Which country has the highest average cost overrun percentage? | [6 empty] | Problem 01 — Cost Overrun (7 questions) | row 5
Country | Avg Overrun % | No. of Projects | Total Budget USD | Total Actual USD | Portfolio Overrun % |  | Problem 02 — Material Price Fluctuation (6) | row 86
Australia | 16.73% | 15 | 690300200 | 826447969 | 19.72% |  | Problem 03 — BOQ Variance (6) | row 159
India | 15.76% | 28 | 1171274510 | 1361321621 | 16.23% |  | Problem 04 — Labour Productivity (6) | row 212
New Zealand | 19.75% | 7 | 290824343 | 344177656 | 18.35% |  | Problem 05 — Tender Bid Comparison (6) | row 276
ANSWER: New Zealand has the highest average cost overrun at 19.7%, vs India the lowest at 15.8%. | [6 empty] | Problem 06 — Delay Root Cause (6) | row 372
[7 empty] | Problem 07 — Cash Flow (6) | row 465
Q2. What is the total budget vs actual cost for each project type? Which type has the worst variance? | [6 empty] | Problem 08 — Change Orders (6) | row 534
Project Type | Total Budget USD | Total Actual USD | Variance USD | Variance % | No. of Projects |  | Problem 09 — Subcontractor Scorecard (6) | row 584
Residential Tower | 238232594 | 300895518 | 62662924 | 26.3% | 4 |  | Problem 10 — Cost Benchmarking (6) | row 649
IT Park | 207257585 | 251957838 | 44700253 | 21.57% | 7 |  | Problem 12 — Earned Value Management (6) | row 714
University Campus | 304580669 | 370758337 | 66177668 | 21.73% | 6 |  | Problem 13 — Procurement Lead Time (6) | row 781
Industrial Warehouse | 162936980 | 186876390 | 23939410 | 14.69% | 3 |  | Problem 14 — Client Payment Aging (6) | row 846
Data Centre | 377404871 | 423300399 | 45895528 | 12.16% | 9 |  | Problem 15 — Portfolio Dashboard (7) | row 916
Hospital | 202218749 | 252196787 | 49978038 | 24.71% | 5 |  | Note: grey blocks in columns H–V are helper calculations.
Commercial Office | 139292114 | 159577657 | 20285543 | 14.56% | 3 |  | Note: P11 and P16–P20 have no data sheet in this workbook.
Hotel | 276402274 | 314328476 | 37926202 | 13.72% | 7
Metro Station | 194389591 | 220692772 | 26303181 | 13.53% | 5
Shopping Mall | 49683626 | 51363072 | 1679446 | 3.38% | 1
TOTAL | 2152399053 | 2531947246 | 379548193 | 17.63% | 50
ANSWER: Worst variance = Residential Tower at 26.3% ($6,26,62,924 over budget). Best = Shopping Mall at 3.4%. Portfolio total: $2,15,23,99,053 budget vs $2,53,19,47,246 actual (17.6%).
Q3. Top 5 projects with the highest absolute cost overrun (USD)
Rank | Project_ID | Project Name | Type | Absolute Overrun USD | Overrun %
1 | WT-1028 | Residential Tower Per-29 | Residential Tower | 24654239 | 33.14%
2 | WT-1032 | Residential Tower Hyd-33 | Residential Tower | 21628203 | 32.87%
3 | WT-1033 | IT Park Syd-34 | IT Park | 19739335 | 33.57%
4 | WT-1034 | University Campus Kol-35 | University Campus | 19335358 | 34.81%
5 | WT-1043 | Industrial Warehouse Can-44 | Industrial Warehouse | 19116067 | 29.55%
ANSWER: Largest single overrun is Residential Tower Per-29 (WT-1028) at $2,46,54,239 (33.1%). The top 5 together account for $10,44,73,202 of overrun.
Q4. Is there a correlation between project duration and cost overrun percentage?
Correlation coefficient (Duration months vs Overrun %) | -0.15638
ANSWER: r = -0.156 — effectively no linear relationship; duration does not explain cost overrun in this portfolio.
Q5. Pivot — average overrun % by Country × Project Type
Project Type | Australia | India | New Zealand | Grand Average | Projects
Residential Tower | 23.32% | 25.87% | - | 24.59% | 4
IT Park | 15.3% | 18.08% | 24.88% | 18.26% | 7
University Campus | 8.872% | 27.21% | - | 21.1% | 6
Industrial Warehouse | 29.55% | 6.115% | 3.773% | 13.15% | 3
Data Centre | 11.29% | 12.64% | -1.848% | 10.73% | 9
Hospital | 18.57% | 23.83% | 29.91% | 25.21% | 5
Commercial Office | - | 13.32% | - | 13.32% | 3
Hotel | 22.21% | 7.426% | - | 13.76% | 7
Metro Station | 9.327% | 5.798% | 25.81% | 15.21% | 5
Shopping Mall | - | 3.38% | - | 3.38% | 1
Grand Average | 16.73% | 15.76% | 19.75% | 16.61% | 50
Max-cell locator (row offset, col offset) | 6 | 3
ANSWER: Highest average overrun combination is Hospital in New Zealand at 29.9%. Portfolio average overrun is 16.6%.
Q6. What percentage of projects came in under budget vs over budget?
Category | No. of Projects | % of Portfolio
Over budget (variance > 0) | 4500% | 90%
Under budget (variance < 0) | 500% | 10%
Total | 5000% | 100%
ANSWER: 90.0% of projects (45 of 50) came in over budget and 10.0% (5) under budget.
Q7. Which city has the most cost-efficient project delivery?
City | Avg Overrun % | No. of Projects | Total Budget USD | Total Actual USD
Perth | 18.8% | 5 | 245312751 | 295064019 | 20.28%
Hyderabad | 25.87% | 2 | 124452671 | 157142270 | 26.27%
Sydney | 33.57% | 1 | 58792612 | 78531947 | 33.57%
Kolkata | 20.9% | 4 | 134555617 | 163376489 | 21.42%
Canberra | 20.54% | 3 | 166360502 | 202363636 | 21.64%
Delhi | 16.72% | 3 | 126142816 | 150895749 | 19.62%
Mumbai | 15.78% | 6 | 282524903 | 334004416 | 18.22%
Auckland | 31.1% | 1 | 55826716 | 73187548 | 31.1%
Chennai | 16.73% | 4 | 178758813 | 210269197 | 17.63%
Christchurch | 17.25% | 3 | 135595096 | 156962814 | 15.76%
Adelaide | 14.06% | 3 | 148852192 | 173354770 | 16.46%
Hamilton | 15.08% | 2 | 85200877 | 96242381 | 12.96%
Brisbane | 11.29% | 2 | 55841056 | 62443180 | 11.82%
Ahmedabad | 9.568% | 5 | 163512448 | 173194884 | 5.922%
Wellington | 25.23% | 1 | 14201654 | 17784913 | 25.23%
Bangalore | 31.22% | 1 | 11046318 | 14494625 | 31.22%
Pune | 5.098% | 3 | 150280924 | 157943991 | 5.099%
Gold Coast | -2.976% | 1 | 15141087 | 14690417 | -2.976%
ANSWER: Gold Coast is the most cost-efficient city (avg overrun -3.0%), while Sydney is the least efficient (33.6%). Note: small samples per city.
PROBLEM 02 — Material Price Fluctuation Tracker ¦ Source sheet: P02-MaterialPrice (90 records, 15 materials, 18 months)
Q1. Which material has shown the highest average price increase over 18 months?
Material | Unit | Avg Price Change % | Data Points | Avg Base Price USD | Avg Current Price USD
Waterproofing Membrane | sqm | 2.52% | 10 | 15 | 15.378
Cement (OPC 53) | MT | 11.86% | 6 | 85 | 95.0783
Aluminium Facade | sqm | 11.7% | 8 | 120 | 134.0375
Bricks (AAC) | 1000 nos | 7.74% | 6 | 380 | 409.4117
Tiles (Vitrified) | sqm | 8.361% | 6 | 18 | 19.505
PVC Conduits | m | 3.042% | 8 | 3 | 3.0913
Sand (River) | cum | 9.52% | 4 | 25 | 27.38
Structural Steel | MT | 6.968% | 6 | 950 | 1016.1933
Aggregate (20mm) | cum | 14.61% | 5 | 22 | 25.214
MS Pipes | m | 9.938% | 4 | 12 | 13.1925
RMC M30 | cum | 14.78% | 4 | 75 | 86.085
Glass (DGU) | sqm | 4.393% | 8 | 95 | 99.1738
Copper Wiring | m | 1.925% | 5 | 8 | 8.154
Plywood (Marine) | sheet | 9.256% | 6 | 45 | 49.165
TMT Steel (Fe500) | MT | 3.914% | 4 | 650 | 675.44
ANSWER: RMC M30 shows the highest average price increase at 14.8%; the lowest is Copper Wiring at 1.9%.
Q2. Monthly price trend for TMT Steel and Cement (line chart placed to the right)
Month | TMT Steel (Fe500) USD/MT | Cement (OPC 53) USD/MT | Month Index
2024-01 | #N/A | 96.77 | 1
2024-02 | #N/A | 94.59 | 2
2024-03 | 710.14 | #N/A | 3
2024-04 | #N/A | #N/A | 4
2024-05 | #N/A | #N/A | 5
2024-06 | #N/A | 81.11 | 6
2024-07 | #N/A | #N/A | 7
2024-08 | #N/A | #N/A | 8
2024-09 | #N/A | 105.52 | 9
2024-10 | #N/A | #N/A | 10
2024-11 | #N/A | #N/A | 11
2024-12 | #N/A | 90.44 | 12
2025-01 | 607.52 | #N/A | 13
2025-02 | 688.19 | #N/A | 14
2025-03 | #N/A | #N/A | 15
2025-04 | #N/A | #N/A | 16
2025-05 | #N/A | 102.04 | 17
2025-06 | 695.91 | #N/A | 18
ANSWER: Both series trend upward overall but the dataset is sampled — only 4 of 18 months carry a TMT Steel price and 6 carry a Cement price (#N/A = no data that month). TMT Steel averages $675/MT (avg change 3.9%) and Cement $95/MT (avg change 11.9%). See the line chart to the right.
Q3. Which country has the most volatile material pricing? (standard deviation)
Country | StDev of Price Change % | Avg Price Change % | Min Change % | Max Change % | Data Points
Australia | 9.21% | 7.875% | -7.333% | 23.32% | 33
India | 9.792% | 7.088% | -7.889% | 24.87% | 39
New Zealand | 8.992% | 7.906% | -7.947% | 23.07% | 18
ANSWER: India has the most volatile material pricing (std dev of price change = 9.8% pts), the least volatile is New Zealand at 9.0%.
Q4. Top 3 materials with price increase > 15% — flag as procurement risk
Rank | Material | Avg Price Change % | Flag | Avg Current Price USD | Unit
1 | RMC M30 | 14.78% | Monitor | 86.085 | cum
2 | Aggregate (20mm) | 14.61% | Monitor | 25.214 | cum
3 | Cement (OPC 53) | 11.86% | Monitor | 95.0783 | MT
ANSWER: No material's AVERAGE increase exceeds 15% (highest is RMC M30 at 14.8%), though 20 of 90 individual monthly records are above 15%. Treat the top 3 — RMC M30 (14.8%), Aggregate (20mm) (14.6%), Cement (OPC 53) (11.9%) — as procurement risk and forward-buy / lock rates.
Q5. Average price change % by material across all months
See the table under Q1 (column C) — full 15-material list.
Average across all materials & months | 7.54% | Median | 7.199% | Materials above average | 9
ANSWER: The portfolio-wide average material price change is 7.5% (median 7.2%). 9 of 15 materials sit above that average — see column C of the Q1 table for the material-by-material figures.
Q6. Projected cost of 500 MT of TMT Steel next quarter (trend-based)
# | Observed Month | Month Index | Price USD/MT
1 | 2024-03 | 3 | 710.14
2 | 2025-01 | 13 | 607.52
3 | 2025-02 | 14 | 688.19
4 | 2025-06 | 18 | 695.91
Trend slope (USD/MT per month) | -1.9008 | Intercept | 698.2498
Latest observed month index | 18 | Forecast month index (+3 months) | 21
Projected price USD/MT | 658.3326 | Quantity required (MT) | 500
Projected procurement cost USD | 329166.3115 | Cost at latest observed price | 347955
ANSWER: Fitting a linear trend to the 4 observed TMT Steel price points gives a slope of -$1.90/MT per month. Projected price for next quarter (month index 21) is $658/MT, so 500 MT ≈ $3,29,166 (vs $3,47,955 at the latest observed price). Caveat: only 4 data points — treat as indicative.
PROBLEM 03 — BOQ Variance Analysis ¦ Source sheet: P03-BOQVariance (72 BOQ line items, 3 projects)
Q1. Which project has the highest total BOQ variance (in USD)?
Project_ID | Total BOQ Amount USD | Total Actual Amount USD | Variance USD | Variance % | BOQ Line Items
WT-DC-MUM-01 | 5686239.8 | 6061894.82 | 375655.02 | 6.606% | 24
WT-OFF-SYD-02 | 5691799.9 | 6408709.85 | 716909.95 | 12.6% | 24
WT-HOS-AKL-03 | 4619527.89 | 5117552.24 | 498024.35 | 10.78% | 24
TOTAL | 15997567.59 | 17588156.91 | 1590589.32 | 9.943% | 72
ANSWER: WT-OFF-SYD-02 has the highest total BOQ variance at $7,16,910 (12.6% over BOQ). All three projects combined are $15,90,589 (9.9%) above BOQ.
Q2. Which trade consistently exceeds BOQ quantities across all 3 projects?
Trade (avg qty variance %) | WT-DC-MUM-01 | WT-OFF-SYD-02 | WT-HOS-AKL-03 | Avg Qty Var % (all) | Projects Over BOQ
Civil & Structure | 13.63% | 12.69% | 2.558% | 9.626% | 3
MEP - Electrical | 5.437% | 14.53% | 13.38% | 11.12% | 3
MEP - Plumbing | -3.799% | 20.31% | 16.65% | 11.05% | 2
MEP - HVAC | 4.947% | 11.9% | 5.421% | 7.422% | 3
Interior Fit-out | 7.679% | 11.71% | 10.69% | 10.03% | 3
ANSWER: MEP - Electrical is the worst offender — average quantity variance of 11.1% and over BOQ in 3 of 3 projects. 4 of 5 trades exceed BOQ in all three projects.
Q3. Top 5 BOQ items with the highest quantity variance %
Rank | Project_ID | Trade | BOQ Item | Qty Variance % | Overrun Impact USD
1 | WT-HOS-AKL-03 | Civil & Structure | Plastering | 28.94% | 151507.6
2 | WT-OFF-SYD-02 | MEP - Electrical | LT Panels | 28.45% | 70934.1
3 | WT-DC-MUM-01 | Civil & Structure | Excavation | 27.75% | 131440.05
4 | WT-HOS-AKL-03 | MEP - Electrical | Conduit Laying | 27.7% | 27898.51
5 | WT-HOS-AKL-03 | Interior Fit-out | False Ceiling | 27.61% | 10833.76
ANSWER: The worst item is Plastering (Civil & Structure, WT-HOS-AKL-03) at 28.9% over BOQ, costing $1,51,508. The top 5 items alone add $3,92,614 of overrun.
Q4. Total financial impact of quantity overruns per project
Project_ID | Overrun Impact USD (items over BOQ) | Savings USD (items under BOQ) | Net Impact USD | Items Over BOQ | Items Under BOQ
WT-DC-MUM-01 | 502032.7 | -126377.68 | 375655.02 | 16 | 8
WT-OFF-SYD-02 | 768547.75 | -51637.8 | 716909.95 | 21 | 3
WT-HOS-AKL-03 | 557911.04 | -59886.69 | 498024.35 | 16 | 8
TOTAL | 1828491.49 | -237902.17 | 1590589.32 | 53 | 19
ANSWER: Gross overrun impact is $18,28,491 against $2,37,902 of savings, a net $15,90,589 across the three projects. Worst project: WT-OFF-SYD-02 at $7,16,910 net.
Q5. BOQ Amount vs Actual Amount per trade — Project WT-DC-MUM-01 (chart to the right)
Trade | BOQ Amount USD | Actual Amount USD | Variance USD | Variance % | Items
Civil & Structure | 1893094.3 | 2132023.62 | 238929.32 | 12.62% | 6
MEP - Electrical | 986727.76 | 1007358.05 | 20630.29 | 2.091% | 5
MEP - Plumbing | 765988.47 | 756568.97 | -9419.5 | -1.23% | 4
MEP - HVAC | 837434.33 | 874041.79 | 36607.46 | 4.371% | 4
Interior Fit-out | 1202994.94 | 1291902.39 | 88907.45 | 7.391% | 5
TOTAL | 5686239.8 | 6061894.82 | 375655.02 | 6.606% | 24
ANSWER: For WT-DC-MUM-01 the BOQ of $56,86,240 has been measured at $60,61,895, a $3,75,655 (6.6%) build-up. The biggest contributor is Civil & Structure (+$2,38,929). Chart to the right shows the BOQ-to-actual build-up by trade.
Q6. Which items have negative variance (came under BOQ)? What is the saving?
Metric | Value
Items under BOQ (qty variance < 0) | 19 | of total items | 72
Total saving USD (absolute) | 237902.17 | Avg saving per item | 12521.1668
Largest single saving — BOQ item | GI Piping | Value USD | 49998.13
Largest saving — project / trade | WT-DC-MUM-01 | MEP - Plumbing
ANSWER: 19 of 72 BOQ items came in under quantity, saving $2,37,902 in total ($12,521 per item on average). The single largest saving is GI Piping on WT-DC-MUM-01 (MEP - Plumbing) at $49,998. Note: the source sheet's Overrun_Impact column records only positive overruns, so savings here are computed as Actual Amount minus BOQ Amount.
PROBLEM 04 — Labour Productivity by Trade ¦ Source sheet: P04-LabourProd (80 daily records, 4 projects)
Q1. Which trade has the highest average productivity per man-hour?
Trade | Avg Productivity / man-hour | Records | Total Man-hours | Total Output Qty | Aggregate Output / Man-hour
Civil & Structure | 3.542 | 13 | 2548.7 | 7864 | 3.0855
MEP - Electrical | 3.0066 | 13 | 2840.9 | 8642.1 | 3.042
MEP - Plumbing | 2.2336 | 14 | 2724.4 | 5585.4 | 2.0501
MEP - HVAC | 2.8316 | 12 | 2686.5 | 7532.2 | 2.8037
Facade & Cladding | 3.103 | 13 | 2035.8 | 6205.9 | 3.0484
Interior Fit-out | 3.4296 | 15 | 2605.3 | 8735.9 | 3.3531
ANSWER: Civil & Structure has the highest average productivity at 3.54 units per man-hour; the lowest is MEP - Plumbing at 2.23. Note: output units differ by trade (cum, rmt, sqm), so compare within a trade rather than across.
Q2. Is there a productivity difference between projects in India vs Australia?
Country (by project location) | Projects | Records | Avg Productivity / man-hour | Total Man-hours | Total Output Qty
India | WT-DC-MUM-01, WT-ITP-BLR-04 | 43 | 3.2471 | 8139.7 | 24781
Australia | WT-OFF-SYD-02 | 16 | 3.0498 | 3201 | 10094.1
New Zealand | WT-HOS-AKL-03 | 21 | 2.5592 | 4100.9 | 9690.4
Difference India vs Australia | 0.19727 | % difference | 6.468%
ANSWER: India-based projects average 3.25 units/man-hour vs Australia at 3.05 — a gap of 0.20 (6.5%). India is more productive on this sample, but the two countries run different trade mixes and output units, so the gap is indicative only.
Q3. Summary statistics of productivity by trade — which has the most variance?
Trade | Minimum | Median | Maximum | Std Deviation | Coefficient of Variation
Civil & Structure | 0.32695 | 3.9618 | 7.0794 | 1.9965 | 56.37%
MEP - Electrical | 0.48567 | 2.325 | 6.6491 | 1.9614 | 65.24%
MEP - Plumbing | 0.27 | 1.7284 | 5.1779 | 1.588 | 71.09%
MEP - HVAC | 0.52113 | 2.9684 | 4.2199 | 1.1282 | 39.84%
Facade & Cladding | 0.23241 | 3.3028 | 5.7643 | 1.8013 | 58.05%
Interior Fit-out | 1.3351 | 3.4835 | 5.754 | 1.4766 | 43.06%
ANSWER: Civil & Structure shows the most variance (std dev 2.00, CV 56.4%); the most consistent is MEP - HVAC (std dev 1.13). High variance points to unstable crew mix or interrupted work fronts.
Q4. On which dates did productivity drop below the 25th percentile? What was the trade?
25th percentile of productivity | 1.5049 | Records below P25 | 20 | Total records | 80
Rank (lowest first) | Date | Trade | Project_ID | Productivity / man-hour | Workers
1 | 2025-01-08 | Facade & Cladding | WT-OFF-SYD-02 | 0.23241 | 15
2 | 2025-01-21 | MEP - Plumbing | WT-DC-MUM-01 | 0.27 | 25
3 | 2025-05-09 | Civil & Structure | WT-HOS-AKL-03 | 0.32695 | 30
4 | 2025-04-01 | MEP - Electrical | WT-DC-MUM-01 | 0.48567 | 34
5 | 2025-03-21 | MEP - HVAC | WT-HOS-AKL-03 | 0.52113 | 26
6 | 2025-05-16 | MEP - Plumbing | WT-HOS-AKL-03 | 0.69755 | 37
7 | 2025-01-17 | Facade & Cladding | WT-ITP-BLR-04 | 0.78101 | 24
8 | 2025-01-08 | MEP - Plumbing | WT-DC-MUM-01 | 0.81688 | 30
9 | 2025-02-27 | MEP - Plumbing | WT-DC-MUM-01 | 0.99322 | 12
10 | 2025-04-17 | MEP - Plumbing | WT-ITP-BLR-04 | 1.0365 | 20
ANSWER: The 25th percentile is 1.50 units/man-hour and 20 of 80 days fall below it. The 10 worst days are listed above; the single lowest was 2025-01-08 (Facade & Cladding on WT-OFF-SYD-02) at 0.23.
Q5. Optimal crew size (workers count) that maximises productivity for Civil & Structure
Crew size band | Records | Avg Productivity / man-hour | Avg Output Qty | Total Man-hours | Avg Workers
Small crew (up to 10 workers) | 0 | - | - | 0 | -
Medium crew (11 to 15) | 5 | 4.164 | 407.84 | 498.5 | 13
Large crew (16 to 20) | 1 | 2.6779 | 412.4 | 154 | 20
Very large crew (21+) | 7 | 3.2211 | 773.2 | 1896.2 | 32.1429
ANSWER: For Civil & Structure the best-performing crew band is Medium crew (11 to 15) at 4.16 units/man-hour (avg crew 13.0 workers) versus 2.68 for the weakest band.
Q6. Total man-hours consumed per project, ranked
Rank | Project_ID | Total Man-hours | Records | Avg Productivity / man-hour | Total Output Qty
1 | WT-DC-MUM-01 | 4631.1 | 24 | 3.1874 | 13574.9
2 | WT-HOS-AKL-03 | 4100.9 | 21 | 2.5592 | 9690.4
3 | WT-ITP-BLR-04 | 3508.6 | 19 | 3.3225 | 11206.1
4 | WT-OFF-SYD-02 | 3201 | 16 | 3.0498 | 10094.1
ANSWER: WT-DC-MUM-01 consumes the most labour at 4,631 man-hours, then WT-HOS-AKL-03 (4,101), WT-ITP-BLR-04 (3,509) and WT-OFF-SYD-02 (3,201). Total across the four projects: 15,442 man-hours.
WT-DC-MUM-01 | 4631.1 | helper — man-hours by project
WT-ITP-BLR-04 | 3508.6 | helper — man-hours by project
WT-OFF-SYD-02 | 3201 | helper — man-hours by project
WT-HOS-AKL-03 | 4100.9 | helper — man-hours by project
PROBLEM 05 — Tender Bid Comparison ¦ Source sheet: P05-TenderBid (40 bids, 5 packages, 13 contractors)
Q1. For each package, which contractor offers the lowest bid? Is the lowest bid always the best choice?
Tender Package | Lowest Bidder | Lowest Bid USD | Highest-Scored Bidder | Weighted Score | Bid of Highest-Scored USD | Cost of choosing quality USD | Bids Received | Weighted Score of Lowest Bidder
Structural Works | Contractor-D | 3366658 | Contractor-D | 80.4271 | 4226208 | 859550 | 8 | 73.4765
MEP Package | Contractor-O | 1360585 | Contractor-N | 65.2877 | 1664277 | 303692 | 8 | 61.2829
Facade & Glazing | Contractor-M | 2916771 | Contractor-I | 76.7682 | 3339940 | 423169 | 8 | 72.2569
Interior Fit-out | Contractor-M | 1631225 | Contractor-M | 91.2862 | 1631225 | 0 | 8 | 91.2862
Landscaping | Contractor-H | 855300 | Contractor-H | 81.6356 | 855300 | 0 | 8 | 81.6356
ANSWER: The lowest bidder is listed in column B for each of the 5 packages. No — lowest is not always best: on 2 of 5 packages the highest-scored bidder is a different contractor, and buying the best-scored bid instead of the cheapest costs $15,86,411 more in total. Ultra-low bids in this set also carry weak safety ratings and higher defect rates (see Q4).
Q2. Weighted scoring model — 40% Price, 20% Time, 15% Experience, 15% Safety, 10% Defects (scores normalised within each package)
Scoring weights (editable inputs) | Price | Time | Experience | Safety | Defects | Total
Weight | 40% | 20% | 15% | 15% | 10% | 100%
Tender Package | Contractor | Bid Amount USD | Completion Days | Price Score | Time Score | Experience Score | Safety Score | Defect Score | Weighted Score (0-100) | Rank in Package
Structural Works | Contractor-K | 6124192 | 306 | 0.54973 | 0.46078 | 0.72 | 0.75556 | 0.44681 | 57.8063 | 6
Structural Works | Contractor-D | 3366658 | 338 | 1 | 0.41716 | 0.32 | 0.68889 | 1 | 73.4765 | 2
Structural Works | Contractor-N | 7111231 | 141 | 0.47343 | 1 | 0.72 | 0.97778 | 0.20792 | 66.483 | 4
Structural Works | Contractor-A | 6052664 | 262 | 0.55623 | 0.53817 | 0.84 | 0.62222 | 0.4375 | 59.3208 | 5
Structural Works | Contractor-N | 6312010 | 174 | 0.53337 | 0.81034 | 1 | 0.8 | 0.40385 | 68.5803 | 3
Structural Works | Contractor-D | 4226208 | 235 | 0.79661 | 0.6 | 1 | 1 | 0.65625 | 80.4271 | 1
Structural Works | Contractor-M | 7079774 | 330 | 0.47553 | 0.42727 | 0.32 | 0.75556 | 0.18421 | 45.5422 | 8
Structural Works | Contractor-H | 6954518 | 234 | 0.4841 | 0.60256 | 0.56 | 0.84444 | 0.39623 | 56.4441 | 7
MEP Package | Contractor-D | 7221449 | 160 | 0.18841 | 0.64375 | 0.52632 | 0.53061 | 0.26667 | 38.9319 | 7
MEP Package | Contractor-O | 1360585 | 354 | 1 | 0.29096 | 0.26316 | 0.65306 | 0.17204 | 61.2829 | 2
MEP Package | Contractor-O | 4806314 | 165 | 0.28308 | 0.62424 | 0.78947 | 0.55102 | 0.14545 | 45.3701 | 6
MEP Package | Contractor-O | 3432532 | 103 | 0.39638 | 1 | 0.78947 | 0.53061 | 0.25397 | 58.1961 | 3
MEP Package | Contractor-B | 3644995 | 204 | 0.37327 | 0.5049 | 0.10526 | 0.67347 | 1 | 46.71 | 5
MEP Package | Contractor-F | 7138581 | 164 | 0.1906 | 0.62805 | 0.31579 | 0.53061 | 0.14414 | 34.3223 | 8
MEP Package | Contractor-N | 1664277 | 330 | 0.81752 | 0.31212 | 0.84211 | 0.81633 | 0.14679 | 65.2877 | 1
MEP Package | Contractor-D | 7504178 | 166 | 0.18131 | 0.62048 | 1 | 1 | 0.21333 | 51.7954 | 4
Facade & Glazing | Contractor-M | 2916771 | 211 | 1 | 0.5782 | 0.45833 | 0.6087 | 0.46875 | 72.2569 | 2
Facade & Glazing | Contractor-J | 4334546 | 122 | 0.67291 | 1 | 0.20833 | 1 | 0.24194 | 67.4609 | 3
Facade & Glazing | Contractor-K | 4823284 | 213 | 0.60473 | 0.57277 | 1 | 0.63043 | 0.27778 | 62.8788 | 6
Facade & Glazing | Contractor-D | 5287074 | 303 | 0.55168 | 0.40264 | 0.29167 | 0.91304 | 1 | 58.1906 | 7
Facade & Glazing | Contractor-B | 4912906 | 349 | 0.5937 | 0.34957 | 0.75 | 0.84783 | 0.3 | 57.7066 | 8
Facade & Glazing | Contractor-K | 3745395 | 281 | 0.77876 | 0.43416 | 0.41667 | 0.95652 | 0.32609 | 63.6924 | 5
Facade & Glazing | Contractor-D | 6648354 | 143 | 0.43872 | 0.85315 | 0.83333 | 0.93478 | 0.34884 | 64.6219 | 4
Facade & Glazing | Contractor-I | 3339940 | 179 | 0.8733 | 0.68156 | 0.95833 | 0.80435 | 0.17647 | 76.7682 | 1
Interior Fit-out | Contractor-M | 1631225 | 122 | 1 | 0.93443 | 1 | 0.97778 | 0.2931 | 91.2862 | 1
Interior Fit-out | Contractor-A | 7136305 | 192 | 0.22858 | 0.59375 | 0.125 | 0.73333 | 0.41463 | 38.0396 | 7
Interior Fit-out | Contractor-N | 5055271 | 332 | 0.32268 | 0.34337 | 0.41667 | 0.57778 | 0.21519 | 36.8432 | 8
Interior Fit-out | Contractor-N | 7050173 | 114 | 0.23137 | 1 | 0.91667 | 0.73333 | 0.89474 | 62.9523 | 3
Interior Fit-out | Contractor-O | 3855625 | 315 | 0.42308 | 0.3619 | 0.58333 | 0.73333 | 0.65385 | 50.4496 | 5
Interior Fit-out | Contractor-F | 7188160 | 355 | 0.22693 | 0.32113 | 0.41667 | 1 | 0.19101 | 38.6599 | 6
Interior Fit-out | Contractor-J | 7398298 | 182 | 0.22049 | 0.62637 | 0.79167 | 0.71111 | 1 | 53.8886 | 4
Interior Fit-out | Contractor-E | 3071073 | 318 | 0.53116 | 0.35849 | 0.875 | 0.95556 | 0.70833 | 62.9578 | 2
Landscaping | Contractor-H | 855300 | 270 | 1 | 0.39259 | 1 | 1 | 0.37838 | 81.6356 | 1
Landscaping | Contractor-A | 1129490 | 297 | 0.75724 | 0.3569 | 0.61905 | 0.76 | 0.15385 | 59.652 | 2
Landscaping | Contractor-A | 1697720 | 314 | 0.50379 | 0.33758 | 0.14286 | 0.56 | 0.4375 | 41.8212 | 7
Landscaping | Contractor-F | 3711615 | 106 | 0.23044 | 1 | 1 | 0.58 | 0.24561 | 55.3737 | 4
Landscaping | Contractor-H | 6901216 | 129 | 0.12393 | 0.82171 | 0.95238 | 0.56 | 0.29787 | 47.0559 | 5
Landscaping | Contractor-E | 2593894 | 148 | 0.32974 | 0.71622 | 0.095238 | 0.86 | 0.22581 | 44.1004 | 6
Landscaping | Contractor-I | 1487850 | 224 | 0.57486 | 0.47321 | 0.47619 | 0.86 | 0.46667 | 57.1681 | 3
Landscaping | Contractor-L | 4620485 | 192 | 0.18511 | 0.55208 | 0.2381 | 0.56 | 1 | 40.4175 | 8
ANSWER: Scores are normalised within each package (best value = 1.0) and weighted 40/20/15/15/10. The strongest bid overall is Contractor-M on Interior Fit-out with 91.3/100; the weakest is Contractor-F on MEP Package with 34.3. Column K gives the rank inside each package — award recommendations are the Rank 1 rows.
Q3. Which contractors appear in multiple packages? What is their average bid competitiveness?
Contractor | Bids Submitted | Packages Bid For | Avg Weighted Score | Avg Bid ÷ Lowest Bid in Package | Total Bid Value USD | Best Rank Achieved | Multi-package?
Contractor-A | 4 | 4 | 49.7084 | 2.3695 | 16016179 | 2 | Yes — 4 bids
Contractor-B | 2 | 2 | 52.2083 | 2.1817 | 8557901 | 5 | Yes — 2 bids
Contractor-D | 6 | 6 | 61.2406 | 2.8617 | 34253921 | 1 | Yes — 6 bids
Contractor-E | 2 | 2 | 53.5291 | 2.4577 | 5664967 | 2 | Yes — 2 bids
Contractor-F | 3 | 3 | 42.7853 | 4.6643 | 18038356 | 4 | Yes — 3 bids
Contractor-H | 3 | 3 | 61.7119 | 3.7115 | 14711034 | 1 | Yes — 3 bids
Contractor-I | 2 | 2 | 66.9681 | 1.4423 | 4827790 | 1 | Yes — 2 bids
Contractor-J | 2 | 2 | 60.6747 | 3.0108 | 11732844 | 3 | Yes — 2 bids
Contractor-K | 3 | 3 | 61.4592 | 1.5856 | 14692871 | 5 | Yes — 3 bids
Contractor-L | 1 | 1 | 40.4175 | 5.4022 | 4620485 | 8 | No
Contractor-M | 3 | 3 | 69.6951 | 1.3676 | 11627770 | 1 | Yes — 3 bids
Contractor-N | 5 | 5 | 60.0293 | 2.5263 | 27192962 | 1 | Yes — 5 bids
Contractor-O | 4 | 4 | 53.8247 | 2.3548 | 13455056 | 2 | Yes — 4 bids
ANSWER: 12 of 13 contractors bid for more than one package. On competitiveness (bid ÷ lowest bid in that package, 1.00 = cheapest), the sharpest pricing comes from Contractor-M at 1.37x and the most expensive is Contractor-L at 5.40x. Best average weighted score: Contractor-M (69.7/100).
Q4. Contractors with Safety Rating < 3.5 AND Defect Rate > 8% — HIGH RISK flag
Bids meeting both risk conditions | 4 | of total bids | 40 | Bids with Safety < 3.5 | 21 | Bids with Defect Rate > 8% | 9
# | Contractor | Tender Package | Bid Amount USD | Safety Rating | Past Defect Rate % | Weighted Score | Flag
1 | Contractor-M | Structural Works | 7079774 | 3.4 | 11.4 | 45.5422 | HIGH RISK — do not award
2 | Contractor-O | MEP Package | 1360585 | 3.2 | 9.3 | 61.2829 | HIGH RISK — do not award
3 | Contractor-O | MEP Package | 4806314 | 2.7 | 11 | 45.3701 | HIGH RISK — do not award
4 | Contractor-F | MEP Package | 7138581 | 2.6 | 11.1 | 34.3223 | HIGH RISK — do not award
5
6
7
8
ANSWER: 4 of 40 bids breach both thresholds (Safety < 3.5 and Defect Rate > 8%) and are listed above as HIGH RISK. Separately, 21 bids have a safety rating below 3.5 and 9 have a defect rate above 8%. Exclude the HIGH RISK rows from award even where they price competitively.
Q5. Total project cost — lowest bidder per package vs highest-scored bidder per package
Award strategy | Total Cost USD | Difference vs Lowest USD | Difference % | Avg Weighted Score | Packages
Award to lowest bidder | 10130539 | 0 | 0% | 75.9876 | 5
Award to highest-scored bidder | 11716950 | 1586411 | 15.66% | 79.081 | 5
ANSWER: Awarding every package to the cheapest bid totals $1,01,30,539 (avg score 76.0/100). Awarding to the highest-scored bid totals $1,17,16,950 (avg score 79.1) — $15,86,411 (15.7%) more. That premium buys better programme, safety and defect performance.
Q6. Bid Amount vs Completion Days — are cheaper bids slower? (scatter chart to the right)
Correlation (Bid Amount vs Completion Days) | -0.25371 | Avg bid of fastest 10 bids | 5063623.5 | Avg bid of slowest 10 bids | 3925204.9
ANSWER: r = -0.254 between bid amount and completion days — a weak negative relationship, i.e. cheaper bids do tend to quote longer programmes. The fastest 10 bids average $50,63,624 against $39,25,205 for the slowest 10.
PROBLEM 06 — Project Delay Root Cause Analysis ¦ Source sheet: P06-DelayRCA (60 delay events, 5 projects)
Q1. What is the most frequent delay cause category? (Pareto table + chart to the right)
Cause Category | Occurrences | Total Delay Days | Avg Delay Days | % of Occurrences | Sort key (helper)
Permit Delay | 8 | 175 | 21.875 | 13.33% | 7625
Client Decision Pending | 6 | 168 | 28 | 10% | 5624
Material Delay | 8 | 162 | 20.25 | 13.33% | 7623
Labour Shortage | 5 | 111 | 22.2 | 8.333% | 4622
Equipment Breakdown | 5 | 132 | 26.4 | 8.333% | 4621
RFI Response Delay | 11 | 266 | 24.1818 | 18.33% | 10620
Rework | 5 | 150 | 30 | 8.333% | 4619
Design Change | 4 | 62 | 15.5 | 6.667% | 3618
Subcontractor Default | 3 | 82 | 27.3333 | 5% | 2617
Weather | 5 | 159 | 31.8 | 8.333% | 4616
TOTAL | 60 | 1467 | 24.45 | 100%
Rank | Cause Category (sorted) | Occurrences | % of Occurrences | Cumulative % | Total Delay Days
1 | RFI Response Delay | 11 | 18.33% | 18.33% | 266
2 | Permit Delay | 8 | 13.33% | 31.67% | 175
3 | Material Delay | 8 | 13.33% | 45% | 162
4 | Client Decision Pending | 6 | 10% | 55% | 168
5 | Labour Shortage | 5 | 8.333% | 63.33% | 111
6 | Equipment Breakdown | 5 | 8.333% | 71.67% | 132
7 | Rework | 5 | 8.333% | 80% | 150
8 | Weather | 5 | 8.333% | 88.33% | 159
9 | Design Change | 4 | 6.667% | 95% | 62
10 | Subcontractor Default | 3 | 5% | 100% | 82
ANSWER: The most frequent delay cause is RFI Response Delay with 11 of 60 events (18.3%) and 266 delay days. The top 3 causes — RFI Response Delay, Permit Delay and Material Delay — account for 45.0% of all delay events (Pareto 80/20 point is reached at rank 7).
Q2. Which responsible party causes the most total delay days?
Responsible Party | Total Delay Days | Incidents | Avg Delay Days | % of Total Delay Days | Max Single Delay
Client | 121 | 5 | 24.2 | 8.248% | 44
Consultant | 339 | 15 | 22.6 | 23.11% | 44
Contractor | 145 | 6 | 24.1667 | 9.884% | 40
Subcontractor | 321 | 13 | 24.6923 | 21.88% | 45
Authority | 240 | 10 | 24 | 16.36% | 38
Force Majeure | 301 | 11 | 27.3636 | 20.52% | 43
TOTAL | 1467 | 60 | 24.45 | 100% | 45
ANSWER: Consultant is responsible for the most delay — 339 days (23.1% of the 1,467 total) across 15 incidents. Lowest contributor: Client with 121 days.
Q3. Project WT-DC-MUM-01 — cumulative delay and dominant cause
Cumulative delay days | 382 | Delay events | 12 | Avg days per event | 31.8333
Cause Category | Delay Days | Events | Avg Days | % of Project Delay
Permit Delay | 0 | 0 | 0 | 0
Client Decision Pending | 80 | 3 | 26.6667 | 0.20942
Material Delay | 105 | 3 | 35 | 0.27487
Labour Shortage | 0 | 0 | 0 | 0
Equipment Breakdown | 53 | 2 | 26.5 | 0.13874
RFI Response Delay | 75 | 2 | 37.5 | 0.19634
Rework | 32 | 1 | 32 | 0.08377
Design Change | 0 | 0 | 0 | 0
Subcontractor Default | 37 | 1 | 37 | 0.096859
Weather | 0 | 0 | 0 | 0
ANSWER: WT-DC-MUM-01 has accumulated 382 delay days across 12 events (avg 31.8 days each). The dominant cause is Material Delay with 105 days (27.5% of the project's delay).
Q4. Is there a seasonal pattern in delays? (by month of actual start; weather isolated)
Month | Weather Delay Days | Weather Events | All-Cause Delay Days | All Events | Weather share of month
Jan | 36 | 1 | 72 | 3 | 50%
Feb | 0 | 0 | 0 | 0 | 0%
Mar | 0 | 0 | 0 | 0 | 0%
Apr | 0 | 0 | 48 | 2 | 0%
May | 0 | 0 | 103 | 5 | 0%
Jun | 44 | 1 | 285 | 11 | 15.44%
Jul | 0 | 0 | 153 | 6 | 0%
Aug | 19 | 1 | 126 | 5 | 15.08%
Sep | 0 | 0 | 239 | 7 | 0%
Oct | 0 | 0 | 33 | 1 | 0%
Nov | 45 | 1 | 141 | 6 | 31.91%
Dec | 15 | 1 | 267 | 14 | 5.618%
ANSWER: Weather delays peak in Nov (45 days) and total 159 days, 10.8% of all delay days. Overall delay days peak in Jun. That concentration points to a genuine seasonal (monsoon/winter) effect worth programming for.
Q5. Which activity is most delay-prone across all projects?
Activity | Delay Events | Total Delay Days | Avg Delay Days | Max Single Delay | % of Total Delay Days
Foundation | 5 | 128 | 25.6 | 36 | 8.725%
Superstructure | 4 | 84 | 21 | 43 | 5.726%
MEP Rough-In | 6 | 201 | 33.5 | 45 | 13.7%
Facade Installation | 6 | 133 | 22.1667 | 38 | 9.066%
Interior Works | 9 | 182 | 20.2222 | 39 | 12.41%
External Works | 7 | 143 | 20.4286 | 44 | 9.748%
Landscape | 7 | 183 | 26.1429 | 44 | 12.47%
Testing & Commissioning | 11 | 291 | 26.4545 | 44 | 19.84%
Handover Prep | 5 | 122 | 24.4 | 37 | 8.316%
ANSWER: Testing & Commissioning is the most delay-prone activity with 291 delay days over 11 events (19.8% of all delay days). On a per-event basis the worst is MEP Rough-In at 33.5 days per event.
Q6. Estimated cost of delay per project at a daily burn rate of $15,000
Daily burn rate USD (input) | 15000
Project_ID | Total Delay Days | Cost of Delay USD | Delay Events | Avg Delay Days per Event | Dominant Cause
WT-DC-MUM-01 | 382 | 5730000 | 12 | 31.8333 | Material Delay
WT-OFF-SYD-02 | 277 | 4155000 | 14 | 19.7857 | Rework
WT-HOS-AKL-03 | 205 | 3075000 | 8 | 25.625 | Rework
WT-RES-MEL-05 | 246 | 3690000 | 12 | 20.5 | Weather
WT-MAL-DEL-06 | 357 | 5355000 | 14 | 25.5 | Weather
TOTAL | 1467 | 22005000 | 60 | 24.45
ANSWER: At $15,000/day the portfolio's 1,467 delay days cost roughly $2,20,05,000. The most exposed project is WT-DC-MUM-01 at $57,30,000 (382 days); the least is WT-HOS-AKL-03 at $30,75,000.
PROBLEM 07 — Monthly Cash Flow Tracking ¦ Source sheet: P07-CashFlow (48 project-months, 4 projects, Jan–Dec 2024)
Q1. Which project had negative net cash flow for the most months?
Project_ID | Months with Negative Net CF | Months Positive | Worst Month | Worst Net CF USD | Total Net CF USD
WT-DC-MUM-01 | 6 | 6 | 2024-02 | -868853 | 839758
WT-OFF-SYD-02 | 6 | 6 | 2024-01 | -1317584 | -1390187
WT-HOS-AKL-03 | 9 | 3 | 2024-12 | -992486 | -3867202
WT-ITP-BLR-04 | 8 | 4 | 2024-04 | -1331420 | -2898856
ANSWER: WT-HOS-AKL-03 ran negative in 9 of 12 months — the most in the portfolio. Its worst month was 2024-12 at -$9,92,486. Best cash discipline: WT-DC-MUM-01 with 6 negative months.
Q2. Cumulative cash position for each project at end of December 2024
Project_ID | Total Planned Inflow USD | Total Actual Inflow USD | Total Actual Outflow USD | Cumulative Cash Position Dec-24 USD | Inflow Shortfall vs Plan USD
WT-DC-MUM-01 | 14886232 | 11569465 | 10729707 | 839758 | -3316767
WT-OFF-SYD-02 | 15300774 | 11902885 | 13293072 | -1390187 | -3397889
WT-HOS-AKL-03 | 14162244 | 10528520 | 14395722 | -3867202 | -3633724
WT-ITP-BLR-04 | 11554097 | 9005567 | 11904423 | -2898856 | -2548530
TOTAL | 55903347 | 43006437 | 50322924 | -7316487 | -12896910
ANSWER: At 31-Dec-2024 the portfolio sits at -$73,16,487 cumulative cash. 3 of 4 projects are cash-negative. Best: WT-DC-MUM-01 at $8,39,758; worst: WT-HOS-AKL-03 at -$38,67,202. Collections came in $1,28,96,910 below plan.
Q3. Monthly net cash flow for all 4 projects (line chart to the right)
Month | WT-DC-MUM-01 | WT-OFF-SYD-02 | WT-HOS-AKL-03 | WT-ITP-BLR-04 | All Projects
2024-01 | -574274 | -1317584 | -595005 | 545759 | -1941104
2024-02 | -868853 | 836765 | -533153 | -3935 | -569176
2024-03 | -221231 | 586100 | 61735 | -186915 | 239689
2024-04 | 1074695 | -455351 | -572862 | -1331420 | -1284938
2024-05 | 389471 | 502180 | 579339 | -107332 | 1363658
2024-06 | 676310 | 767572 | -68464 | -1097039 | 278379
2024-07 | 147369 | -195047 | 102073 | 103162 | 157557
2024-08 | -30373 | -1056516 | -436762 | 596012 | -927639
2024-09 | -576106 | 226548 | -958914 | -810634 | -2119106
2024-10 | 701779 | 73497 | -345897 | -1038711 | -609332
2024-11 | 674262 | -824642 | -106806 | 447192 | 190006
2024-12 | -553291 | -533709 | -992486 | -14995 | -2094481
ANSWER: The chart to the right plots all four projects month by month. Portfolio net cash flow is negative in 7 of 12 months, with the deepest trough in 2024-09 (-$21,19,106) and the strongest month 2024-05 ($13,63,658).
Q4. Months where actual inflow fell below 70% of planned — collection risk
Collection risk threshold (input) | 70% | Project-months below threshold | 17 | of total project-months | 48
# | Month | Project_ID | Planned Inflow USD | Actual Inflow USD | Actual ÷ Planned
1 | 2024-01 | WT-DC-MUM-01 | 1554546 | 978713 | 62.96%
2 | 2024-04 | WT-DC-MUM-01 | 1956584 | 1345923 | 68.79%
3 | 2024-07 | WT-DC-MUM-01 | 1464127 | 957027 | 65.37%
4 | 2024-10 | WT-DC-MUM-01 | 1896205 | 1244523 | 65.63%
5 | 2024-01 | WT-OFF-SYD-02 | 605088 | 416147 | 68.77%
6 | 2024-03 | WT-OFF-SYD-02 | 1603531 | 1038595 | 64.77%
7 | 2024-04 | WT-OFF-SYD-02 | 720192 | 434574 | 60.34%
8 | 2024-08 | WT-OFF-SYD-02 | 843419 | 573405 | 67.99%
9 | 2024-03 | WT-HOS-AKL-03 | 1851236 | 1186522 | 64.09%
10 | 2024-04 | WT-HOS-AKL-03 | 958717 | 612669 | 63.91%
11 | 2024-06 | WT-HOS-AKL-03 | 1325457 | 894585 | 67.49%
12 | 2024-07 | WT-HOS-AKL-03 | 1126606 | 741441 | 65.81%
13 | 2024-08 | WT-HOS-AKL-03 | 1225146 | 790795 | 64.55%
14 | 2024-10 | WT-HOS-AKL-03 | 1382607 | 869477 | 62.89%
ANSWER: 17 of 48 project-months collected less than 70% of planned inflow (the first 14 are listed above). The single worst is WT-OFF-SYD-02 in 2024-04 at 60.3% of plan. Concentrate collection effort on the projects appearing most often in column C.
Q5. Total cash surplus / deficit across all projects
Measure | Amount USD
Total actual inflow | 43006437 | Total planned inflow | 55903347
Total actual outflow | 50322924 | Total planned outflow | 49699767
Net cash surplus / (deficit) | -7316487 | Projects in deficit | 3
ANSWER: Across all four projects WT collected $4,30,06,437 and spent $5,03,22,924, a net DEFICIT of $73,16,487 for 2024. 3 of 4 projects are individually in deficit.
Q6. Cash flow forecast accuracy — (Actual Inflow ÷ Planned Inflow) × 100
Project_ID | Planned Inflow USD | Actual Inflow USD | Forecast Accuracy % | Months below 70% | Best Month Accuracy %
WT-DC-MUM-01 | 14886232 | 11569465 | 77.72% | 4 | 105.7%
WT-OFF-SYD-02 | 15300774 | 11902885 | 77.79% | 4 | 98.49%
WT-HOS-AKL-03 | 14162244 | 10528520 | 74.34% | 6 | 97.87%
WT-ITP-BLR-04 | 11554097 | 9005567 | 77.94% | 3 | 106.7%
PORTFOLIO | 55903347 | 43006437 | 76.93% | 17 | 106.7%
ANSWER: Portfolio forecast accuracy is 76.9% — collections are running 23.1% below the cash-flow forecast. Most accurate project: WT-ITP-BLR-04 (77.9%); least accurate: WT-HOS-AKL-03 (74.3%). Anything below ~90% means the forecast, not just the client, needs fixing.
PROBLEM 08 — Change Order (VO) Impact Analysis ¦ Source sheet: P08-ChangeOrder (45 variation orders, 4 projects)
Q1. Total approved cost impact of all change orders per project
Project_ID | Approved VOs | Approved Cost Impact USD | All VOs | All VO Cost Impact USD | Approved Time Impact (days)
WT-DC-MUM-01 | 1 | 791101 | 8 | 2083172 | -2
WT-OFF-SYD-02 | 6 | 583674 | 14 | 4884716 | 44
WT-HOS-AKL-03 | 4 | 1919398 | 12 | 3608761 | 48
WT-RES-MEL-05 | 2 | 892260 | 11 | 3770085 | 44
TOTAL | 13 | 4186433 | 45 | 14346734 | 134
ANSWER: Approved change orders add $41,86,433 across the four projects (13 of 45 VOs approved). The largest approved exposure is WT-HOS-AKL-03 at $19,19,398; the smallest is WT-OFF-SYD-02 at $5,83,674.
Q2. Who initiates the most change orders — Client, Consultant, Contractor or Architect?
Initiated By | VOs Raised | % of All VOs | Total Cost Impact USD | Approved Cost Impact USD | Avg Cost per VO USD
Client | 11 | 24.44% | 5297017 | 1842542 | 481547
Consultant | 16 | 35.56% | 4771005 | 1046274 | 298187.8125
Contractor | 4 | 8.889% | 1151753 | 195489 | 287938.25
Architect | 14 | 31.11% | 3126959 | 1102128 | 223354.2143
TOTAL | 45 | 100% | 14346734 | 4186433 | 318816.3111
ANSWER: Consultant initiates the most change orders — 16 of 45 (35.6%). By value the biggest driver is Client at $52,97,017 of cost impact.
Q3. What % of change orders are still Pending or Under Review? What is the cost exposure?
Status | VOs | % of VOs | Cost Impact USD | % of Cost Impact | Avg Time Impact (days)
Approved | 13 | 28.89% | 4186433 | 29.18% | 10.3077
Pending | 7 | 15.56% | 1322846 | 9.221% | 11.8571
Under Review | 8 | 17.78% | 1974306 | 13.76% | 12.625
Rejected | 17 | 37.78% | 6863149 | 47.84% | 15.8235
TOTAL | 45 | 100% | 14346734 | 100% | 13.0444
Unresolved (Pending + Under Review) | 15 | 33.33% | 3297152 | 22.98%
ANSWER: 15 of 45 change orders (33.3%) are still Pending or Under Review, carrying $32,97,152 of unquantified cost exposure (23.0% of all VO value). That is the number to put in the risk register until these are determined.
Q4. Is there a correlation between cost impact and time impact of VOs?
Correlation (Cost Impact vs Time Impact) | 0.12417 | Avg cost impact USD | 318816.3111 | Avg time impact days | 13.0444
ANSWER: r = 0.124 — there is effectively no linear relationship between the money and the time a VO costs; expensive variations are not necessarily the ones that delay the programme. Average VO: $3,18,816 and 13.0 days.
Q5. Which project has the highest change order frequency per month?
Project_ID | VOs Raised | First VO Raised | Last VO Raised | Months Active | VOs per Month
WT-DC-MUM-01 | 8 | 2024-04 | 2025-01 | 10 | 0.8
WT-OFF-SYD-02 | 14 | 2024-01 | 2024-12 | 12 | 1.1667
WT-HOS-AKL-03 | 12 | 2024-01 | 2024-10 | 10 | 1.2
WT-RES-MEL-05 | 11 | 2024-01 | 2025-01 | 13 | 0.84615
ANSWER: WT-HOS-AKL-03 has the highest change-order frequency at 1.20 VOs per active month (12 VOs over 10 months). Lowest churn: WT-DC-MUM-01 at 0.80 per month.
Q6. Approved vs Pending vs Under Review vs Rejected VO cost per project (stacked bar chart to the right)
Project_ID | Approved USD | Pending USD | Under Review USD | Rejected USD | Total USD
WT-DC-MUM-01 | 791101 | 758642 | 675467 | -142038 | 2083172
WT-OFF-SYD-02 | 583674 | 0 | 577493 | 3723549 | 4884716
WT-HOS-AKL-03 | 1919398 | 449749 | 158155 | 1081459 | 3608761
WT-RES-MEL-05 | 892260 | 114455 | 563191 | 2200179 | 3770085
TOTAL | 4186433 | 1322846 | 1974306 | 6863149 | 14346734
ANSWER: The stacked bar to the right splits VO value by status for each project. Portfolio-wide: $41,86,433 approved, $13,22,846 pending, $19,74,306 under review and $68,63,149 rejected, on a total VO book of $1,43,46,734.
PROBLEM 09 — Subcontractor Performance Scorecard ¦ Source sheet: P09-SubconScore (30 scorecards, 13 subcontractors, 3 projects)
Q1. Rank all subcontractors by weighted score — top 3 and bottom 3
Rank | Subcontractor | Avg Weighted Score | Scorecards | Avg Quality Score | Total Defects |  | helper — avg weighted score by subcontractor
1 | Contractor-C | 3.86 | 1 | 4 | 13 |  | Contractor-A | 3.24
2 | Contractor-M | 3.7975 | 2 | 3.15 | 32 |  | Contractor-B | 3.645
3 | Contractor-B | 3.645 | 2 | 4.25 | 37 |  | Contractor-C | 3.86
4 | Contractor-H | 3.605 | 1 | 3.2 | 9 |  | Contractor-D | 3.47
5 | Contractor-F | 3.5075 | 2 | 3.7 | 23 |  | Contractor-E | 3.2475
6 | Contractor-I | 3.4717 | 3 | 3.9333 | 53 |  | Contractor-F | 3.5075
7 | Contractor-D | 3.47 | 1 | 3.7 | 20 |  | Contractor-G | 3.395
8 | Contractor-G | 3.395 | 5 | 2.94 | 71 |  | Contractor-H | 3.605
9 | Contractor-J | 3.355 | 5 | 3.32 | 50 |  | Contractor-I | 3.4717
10 | Contractor-L | 3.3067 | 3 | 3.1667 | 39 |  | Contractor-J | 3.355
11 | Contractor-E | 3.2475 | 2 | 3.15 | 36 |  | Contractor-L | 3.3067
12 | Contractor-A | 3.24 | 1 | 2.6 | 15 |  | Contractor-M | 3.7975
13 | Contractor-N | 3.1475 | 2 | 3 | 27 |  | Contractor-N | 3.1475
ANSWER: Top 3 — Contractor-C (3.86), Contractor-M (3.80) and Contractor-B (3.65). Bottom 3 — Contractor-N (3.15), Contractor-A (3.24) and Contractor-E (3.25). Portfolio average weighted score: 3.43.
Q2. Which trade has the lowest average quality score?
Trade | Avg Quality Score | Scorecards | Avg Weighted Score | Avg Safety Score | Total Defects
Civil & Structure | 2.45 | 2 | 3.3875 | 4 | 48
MEP - Electrical | 3.5 | 4 | 3.5125 | 3.675 | 66
MEP - Plumbing | 3.275 | 4 | 3.57 | 3.975 | 53
MEP - HVAC | 3.6 | 2 | 3.3275 | 2.6 | 22
Facade & Cladding | 2.65 | 2 | 3.35 | 3.65 | 32
Interior Fit-out | 3.875 | 4 | 3.695 | 3.7 | 61
Fire Safety | 2.9 | 3 | 3.2233 | 3.4667 | 24
Elevator Installation | 3.7 | 5 | 3.266 | 3.24 | 57
IT & Low Current | 3.6 | 2 | 3.3525 | 2.5 | 33
Landscaping | 3.1 | 2 | 3.5025 | 3 | 29
ANSWER: Civil & Structure has the lowest average quality score at 2.45 (vs the best, Interior Fit-out, at 3.88). Quality on that trade also carries 48 recorded defects.
Q3. Is there a negative correlation between defect count and quality score?
Correlation (Defects vs Quality Score) | -0.086848 | Correlation (Defects vs Weighted Score) | 0.083362 | Avg defects per scorecard | 14.1667
ANSWER: r = -0.087 between defect count and quality score — essentially no relationship, which suggests the quality score is not being driven by recorded defects and the scoring may need review. Defects vs overall weighted score: r = 0.083.
Q4. Five-dimension profile of the top-performing subcontractor (radar chart to the right)
Top performer | Contractor-C | Avg weighted score | 3.86 | Scorecards | 1
Dimension | Score (out of 5)
Quality | 4
Time | 3.2
Safety | 4.2
Cost | 4.6
Communication | 3.3
ANSWER: The top performer is Contractor-C with an average weighted score of 3.86. Its strongest dimension is Cost (4.60) and its weakest is Time (3.20) — see the radar chart to the right.
Q5. Which subcontractors should be blacklisted? (weighted score < 3.0 AND defects > 15)
Scorecards meeting both criteria | 2 | Scorecards with score < 3.0 | 4 | Scorecards with defects > 15 | 13
# | Subcontractor | Trade | Project_ID | Weighted Score | Defect Count
1 | Contractor-G | Facade & Cladding | WT-OFF-SYD-02 | 2.805 | 22
2 | Contractor-N | Elevator Installation | WT-DC-MUM-01 | 2.99 | 20
3
4
5
6
ANSWER: 2 scorecard(s) breach both blacklist criteria and are listed above. Separately 4 score below 3.0 and 13 carry more than 15 defects.
Q6. Subcontractor performance across the 3 projects — is any project a consistent outlier?
Project_ID | Subcontractors Scored | Avg Weighted Score | Avg Quality | Avg Safety | Total Defects
WT-DC-MUM-01 | 10 | 3.3905 | 3.54 | 3.14 | 123
WT-OFF-SYD-02 | 10 | 3.4735 | 3.08 | 3.51 | 130
WT-HOS-AKL-03 | 10 | 3.431 | 3.44 | 3.7 | 172
PORTFOLIO | 30 | 3.4317 | 3.3533 | 3.45 | 425
ANSWER: WT-DC-MUM-01 is the weakest project for subcontractor performance (avg weighted score 3.39 vs portfolio 3.43), while WT-OFF-SYD-02 is the strongest at 3.47. The spread is 0.08 points, so no project is a consistent outlier — performance differences are marginal.
PROBLEM 10 — Construction Cost Benchmarking ¦ Source sheet: P10-Benchmark (40 completed projects, 3 countries, 2022–2025)
Q1. Average cost per sqm by country (bar chart to the right)
Country | Avg Cost per sqm USD | Projects | Total GFA sqm | Total Cost USD | Blended Cost per sqm USD
Australia | 3677.1111 | 18 | 1240702 | 4775441848 | 3848.9838
India | 670.4 | 15 | 993039 | 695290875 | 700.1647
New Zealand | 2993 | 7 | 596049 | 1809186062 | 3035.2975
GLOBAL | 2429.875 | 40 | 2829790 | 7279918785 | 2572.6004
ANSWER: Australia is the most expensive market at $3,677/sqm, India the cheapest at $670/sqm — a 448.5% premium. Global average: $2,430/sqm.
Q2. Which project type has the highest and lowest cost per sqm globally?
Project Type | Avg Cost per sqm USD | Projects | Min Cost/sqm | Max Cost/sqm | Total Cost USD
Data Centre | 1731.7778 | 9 | 407 | 4728 | 649785313
Commercial Office | 3299.75 | 4 | 2356 | 4574 | 1088349704
Residential Tower | 2812.5 | 4 | 816 | 3622 | 635255972
Hospital | 2278 | 6 | 471 | 4677 | 1144180217
Hotel | 3859 | 3 | 1998 | 4797 | 1342280112
IT Park | 2933.6667 | 3 | 878 | 4598 | 1067677998
Industrial Warehouse | 1813.3333 | 3 | 400 | 4197 | 189149393
Metro Station | 2381 | 1 | 2381 | 2381 | 13447888
Shopping Mall | 1902.75 | 4 | 602 | 3567 | 572618609
University Campus | 2560.6667 | 3 | 440 | 4241 | 577173579
ANSWER: Highest cost per sqm globally is Hotel at $3,859/sqm; lowest is Data Centre at $1,732/sqm — a spread of $2,127/sqm (2.2x).
Q3. Has cost per sqm increased year-over-year? Trend by country
Year | Australia | India | New Zealand | Global Avg Cost/sqm | Projects
2022 | 3476.6667 | 417.3333 | 3119 | 2415.8 | 10
2023 | 4303 | 628.3333 | - | 2925 | 8
2024 | 3099 | 807 | - | 2444.1429 | 7
2025 | 3749.6 | 757.8571 | 2825 | 2168.5333 | 15
Change 2022 → 2025 | 7.85% | 81.6% | -9.426% | -10.24%
ANSWER: Global average cost per sqm moved from $2,416 in 2022 to $2,169 in 2025, -10.2% over the period. By country: Australia 7.9%, India 81.6%, New Zealand -9.4%. Costs are flat or falling on this sample, but yearly samples are small (see column F).
Q4. Benchmark table — Project Type × Country, average cost per sqm (USD)
Project Type | Australia | India | New Zealand | Global Avg | Projects
Data Centre | 3687.5 | 614.4 | 2569.5 | 1731.7778 | 9
Commercial Office | 3299.75 |  |  | 3299.75 | 4
Residential Tower | 3476 | 816 | 3479 | 2812.5 | 4
Hospital | 4677 | 711.6667 | 3428 | 2278 | 6
Hotel | 4789.5 |  | 1998 | 3859 | 3
IT Park | 3961.5 | 878 |  | 2933.6667 | 3
Industrial Warehouse | 4197 | 621.5 |  | 1813.3333 | 3
Metro Station | 2381 |  |  | 2381 | 1
Shopping Mall | 3069.5 | 736 |  | 1902.75 | 4
University Campus | 3621 | 440 |  | 2560.6667 | 3
Country Average | 3677.1111 | 670.4 | 2993 | 2429.875 | 40
ANSWER: The grid above is the benchmark table (blank = no project of that type in that country). The most expensive combination is $4,790/sqm and the cheapest is $440/sqm. Use the relevant cell as the rate base when pricing a new pursuit, then adjust for year (Q3) and specification.
Q5. Outliers — projects where cost/sqm is more than 1.5× the average for that type in that country
Outlier threshold (input) | 1.5 | Outliers found | 0 | Projects tested | 40 | [5 empty] | Project_ID | Type-Country key | Type-Country Avg | Ratio
# | Project_ID | Project Type | Country | Cost per sqm USD | Type-Country Avg USD | Ratio to Benchmark |  |  |  |  | WT-BM-100 | Hospital ¦ Australia | 4677 | 1
1 | [10 empty] | WT-BM-101 | Commercial Office ¦ Australia | 3299.75 | 0.71399
2 | [10 empty] | WT-BM-102 | Hospital ¦ India | 711.6667 | 1.1803
3 | [10 empty] | WT-BM-103 | Residential Tower ¦ India | 816 | 1
4 | [10 empty] | WT-BM-104 | IT Park ¦ Australia | 3961.5 | 0.83933
5 | [10 empty] | WT-BM-105 | Hotel ¦ Australia | 4789.5 | 0.99843
6 | [10 empty] | WT-BM-106 | Industrial Warehouse ¦ India | 621.5 | 1.3564
ANSWER: No project exceeds 1.5x the average cost/sqm for its type and country — cost performance is consistent across the benchmark set. The highest ratio recorded is 1.39x. | [10 empty] | WT-BM-107 | Hospital ¦ India | 711.6667 | 1.1578
[11 empty] | WT-BM-108 | Residential Tower ¦ New Zealand | 3479 | 0.9589
Q6. Budget estimate for a 50,000 sqm Data Centre in Mumbai | [10 empty] | WT-BM-109 | Data Centre ¦ India | 614.4 | 1.0791
GFA required (sqm) — input | 50000 | Project type — input | Data Centre | Country — input | India | [5 empty] | WT-BM-110 | Metro Station ¦ Australia | 2381 | 1
Benchmark — Data Centre in India (avg $/sqm) | 614.4 | Projects in benchmark | 5 | Global Data Centre avg $/sqm | 1731.7778 | [5 empty] | WT-BM-111 | Data Centre ¦ New Zealand | 2569.5 | 1.0379
Low case (min $/sqm) | 407 | High case (max $/sqm) | 798 | India cost/sqm change 2022→2025 | 81.6% | [5 empty] | WT-BM-112 | University Campus ¦ Australia | 3621 | 1.1712
Budget — base case USD | 30720000 | Budget — low case USD | 20350000 | Budget — high case USD | 39900000 | [5 empty] | WT-BM-113 | Hotel ¦ New Zealand | 1998 | 1
ANSWER: Indian Data Centre benchmarks average $614/sqm across 5 project(s), so a 50,000 sqm data centre in Mumbai should be budgeted at roughly $3,07,20,000, with a range of $2,03,50,000 (low) to $3,99,00,000 (high). Add escalation — Indian cost/sqm has moved 81.6% between 2022 and 2025 — plus site-specific loadings for power, cooling and redundancy. | [10 empty] | WT-BM-114 | Data Centre ¦ Australia | 3687.5 | 0.71783
[11 empty] | WT-BM-115 | Commercial Office ¦ Australia | 3299.75 | 0.76976
PROBLEM 12 — Earned Value Management (EVM) ¦ Source sheet: P12-EVM (36 monthly periods, BAC $25m) | [10 empty] | WT-BM-116 | Residential Tower ¦ Australia | 3476 | 1
Q1. In which month does the project first show a negative Schedule Variance (SV)? | [10 empty] | WT-BM-117 | Shopping Mall ¦ India | 736 | 0.81793
First month with negative SV | Month 1 | SV in that month | -130878 | Months with negative SV | 31 | [5 empty] | WT-BM-118 | Industrial Warehouse ¦ India | 621.5 | 0.6436
SPI in that month | 0.81669 | Worst SV (USD) | -4941717 | Month of worst SV | Month 32 | [5 empty] | WT-BM-119 | Residential Tower ¦ New Zealand | 3479 | 1.0411
ANSWER: Schedule Variance first turns negative in Month 1 (SV = -$1,30,878, SPI 0.82). In total 31 of 36 months run a negative SV, and the deepest point is Month 32 at -$49,41,717. | [10 empty] | WT-BM-120 | Commercial Office ¦ Australia | 3299.75 | 1.1301
[11 empty] | WT-BM-121 | Data Centre ¦ India | 614.4 | 0.72428
Q2. What is the CPI trend? Is the project getting more or less cost-efficient over time? | [10 empty] | WT-BM-122 | Shopping Mall ¦ Australia | 3069.5 | 1.1621
CPI at Month 1 | 1.0423 | CPI at Month 36 | 0.89976 | Trend slope per month | -0.00044318 | [5 empty] | WT-BM-123 | Data Centre ¦ New Zealand | 2569.5 | 0.96205
Average CPI | 0.95392 | Minimum CPI | 0.84435 | Months with CPI < 1.00 | 25 | [5 empty] | WT-BM-124 | Shopping Mall ¦ India | 736 | 1.1821
ANSWER: CPI moves from 1.042 in Month 1 to 0.900 in Month 36, a trend of -0.0004 per month — the project is getting LESS cost-efficient over time. Average CPI is 0.954 and 25 of 36 months sit below 1.00, so cost performance is structurally over budget. | [10 empty] | WT-BM-125 | Hospital ¦ India | 711.6667 | 0.66183
[11 empty] | WT-BM-126 | Shopping Mall ¦ Australia | 3069.5 | 0.83792
Q3. Based on EAC at Month 36, what is the projected cost overrun? | [10 empty] | WT-BM-127 | Data Centre ¦ India | 614.4 | 1.2988
Budget at Completion (BAC) | 25000000 | EAC at Month 36 | 27785221.4894 | Variance at Completion (BAC - EAC) | -2785221.4894 | [5 empty] | WT-BM-128 | Hospital ¦ New Zealand | 3428 | 0.87806
Projected cost overrun USD | 2785221.4894 | Overrun % | 11.14% | ETC remaining at Month 36 | 6687111.4894 | [5 empty] | WT-BM-129 | Hospital ¦ New Zealand | 3428 | 1.1219
ANSWER: EAC at Month 36 is $2,77,85,221 against a BAC of $2,50,00,000 — a projected OVERRUN of $27,85,221 (11.1%). Variance at Completion is -$27,85,221. | [10 empty] | WT-BM-130 | IT Park ¦ India | 878 | 1
[11 empty] | WT-BM-131 | Hotel ¦ Australia | 4789.5 | 1.0016
Q4. PV, EV and AC — the classic S-curve (line chart to the right) | [10 empty] | WT-BM-132 | Data Centre ¦ India | 614.4 | 0.66243
Month | PV — Planned Value USD | EV — Earned Value USD | AC — Actual Cost USD | SPI | CPI | [5 empty] | WT-BM-133 | Commercial Office ¦ Australia | 3299.75 | 1.3862
Month 1 | 713955 | 583077 | 559427 | 0.81669 | 1.0423 | [5 empty] | WT-BM-134 | Industrial Warehouse ¦ Australia | 4197 | 1
Month 2 | 1375080 | 1314419 | 1552686 | 0.95589 | 0.84655 | [5 empty] | WT-BM-135 | University Campus ¦ India | 440 | 1
Month 3 | 1996674 | 1848591 | 2172516 | 0.92584 | 0.8509 | [5 empty] | WT-BM-136 | IT Park ¦ Australia | 3961.5 | 1.1607
Month 4 | 2659718 | 2790438 | 2676937 | 1.0491 | 1.0424 | [5 empty] | WT-BM-137 | University Campus ¦ Australia | 3621 | 0.82878
Month 5 | 3522912 | 3497510 | 3244267 | 0.99279 | 1.0781 | [5 empty] | WT-BM-138 | Data Centre ¦ Australia | 3687.5 | 1.2822
Month 6 | 4311364 | 4279745 | 4009086 | 0.99267 | 1.0675 | [5 empty] | WT-BM-139 | Data Centre ¦ India | 614.4 | 1.2354
Month 7 | 5076108 | 3884193 | 4572625 | 0.76519 | 0.84944
Month 8 | 5518420 | 5338129 | 5598832 | 0.96733 | 0.95344
Month 9 | 6176705 | 5423142 | 5456673 | 0.878 | 0.99386
Month 10 | 7227989 | 6017261 | 6220665 | 0.83249 | 0.9673
Month 11 | 7370482 | 6885739 | 7471668 | 0.93423 | 0.92158
Month 12 | 8456065 | 7607646 | 8861641 | 0.89967 | 0.85849
Month 13 | 9008847 | 6993716 | 7097954 | 0.77632 | 0.98531
Month 14 | 9643700 | 9092039 | 10357281 | 0.9428 | 0.87784
Month 15 | 10155362 | 10645116 | 11316790 | 1.0482 | 0.94065
Month 16 | 10577255 | 9146675 | 10189498 | 0.86475 | 0.89766
Month 17 | 11781571 | 11598138 | 11635370 | 0.98443 | 0.9968
Month 18 | 12582063 | 10650481 | 10449513 | 0.84648 | 1.0192
Month 19 | 12569110 | 11678398 | 10613223 | 0.92913 | 1.1004
Month 20 | 14320401 | 11947221 | 13650848 | 0.83428 | 0.8752
Month 21 | 14542039 | 12465870 | 13403261 | 0.85723 | 0.93006
Month 22 | 14869497 | 11864184 | 11559952 | 0.79789 | 1.0263
Month 23 | 15558785 | 14160157 | 16105354 | 0.91011 | 0.87922
Month 24 | 17061766 | 16707135 | 19786940 | 0.97921 | 0.84435
Month 25 | 17492521 | 18276175 | 18578220 | 1.0448 | 0.98374
Month 26 | 18841344 | 19735602 | 18790535 | 1.0475 | 1.0503
Month 27 | 18256033 | 15433674 | 17307808 | 0.8454 | 0.89172
Month 28 | 19169856 | 17779442 | 19753597 | 0.92747 | 0.90006
Month 29 | 19840193 | 18258838 | 17211341 | 0.9203 | 1.0609
Month 30 | 21767434 | 21789398 | 24907904 | 1.001 | 0.8748
Month 31 | 22540417 | 20571227 | 19597529 | 0.91264 | 1.0497
Month 32 | 21195474 | 16253757 | 17562165 | 0.76685 | 0.9255
Month 33 | 21816501 | 19490789 | 19481437 | 0.8934 | 1.0005
Month 34 | 23880595 | 23687965 | 23740734 | 0.99193 | 0.99778
Month 35 | 23521603 | 23303495 | 27042893 | 0.99073 | 0.86172
Month 36 | 23898889 | 18983212 | 21098110 | 0.79431 | 0.89976
ANSWER: The S-curve to the right plots PV, EV and AC over 36 months. At Month 36: PV $2,38,98,889, EV $1,89,83,212, AC $2,10,98,110. EV sits -$49,15,677 against plan and AC is $21,14,898 above value earned — the classic signature of a project that is both behind schedule and over cost.
Q5. At what month does SPI drop below 0.90 (critical schedule delay)?
SPI threshold (input) | 0.9 | First month below threshold | Month 1 | Months below threshold | 15
Minimum SPI | 0.76519 | Month of minimum SPI | Month 7 | SPI at Month 36 | 0.79431
ANSWER: SPI first falls below 0.90 in Month 1, and is below 0.90 in 15 of the 36 months. The low point is 0.765 in Month 7, and the project closes Month 36 at SPI 0.794 — schedule recovery has not happened.
Q6. If management wants CPI ≥ 1.0 by Month 24, how much cost needs to be recovered?
Target CPI (input) | 1 | Target month (input) | 24
EV at Month 24 | 16707135 | AC at Month 24 | 19786940 | CPI at Month 24 | 0.84435
AC allowed for target CPI | 16707135 | Cost to be recovered USD | 3079805 | Recovery as % of AC | 15.56%
ANSWER: At Month 24, EV is $1,67,07,135 against AC of $1,97,86,940 (CPI 0.844). To reach CPI = 1.00 the actual cost would have to be no more than $1,67,07,135, so $30,79,805 (15.6% of spend to date) must be recovered — through value engineering, claim recovery or productivity gains — or the target must be reset.
PROBLEM 13 — Procurement Lead Time Analysis ¦ Source sheet: P13-LeadTime (50 purchase orders, 10 suppliers)
Q1. Average lead time (order date to actual delivery) by material
Material | Avg Lead Time (days) | POs | Min (days) | Max (days) | Std Dev (days)
Cement (OPC 53) | 38.6 | 5 | 24 | 52 | 13.1072
TMT Steel (Fe500) | 26.25 | 4 | 12 | 42 | 15.4569
Structural Steel | 41 | 6 | 18 | 77 | 20.1296
Aluminium Facade | 55 | 2 | 54 | 56 | 1.4142
Glass (DGU) | 36 | 2 | 18 | 54 | 25.4558
RMC M30 | 41 | 4 | 12 | 67 | 28.0595
Aggregate (20mm) | 26.3333 | 6 | 5 | 48 | 15.1877
Sand (River) | 34 | 1 | 34 | 34 | -
Bricks (AAC) | 37 | 3 | 32 | 45 | 7
Tiles (Vitrified) | 46 | 2 | 18 | 74 | 39.598
Plywood (Marine) | 21.6667 | 6 | 5 | 53 | 18.272
Waterproofing Membrane | 45.3333 | 3 | 35 | 59 | 12.3423
PVC Conduits | 42.3333 | 3 | 22 | 56 | 17.9536
MS Pipes | 49 | 2 | 34 | 64 | 21.2132
Copper Wiring | 69 | 1 | 69 | 69 | -
ANSWER: Average lead time across all 50 POs is 36.9 days. The longest is Copper Wiring at 69.0 days and the shortest is Plywood (Marine) at 21.7 days — plan procurement call-offs accordingly.
Q2. Which supplier has the worst on-time delivery rate?
Supplier | POs | On-time Deliveries | On-time % | Avg Delay vs Expected (days) | Avg Lead Time (days) |  | helper — sort key
Supplier-A | 3 | 1 | 33.33% | 4.6667 | 43 |  | -469.6667
Supplier-B | 1 | 0 | 0% | 12 | 35 |  | -804
Supplier-C | 5 | 2 | 40% | 7.8 | 36.4 |  | -405
Supplier-D | 5 | 2 | 40% | 2.2 | 46.2 |  | -406
Supplier-E | 7 | 2 | 28.57% | 3.1429 | 27 |  | -521.2857
Supplier-F | 8 | 3 | 37.5% | 4.5 | 35.25 |  | -433
Supplier-G | 6 | 1 | 16.67% | 7 | 43.3333 |  | -642.3333
Supplier-H | 1 | 0 | 0% | 17 | 64 |  | -810
Supplier-I | 7 | 1 | 14.29% | 10 | 27.7143 |  | -668.1429
Supplier-J | 7 | 3 | 42.86% | 4.4286 | 39.8571 |  | -383.4286
ANSWER: Supplier-B has the worst on-time delivery rate at 0.0% (0 of 1 POs on time, average 12.0 days late). Best performer: Supplier-J at 42.9%.
Q3. How many POs were delivered late? What is the average delay?
POs delivered late | 35 | % of all POs | 70% | Total POs | 50
Avg delay of late POs (days) | 9.5714 | Avg delay across all POs (days) | 5.88 | Worst single delay (days) | 20
ANSWER: 35 of 50 POs (70.0%) were delivered after the expected date. Late POs run 9.6 days late on average; across the whole book the average slippage is 5.9 days, with a worst case of 20 days.
Q4. Is there a country-level difference in procurement lead times?
Country | POs | Avg Lead Time (days) | Avg Delay (days) | On-time % | Std Dev of Lead Time
India | 21 | 35.8571 | 6.3333 | 19.05% | 20.5968
Australia | 13 | 36.8462 | 6.6923 | 38.46% | 18.6093
New Zealand | 16 | 38.3125 | 4.625 | 37.5% | 17.8689
ANSWER: Lead times range from 35.9 days in India to 38.3 days in New Zealand — a 2.5 day spread. On-time performance is best in Australia (38.5%) and worst in India (19.0%).
Q5. Which material has the longest and most unpredictable lead time?
Longest avg lead time — material | Copper Wiring | Days | 69 | POs | 1
Most unpredictable — material | Tiles (Vitrified) | Std Dev (days) | 39.598 | Range min–max (days) | 18 – 74
ANSWER: Copper Wiring has the longest average lead time at 69.0 days. Tiles (Vitrified) is the most unpredictable, with a standard deviation of 39.6 days and deliveries ranging 18 – 74 days. Carry buffer stock or dual-source those two.
Q6. Supplier reliability scorecard (ranked by on-time delivery %)
Rank | Supplier | On-time % | POs | Avg Delay (days) | Reliability Rating
1 | Supplier-J | 42.86% | 7 | 4.4286 | D - Replace
2 | Supplier-C | 40% | 5 | 7.8 | D - Replace
3 | Supplier-D | 40% | 5 | 2.2 | D - Replace
4 | Supplier-F | 37.5% | 8 | 4.5 | D - Replace
5 | Supplier-A | 33.33% | 3 | 4.6667 | D - Replace
6 | Supplier-E | 28.57% | 7 | 3.1429 | D - Replace
7 | Supplier-G | 16.67% | 6 | 7 | D - Replace
8 | Supplier-I | 14.29% | 7 | 10 | D - Replace
9 | Supplier-B | 0% | 1 | 12 | D - Replace
10 | Supplier-H | 0% | 1 | 17 | D - Replace
ANSWER: The scorecard above ranks all 10 suppliers. 0 rate A (90%+ on time), 0 rate B, 0 are watch-list and 10 should be replaced. Portfolio on-time performance is 30.0%.
PROBLEM 14 — Client Payment Aging Tracker ¦ Source sheet: P14-PaymentAging (40 invoices, 10 clients, 5 projects)
Q1. What is the total outstanding amount across all projects?
Total invoiced USD | 41713158 | Total paid USD | 29856300 | Total outstanding USD | 11856858 | [5 empty] | Invoice | Client | Project | Days Past Due | Outstanding USD | Overdue Amount USD | Interest USD | Days to Pay | Paid Late Amount USD
ANSWER: Total outstanding across all projects is $1,18,56,858 on $4,17,13,158 invoiced — a collection rate of 71.6%. 19 of 40 invoices carry a balance. | [10 empty] | INV-700 | GPT Group | WT-HOS-AKL-03 | 37 | 0 | 0 | 0 | 67 | 1697785
[11 empty] | INV-701 | Ascendas REIT | WT-ITP-BLR-04 | -3 | 109120 | 0 | 0 | 27 | 0
Q2. Which client has the highest overdue amount (paid after due date / still unpaid)? | [10 empty] | INV-702 | GPT Group | WT-HOS-AKL-03 | 13 | 0 | 0 | 0 | 43 | 1189156
Client | Invoices | Invoiced USD | Paid USD | Outstanding USD | Paid-Late Amount USD | [5 empty] | INV-703 | Goodman Group | WT-OFF-SYD-02 | 60 | 850225 | 850225 | 25506.75 |  | 0
GPT Group | 4 | 4067274 | 3341941 | 725333 | 3341941 | [5 empty] | INV-704 | Tata Realty | WT-DC-MUM-01 | 21 | 0 | 0 | 0 | 51 | 1667376
Ascendas REIT | 5 | 5877131 | 4731174 | 1145957 | 4622054 | [5 empty] | INV-705 | Tata Realty | WT-DC-MUM-01 | 243 | 1592083 | 1592083 | 193438.0845 |  | 0
Goodman Group | 4 | 3730694 | 2880469 | 850225 | 2880469 | [5 empty] | INV-706 | Tata Realty | WT-RES-MEL-05 | 29 | 0 | 0 | 0 | 59 | 866049
Tata Realty | 7 | 7778748 | 4865987 | 2912761 | 4145611 | [5 empty] | INV-707 | Brookfield | WT-HOS-AKL-03 | 156 | 1577223 | 1577223 | 123023.394 |  | 0
Brookfield | 9 | 8558948 | 4423250 | 4135698 | 4423250 | [5 empty] | INV-708 | Dexus | WT-RES-MEL-05 | 28 | 0 | 0 | 0 | 58 | 581235
Dexus | 4 | 2554118 | 2364281 | 189837 | 2364281 | [5 empty] | INV-709 | Stockland | WT-OFF-SYD-02 | 17 | 0 | 0 | 0 | 47 | 1861221
Stockland | 2 | 3181997 | 3181997 | 0 | 1861221 | [5 empty] | INV-710 | Tata Realty | WT-DC-MUM-01 | -9 | 240126 | 0 | 0 | 21 | 0
Embassy Group | 1 | 1212913 | 606456 | 606457 | 0 | [5 empty] | INV-711 | Goodman Group | WT-OFF-SYD-02 | 21 | 0 | 0 | 0 | 51 | 300923
Mirvac | 2 | 2883728 | 2280472 | 603256 | 2280472 | [5 empty] | INV-712 | Ascendas REIT | WT-DC-MUM-01 | 50 | 0 | 0 | 0 | 80 | 1693066
Lendlease | 2 | 1867607 | 1180273 | 687334 | 1180273 | [5 empty] | INV-713 | Brookfield | WT-RES-MEL-05 | 288 | 1666478 | 1666478 | 239972.832 |  | 0
TOTAL | 40 | 41713158 | 29856300 | 11856858 | 27099572 | [5 empty] | INV-714 | Brookfield | WT-OFF-SYD-02 | 33 | 0 | 0 | 0 | 63 | 241682
ANSWER: Ascendas REIT has the largest value paid after the due date — $46,22,054. On money still unpaid, the biggest exposure is Brookfield at $41,35,698 outstanding. | [10 empty] | INV-715 | Ascendas REIT | WT-DC-MUM-01 | 58 | 700886 | 700886 | 20325.694 | 88 | 700885
[11 empty] | INV-716 | Brookfield | WT-DC-MUM-01 | 34 | 134489 | 134489 | 2286.313 | 64 | 403465
Q3. Aging bucket analysis of outstanding balances | [10 empty] | INV-717 | Tata Realty | WT-ITP-BLR-04 | 35 | 0 | 0 | 0 | 65 | 1495461
As-at date for aging (input) | 2025-05-23 | Invoices with a balance | 19 | Total outstanding USD | 11856858 | [5 empty] | INV-718 | Goodman Group | WT-OFF-SYD-02 | 46 | 0 | 0 | 0 | 76 | 1067752
Aging Bucket (days past due) | Invoices | Outstanding USD | % of Outstanding | Avg Days Past Due | [6 empty] | INV-719 | Goodman Group | WT-RES-MEL-05 | 14 | 0 | 0 | 0 | 44 | 1511794
0–30 days | 3 | 998469 | 9.159% | 16.3333 | [6 empty] | INV-720 | Brookfield | WT-RES-MEL-05 | 49 | 194777 | 194777 | 4772.0365 | 79 | 584328
31–60 days | 7 | 3071180 | 28.17% | 52.5714 | [6 empty] | INV-721 | Embassy Group | WT-HOS-AKL-03 | -2 | 606457 | 0 | 0 | 28 | 0
61–90 days | 0 | 0 | 0% | - | [6 empty] | INV-722 | Brookfield | WT-RES-MEL-05 | 59 | 167518 | 167518 | 4941.781 | 89 | 502552
90+ days | 6 | 6831506 | 62.67% | 186.8333 | [6 empty] | INV-723 | Mirvac | WT-HOS-AKL-03 | 54 | 0 | 0 | 0 | 84 | 1677217
TOTAL PAST DUE | 16 | 10901155 | 100% | 80.2105 | [6 empty] | INV-724 | Brookfield | WT-ITP-BLR-04 | 20 | 337420 | 337420 | 3374.2 | 50 | 1012257
ANSWER: Of $1,18,56,858 outstanding, $1,09,01,155 is past due and splits as: $9,98,469 (9.2%) 0–30 days, $30,71,180 (28.2%) 31–60 days, $0 (0.0%) 61–90 days and $68,31,506 (62.7%) 90+ days. The remaining $9,55,703 is not yet due. Average age of past-due debt: 80 days. | [10 empty] | INV-725 | Lendlease | WT-HOS-AKL-03 | 14 | 0 | 0 | 0 | 44 | 1180273
[11 empty] | INV-726 | Mirvac | WT-RES-MEL-05 | 26 | 603256 | 603256 | 7842.328 | 56 | 603255
Q4. Average days-to-pay by client (payment date minus invoice date) | [10 empty] | INV-727 | GPT Group | WT-HOS-AKL-03 | 150 | 725333 | 725333 | 54399.975 |  | 0
Client | Invoices Paid | Avg Days to Pay | Max Days to Pay | Avg Days vs Due Date | Invoices Unpaid | [5 empty] | INV-728 | Dexus | WT-DC-MUM-01 | 141 | 189837 | 189837 | 13383.5085 |  | 0
GPT Group | 3 | 53.6667 | 67 | 55.25 | 1 | [5 empty] | INV-729 | Brookfield | WT-OFF-SYD-02 | 3 | 57793 | 57793 | 86.6895 | 33 | 57792
Ascendas REIT | 5 | 71 | 88 | 41 | 0 | [5 empty] | INV-730 | Tata Realty | WT-ITP-BLR-04 | 39 | 0 | 0 | 0 | 69 | 116725
Goodman Group | 3 | 57 | 76 | 35.25 | 1 | [5 empty] | INV-731 | Dexus | WT-ITP-BLR-04 | 22 | 0 | 0 | 0 | 52 | 1520762
Tata Realty | 5 | 53 | 69 | 71.5714 | 2 | [5 empty] | INV-732 | Stockland | WT-DC-MUM-01 | -1 | 0 | 0 | 0 | 29 | 0
Brookfield | 7 | 64.4286 | 89 | 76.1111 | 2 | [5 empty] | INV-733 | Tata Realty | WT-DC-MUM-01 | 143 | 1080552 | 1080552 | 77259.468 |  | 0
Dexus | 3 | 53 | 58 | 52.5 | 1 | [5 empty] | INV-734 | Ascendas REIT | WT-ITP-BLR-04 | 43 | 0 | 0 | 0 | 73 | 1220252
Stockland | 2 | 38 | 47 | 8 | 0 | [5 empty] | INV-735 | Ascendas REIT | WT-HOS-AKL-03 | 57 | 335951 | 335951 | 9574.6035 | 87 | 1007851
Embassy Group | 1 | 28 | 28 | -2 | 0 | [5 empty] | INV-736 | Lendlease | WT-DC-MUM-01 | 51 | 687334 | 687334 | 17527.017 |  | 0
Mirvac | 2 | 70 | 84 | 40 | 0 | [5 empty] | INV-737 | Dexus | WT-OFF-SYD-02 | 19 | 0 | 0 | 0 | 49 | 262284
Lendlease | 1 | 44 | 44 | 32.5 | 1 | [5 empty] | INV-738 | GPT Group | WT-RES-MEL-05 | 21 | 0 | 0 | 0 | 51 | 455000
ANSWER: The slowest payer is Ascendas REIT at 71 days from invoice to payment; the fastest is Embassy Group at 28 days. Portfolio average: 58 days against payment terms of roughly 30 days. | [10 empty] | INV-739 | Brookfield | WT-RES-MEL-05 | 43 | 0 | 0 | 0 | 73 | 1621174
Q5. Which project has the worst collection rate (Paid ÷ Invoiced)?
Project_ID | Invoices | Invoiced USD | Paid USD | Collection Rate | Outstanding USD
WT-DC-MUM-01 | 10 | 11131251 | 6505944 | 58.45% | 4625307
WT-OFF-SYD-02 | 7 | 4699672 | 3791654 | 80.68% | 908018
WT-HOS-AKL-03 | 8 | 10603702 | 7358738 | 69.4% | 3244964
WT-ITP-BLR-04 | 6 | 5921117 | 5474577 | 92.46% | 446540
WT-RES-MEL-05 | 9 | 9357416 | 6725387 | 71.87% | 2632029
TOTAL | 40 | 41713158 | 29856300 | 71.58% | 11856858
ANSWER: WT-DC-MUM-01 has the worst collection rate at 58.4% ($46,25,307 outstanding); the best is WT-ITP-BLR-04 at 92.5%. Portfolio collection rate: 71.6%.
Q6. Interest receivable on overdue amounts at 1.5% per month
Monthly interest rate (input) | 1.5% | Overdue invoices | 16 | Total overdue amount USD | 10901155
Client | Overdue Amount USD | Avg Days Overdue | Interest Receivable USD
GPT Group | 725333 | 150 | 54399.975
Ascendas REIT | 1036837 | 57.5 | 29900.2975
Goodman Group | 850225 | 60 | 25506.75
Tata Realty | 2672635 | 193 | 270697.5525
Brookfield | 4135698 | 87 | 378457.246
Dexus | 189837 | 141 | 13383.5085
Stockland | 0 | - | 0
Embassy Group | 0 | - | 0
Mirvac | 603256 | 26 | 7842.328
Lendlease | 687334 | 51 | 17527.017
TOTAL | 10901155 | 96.125 | 797714.6745
ANSWER: At 1.5% per month, the $1,09,01,155 of overdue balances (average 96 days past due) carries $7,97,715 of interest receivable. The largest single claim is against Brookfield at $3,78,457. Aging is measured to 23-May-2025 (latest payment date in the data).
PROBLEM 15 — Multi-Project Portfolio Dashboard ¦ Source sheet: P15-Portfolio (25 projects, 3 countries)
Q1. How many projects are In Progress, On Hold, Completed and Planning? (pie chart to the right)
Status | Projects | % of Portfolio | Budget USD | Spent USD | Avg Completion %
In Progress | 4 | 16% | 142240052 | 109936604 | 75.5%
On Hold | 8 | 32% | 505848491 | 319243519 | 49%
Completed | 8 | 32% | 397754853 | 261592213 | 68.75%
Planning | 5 | 20% | 379882427 | 0 | 0%
TOTAL | 25 | 100% | 1425725823 | 690772336 | 49.76%
ANSWER: The portfolio splits 4 In Progress, 8 On Hold, 8 Completed and 5 in Planning (25 projects total). On Hold is the largest group at 32.0% of projects. On-hold projects alone tie up $50,58,48,491 of budget.
Q2. Total portfolio budget and spend, and overall budget variance
Total portfolio budget USD | 1425725823 | Total spent USD | 690772336 | Budget variance USD (spent - budget) | -734953487
Variance % | -51.55% | Budget remaining USD | 734953487 | Average completion % | 49.76%
ANSWER: Portfolio budget is $1,42,57,25,823 and spend to date is $69,07,72,336 — 48.5% of budget drawn against 49.8% average completion, leaving $73,49,53,487 unspent. On the source sheet's own Budget_Variance column the portfolio is $3,61,50,438 adrift, and 12 of 25 projects show an adverse variance.
Q3. Red-zone projects — CPI < 0.90 AND SPI < 0.90
Red-zone projects | 3 | Projects with CPI < 0.90 | 11 | Projects with SPI < 0.90 | 9
# | Project_ID | Project Name | Country | SPI | CPI
1 | WT-2005 | IT Park Sydney | Australia | 0.78 | 0.86
2 | WT-2015 | Shopping Mall Canberra | Australia | 0.88 | 0.83
3 | WT-2024 | Hospital Bangalore | India | 0.78 | 0.89
4
5
6
7
8
ANSWER: 3 of 25 projects are in the red zone (both CPI and SPI below 0.90) and are listed above. Separately 11 projects have CPI below 0.90 and 9 have SPI below 0.90. These need recovery plans before any new work is taken on.
Q4. Bubble view — X = SPI, Y = CPI, bubble size = Budget (chart to the right)
SPI | CPI | Budget USD | Project_ID | Status | Risk Level
0.91 | 0.79 | 95528859 | WT-2000 | Completed | Medium
1 | 1.12 | 93252435 | WT-2001 | Completed | High
1.06 | 0.99 | 60343779 | WT-2002 | Completed | Medium
0.9 | 1.04 | 53319528 | WT-2003 | Completed | High
0.81 | 1.09 | 45512501 | WT-2004 | On Hold | Low
0.78 | 0.86 | 17655004 | WT-2005 | On Hold | Medium
1.16 | 1.04 | 17335296 | WT-2006 | Completed | High
1.11 | 0.79 | 97555887 | WT-2007 | Planning | High
1.16 | 0.88 | 15533057 | WT-2008 | Planning | Critical
1.02 | 1 | 92614538 | WT-2009 | On Hold | Low
0.86 | 1.03 | 47857940 | WT-2010 | In Progress | Medium
0.75 | 0.92 | 84877290 | WT-2011 | Planning | Critical
0.72 | 0.91 | 16079017 | WT-2012 | Completed | Low
0.77 | 0.97 | 98666595 | WT-2013 | Planning | Critical
0.96 | 0.85 | 80318641 | WT-2014 | On Hold | High
0.88 | 0.83 | 20103503 | WT-2015 | In Progress | High
1.1 | 1 | 51938140 | WT-2016 | On Hold | Critical
1.06 | 0.78 | 96987358 | WT-2017 | On Hold | Low
1.1 | 0.87 | 43612439 | WT-2018 | On Hold | Critical
0.96 | 0.85 | 77209870 | WT-2019 | On Hold | Critical
0.96 | 0.85 | 83249598 | WT-2020 | Planning | Low
0.7 | 0.91 | 12124981 | WT-2021 | Completed | High
1.19 | 0.95 | 44258091 | WT-2022 | In Progress | Low
0.93 | 1.12 | 30020518 | WT-2023 | In Progress | Low
0.78 | 0.89 | 49770958 | WT-2024 | Completed | High
Quadrant | Definition | Projects | % of Portfolio | Budget USD
Star | SPI ≥ 1 and CPI ≥ 1 | 4 | 16% | 255140409
On time, over cost | SPI ≥ 1 and CPI < 1 | 6 | 24% | 358290611
Late, on cost | SPI < 1 and CPI ≥ 1 | 4 | 16% | 176710487
Late and over cost | SPI < 1 and CPI < 1 | 11 | 44% | 635584316
TOTAL |  | 25 | 100% | 1425725823
ANSWER: The busiest quadrant is "Late and over cost" with 11 of 25 projects (44.0%) and $63,55,84,316 of budget. Only 4 projects are true stars (both indices at or above 1.00).
Q5. Average completion % by country
Country | Projects | Avg Completion % | Total Budget USD | Total Spent USD | Avg CPI
India | 12 | 41.33% | 677634383 | 269966826 | 0.90583
Australia | 10 | 62.7% | 496939339 | 336846853 | 0.956
New Zealand | 3 | 40.33% | 251152101 | 83958657 | 0.96667
PORTFOLIO | 25 | 49.76% | 1425725823 | 690772336 | 0.9332
ANSWER: Australia is furthest advanced at 62.7% average completion, while New Zealand trails at 40.3%. Portfolio average completion is 49.8%.
Q6. Traffic-light summary — Green (CPI≥1 and SPI≥1), Red (both < 0.9), Amber (everything else)
Category | Definition | Projects | % of Portfolio | Budget USD | Avg Completion %
GREEN | CPI ≥ 1.0 and SPI ≥ 1.0 | 4 | 16% | 255140409 | 72%
RED | CPI < 0.9 and SPI < 0.9 | 3 | 12% | 87529465 | 60.33%
AMBER | Either index below 1.0 but not red | 18 | 72% | 1083055949
TOTAL |  | 25 | 100% | 1425725823 | 49.76%
ANSWER: 4 projects are GREEN (16.0%), 18 AMBER (72.0%) and 3 RED (12.0%). Red projects carry $8,75,29,465 of budget — that is the portion of the portfolio needing intervention now.
Q7. Three-line executive summary for the board
1. Scale — WT is running 25 projects worth $1,42,57,25,823 across India, Australia and New Zealand, 49.8% complete on average, with $73,49,53,487 still to spend.
2. Performance — average CPI is 0.93 and average SPI 0.95; 4 projects are green, 18 amber and 3 red, with 48.5% of budget drawn against 49.8% completion.
3. Action — the 3 red-zone projects ($8,75,29,465 of budget) plus 8 on-hold projects ($50,58,48,491) are where recovery plans and cash are needed; everything else is tracking within tolerance.
ANSWER: The three lines above are the board summary — scale, performance and the action required.

## Q&A Chart Dashboard
WT PARTNERSHIP ¦ 86-QUESTION CHART DASHBOARD | [8 empty] | CHART DATA — every cell is a live formula link to 'Analysis report' (or the named source sheet). Do not delete; all 86 charts on this dashboard read from these tables.
H1 — P01 Q3 — top 5 absolute overruns
One chart per question for all 86 analysis questions listed on the 'Analysis Dashboard ' sheet. Every chart, question title and answer line is a live formula link to the 'Analysis report' sheet — no value is retyped. Chart source tables sit in columns BA:BE of this sheet. | [8 empty] | Project | Absolute overrun USD
[9 empty] | Residential Tower Per-29 | 24654239
CONTENTS — jump to row | [8 empty] | Residential Tower Hyd-33 | 21628203
P01 — row 13 | P02 — row 82 | P03 — row 129 |  | P04 — row 176 | P05 — row 223 |  | P06 — row 270 | P07 — row 317 | IT Park Syd-34 | 19739335
P08 — row 364 | P09 — row 411 | P10 — row 458 |  | P12 — row 505 | P13 — row 552 |  | P14 — row 599 | P15 — row 646 | University Campus Kol-35 | 19335358
[9 empty] | Industrial Warehouse Can-44 | 19116067
H2 — P01 Q4 — duration vs overrun (50 projects)
[9 empty] | Duration (months) | Cost overrun %
[9 empty] | 39 | 33.14%
PROBLEM 01 — Project Cost Overrun Analysis ¦ Source sheet: P01-CostOverrun (50 projects) | [8 empty] | 16 | 32.87%
[9 empty] | 40 | 33.57%
Q1. Which country has the highest average cost overrun percentage? |  |  | Q2. What is the total budget vs actual cost for each project type? Which type has the worst variance? |  |  | Q3. Top 5 projects with the highest absolute cost overrun (USD) |  |  | 47 | 34.81%
[9 empty] | 9 | 29.55%
ANSWER: New Zealand has the highest average cost overrun at 19.7%, vs India the lowest at 15.8%. |  |  | ANSWER: Worst variance = Residential Tower at 26.3% ($6,26,62,924 over budget). Best = Shopping Mall at 3.4%. Portfolio total: $2,15,23,99,053 budget vs $2,53,19,47,246 actual (17.6%). |  |  | ANSWER: Largest single overrun is Residential Tower Per-29 (WT-1028) at $2,46,54,239 (33.1%). The top 5 together account for $10,44,73,202 of overrun. |  |  | 40 | 27.64%
[9 empty] | 47 | 25.04%
[9 empty] | 38 | 25.48%
[9 empty] | 16 | 31.1%
[9 empty] | 15 | 19.36%
[9 empty] | 12 | 24.13%
[9 empty] | 9 | 28.71%
[9 empty] | 29 | 20.43%
[9 empty] | 6 | 18.57%
[9 empty] | 30 | 18.86%
[9 empty] | 41 | 16.16%
[9 empty] | 35 | 27.29%
[9 empty] | 21 | 13.06%
[9 empty] | 33 | 24.88%
[9 empty] | 32 | 26.38%
[9 empty] | 40 | 23.64%
[9 empty] | 13 | 14.54%
[9 empty] | 8 | 23.18%
[9 empty] | 10 | 13.51%
[9 empty] | 35 | 12.39%
Q4. Is there a correlation between project duration and cost overrun percentage? |  |  | Q5. Pivot — average overrun % by Country × Project Type |  |  | Q6. What percentage of projects came in under budget vs over budget? |  |  | 10 | 11.05%
[9 empty] | 42 | 23.93%
ANSWER: r = -0.156 — effectively no linear relationship; duration does not explain cost overrun in this portfolio. |  |  | ANSWER: Highest average overrun combination is Hospital in New Zealand at 29.9%. Portfolio average overrun is 16.6%. |  |  | ANSWER: 90.0% of projects (45 of 50) came in over budget and 10.0% (5) under budget. |  |  | 14 | 16.45%
[9 empty] | 21 | 16.37%
[9 empty] | 12 | 29.21%
[9 empty] | 13 | 25.23%
[9 empty] | 27 | 31.22%
[9 empty] | 28 | 21.36%
[9 empty] | 46 | 5.798%
[9 empty] | 19 | 6.115%
[9 empty] | 8 | 18.62%
[9 empty] | 37 | 6.139%
[9 empty] | 41 | -4.159%
[9 empty] | 14 | 3.773%
[9 empty] | 14 | 4.796%
[9 empty] | 23 | 3.38%
[9 empty] | 37 | 3.505%
[9 empty] | 46 | -4.712%
[9 empty] | 28 | 10.2%
[9 empty] | 44 | 4.306%
[9 empty] | 21 | 5.595%
[9 empty] | 24 | -1.848%
Q7. Which city has the most cost-efficient project delivery? | [8 empty] | 42 | -2.683%
[9 empty] | 37 | 1.652%
ANSWER: Gold Coast is the most cost-efficient city (avg overrun -3.0%), while Sydney is the least efficient (33.6%). Note: small samples per city. | [8 empty] | 40 | -2.976%
H3 — P02 Q1/Q5 — avg price change by material
[9 empty] | Material | Avg price change %
[9 empty] | Waterproofing Membrane | 2.52%
[9 empty] | Cement (OPC 53) | 11.86%
[9 empty] | Aluminium Facade | 11.7%
[9 empty] | Bricks (AAC) | 7.74%
[9 empty] | Tiles (Vitrified) | 8.361%
[9 empty] | PVC Conduits | 3.042%
[9 empty] | Sand (River) | 9.52%
[9 empty] | Structural Steel | 6.968%
[9 empty] | Aggregate (20mm) | 14.61%
[9 empty] | MS Pipes | 9.938%
[9 empty] | RMC M30 | 14.78%
[9 empty] | Glass (DGU) | 4.393%
[9 empty] | Copper Wiring | 1.925%
[9 empty] | Plywood (Marine) | 9.256%
[9 empty] | TMT Steel (Fe500) | 3.914%
H4 — P02 Q6 — TMT Steel observed + forecast
PROBLEM 02 — Material Price Fluctuation Tracker ¦ Source sheet: P02-MaterialPrice (90 records, 15 materials, 18 months) | [8 empty] | Month | TMT Steel USD/MT
[9 empty] | 2024-03 | 710.14
Q1. Which material has shown the highest average price increase over 18 months? |  |  | Q2. Monthly price trend for TMT Steel and Cement (line chart placed to the right) |  |  | Q3. Which country has the most volatile material pricing? (standard deviation) |  |  | 2025-01 | 607.52
[9 empty] | 2025-02 | 688.19
ANSWER: RMC M30 shows the highest average price increase at 14.8%; the lowest is Copper Wiring at 1.9%. |  |  | ANSWER: Both series trend upward overall but the dataset is sampled — only 4 of 18 months carry a TMT Steel price and 6 carry a Cement price (#N/A = no data that month). TMT Steel averages $675/MT (avg change 3.9%) and Cement $95/MT (avg change 11.9%). See the line chart to the right. |  |  | ANSWER: India has the most volatile material pricing (std dev of price change = 9.8% pts), the least volatile is New Zealand at 9.0%. |  |  | 2025-06 | 695.91
[9 empty] | Forecast · month 21 | 658.3326
H5 — P03 Q6 — savings on items under BOQ
[9 empty] | Project | Savings USD (items under BOQ)
[9 empty] | WT-DC-MUM-01 | -126377.68
[9 empty] | WT-OFF-SYD-02 | -51637.8
[9 empty] | WT-HOS-AKL-03 | -59886.69
H6 — P04 Q2 — productivity by country
[9 empty] | Country | Avg productivity / man-hour
[9 empty] | India | 3.2471
[9 empty] | Australia | 3.0498
[9 empty] | New Zealand | 2.5592
H7 — P04 Q4 — 10 worst productivity days
[9 empty] | Date · Trade | Productivity / man-hour
[9 empty] | 08-Jan-25 · Facade & Cladding | 0.23241
[9 empty] | 21-Jan-25 · MEP - Plumbing | 0.27
[9 empty] | 09-May-25 · Civil & Structure | 0.32695
Q4. Top 3 materials with price increase > 15% — flag as procurement risk |  |  | Q5. Average price change % by material across all months |  |  | Q6. Projected cost of 500 MT of TMT Steel next quarter (trend-based) |  |  | 01-Apr-25 · MEP - Electrical | 0.48567
[9 empty] | 21-Mar-25 · MEP - HVAC | 0.52113
ANSWER: No material's AVERAGE increase exceeds 15% (highest is RMC M30 at 14.8%), though 20 of 90 individual monthly records are above 15%. Treat the top 3 — RMC M30 (14.8%), Aggregate (20mm) (14.6%), Cement (OPC 53) (11.9%) — as procurement risk and forward-buy / lock rates. |  |  | ANSWER: The portfolio-wide average material price change is 7.5% (median 7.2%). 9 of 15 materials sit above that average — see column C of the Q1 table for the material-by-material figures. |  |  | ANSWER: Fitting a linear trend to the 4 observed TMT Steel price points gives a slope of -$1.90/MT per month. Projected price for next quarter (month index 21) is $658/MT, so 500 MT ≈ $3,29,166 (vs $3,47,955 at the latest observed price). Caveat: only 4 data points — treat as indicative. |  |  | 16-May-25 · MEP - Plumbing | 0.69755
[9 empty] | 17-Jan-25 · Facade & Cladding | 0.78101
[9 empty] | 08-Jan-25 · MEP - Plumbing | 0.81688
[9 empty] | 27-Feb-25 · MEP - Plumbing | 0.99322
[9 empty] | 17-Apr-25 · MEP - Plumbing | 1.0365
H8 — P04 Q5 — productivity by crew band
[9 empty] | Crew size band | Avg productivity / man-hour
[9 empty] | Small crew (up to 10 workers) | -
[9 empty] | Medium crew (11 to 15) | 4.164
[9 empty] | Large crew (16 to 20) | 2.6779
[9 empty] | Very large crew (21+) | 3.2211
H9 — P05 Q1 — lowest bid vs highest-scored bid
[9 empty] | Tender package | Lowest bid USD | Bid of highest-scored USD
[9 empty] | Structural Works | 3366658 | 4226208
[9 empty] | MEP Package | 1360585 | 1664277
[9 empty] | Facade & Glazing | 2916771 | 3339940
[9 empty] | Interior Fit-out | 1631225 | 1631225
[9 empty] | Landscaping | 855300 | 855300
PROBLEM 03 — BOQ Variance Analysis ¦ Source sheet: P03-BOQVariance (72 BOQ line items, 3 projects) | [8 empty] | H10 — P05 Q2 — best vs worst weighted score per package
[9 empty] | Tender package | Best weighted score | Worst weighted score
Q1. Which project has the highest total BOQ variance (in USD)? |  |  | Q2. Which trade consistently exceeds BOQ quantities across all 3 projects? |  |  | Q3. Top 5 BOQ items with the highest quantity variance % |  |  | Structural Works | 80.4271 | 45.5422
[9 empty] | MEP Package | 65.2877 | 34.3223
ANSWER: WT-OFF-SYD-02 has the highest total BOQ variance at $7,16,910 (12.6% over BOQ). All three projects combined are $15,90,589 (9.9%) above BOQ. |  |  | ANSWER: MEP - Electrical is the worst offender — average quantity variance of 11.1% and over BOQ in 3 of 3 projects. 4 of 5 trades exceed BOQ in all three projects. |  |  | ANSWER: The worst item is Plastering (Civil & Structure, WT-HOS-AKL-03) at 28.9% over BOQ, costing $1,51,508. The top 5 items alone add $3,92,614 of overrun. |  |  | Facade & Glazing | 76.7682 | 57.7066
[9 empty] | Interior Fit-out | 91.2862 | 36.8432
[9 empty] | Landscaping | 81.6356 | 40.4175
H11 — P05 Q3 — bids submitted and competitiveness
[9 empty] | Contractor | Bids submitted | Avg bid ÷ lowest bid
[9 empty] | Contractor-A | 4 | 2.3695
[9 empty] | Contractor-B | 2 | 2.1817
[9 empty] | Contractor-D | 6 | 2.8617
[9 empty] | Contractor-E | 2 | 2.4577
[9 empty] | Contractor-F | 3 | 4.6643
[9 empty] | Contractor-H | 3 | 3.7115
[9 empty] | Contractor-I | 2 | 1.4423
[9 empty] | Contractor-J | 2 | 3.0108
[9 empty] | Contractor-K | 3 | 1.5856
[9 empty] | Contractor-L | 1 | 5.4022
[9 empty] | Contractor-M | 3 | 1.3676
[9 empty] | Contractor-N | 5 | 2.5263
[9 empty] | Contractor-O | 4 | 2.3548
Q4. Total financial impact of quantity overruns per project |  |  | Q5. BOQ Amount vs Actual Amount per trade — Project WT-DC-MUM-01 (chart to the right) |  |  | Q6. Which items have negative variance (came under BOQ)? What is the saving? |  |  | H12 — P05 Q4 — HIGH RISK bids
[9 empty] | Contractor · Package | Safety rating | Past defect rate %
ANSWER: Gross overrun impact is $18,28,491 against $2,37,902 of savings, a net $15,90,589 across the three projects. Worst project: WT-OFF-SYD-02 at $7,16,910 net. |  |  | ANSWER: For WT-DC-MUM-01 the BOQ of $56,86,240 has been measured at $60,61,895, a $3,75,655 (6.6%) build-up. The biggest contributor is Civil & Structure (+$2,38,929). Chart to the right shows the BOQ-to-actual build-up by trade. |  |  | ANSWER: 19 of 72 BOQ items came in under quantity, saving $2,37,902 in total ($12,521 per item on average). The single largest saving is GI Piping on WT-DC-MUM-01 (MEP - Plumbing) at $49,998. Note: the source sheet's Overrun_Impact column records only positive overruns, so savings here are computed as Actual Amount minus BOQ Amount. |  |  | Contractor-M · Structural Works | 3.4 | 11.4
[9 empty] | Contractor-O · MEP Package | 3.2 | 9.3
[9 empty] | Contractor-O · MEP Package | 2.7 | 11
[9 empty] | Contractor-F · MEP Package | 2.6 | 11.1
H13 — P06 Q1 — delay cause Pareto
[9 empty] | Delay cause | Occurrences | Cumulative %
[9 empty] | RFI Response Delay | 11 | 18.33%
[9 empty] | Permit Delay | 8 | 31.67%
[9 empty] | Material Delay | 8 | 45%
[9 empty] | Client Decision Pending | 6 | 55%
[9 empty] | Labour Shortage | 5 | 63.33%
[9 empty] | Equipment Breakdown | 5 | 71.67%
[9 empty] | Rework | 5 | 80%
[9 empty] | Weather | 5 | 88.33%
[9 empty] | Design Change | 4 | 95%
[9 empty] | Subcontractor Default | 3 | 100%
H14 — P06 Q4 — weather vs all-cause delay by month
[9 empty] | Month | Weather delay days | All-cause delay days
[9 empty] | Jan | 36 | 72
PROBLEM 04 — Labour Productivity by Trade ¦ Source sheet: P04-LabourProd (80 daily records, 4 projects) | [8 empty] | Feb | 0 | 0
[9 empty] | Mar | 0 | 0
Q1. Which trade has the highest average productivity per man-hour? |  |  | Q2. Is there a productivity difference between projects in India vs Australia? |  |  | Q3. Summary statistics of productivity by trade — which has the most variance? |  |  | Apr | 0 | 48
[9 empty] | May | 0 | 103
ANSWER: Civil & Structure has the highest average productivity at 3.54 units per man-hour; the lowest is MEP - Plumbing at 2.23. Note: output units differ by trade (cum, rmt, sqm), so compare within a trade rather than across. |  |  | ANSWER: India-based projects average 3.25 units/man-hour vs Australia at 3.05 — a gap of 0.20 (6.5%). India is more productive on this sample, but the two countries run different trade mixes and output units, so the gap is indicative only. |  |  | ANSWER: Civil & Structure shows the most variance (std dev 2.00, CV 56.4%); the most consistent is MEP - HVAC (std dev 1.13). High variance points to unstable crew mix or interrupted work fronts. |  |  | Jun | 44 | 285
[9 empty] | Jul | 0 | 153
[9 empty] | Aug | 19 | 126
[9 empty] | Sep | 0 | 239
[9 empty] | Oct | 0 | 33
[9 empty] | Nov | 45 | 141
[9 empty] | Dec | 15 | 267
H15 — P06 Q5 — delay by activity
[9 empty] | Activity | Total delay days | Avg delay days
[9 empty] | Foundation | 128 | 25.6
[9 empty] | Superstructure | 84 | 21
[9 empty] | MEP Rough-In | 201 | 33.5
[9 empty] | Facade Installation | 133 | 22.1667
[9 empty] | Interior Works | 182 | 20.2222
[9 empty] | External Works | 143 | 20.4286
[9 empty] | Landscape | 183 | 26.1429
[9 empty] | Testing & Commissioning | 291 | 26.4545
[9 empty] | Handover Prep | 122 | 24.4
Q4. On which dates did productivity drop below the 25th percentile? What was the trade? |  |  | Q5. Optimal crew size (workers count) that maximises productivity for Civil & Structure |  |  | Q6. Total man-hours consumed per project, ranked |  |  | H16 — P06 Q6 — cost of delay by project
[9 empty] | Project | Cost of delay USD
ANSWER: The 25th percentile is 1.50 units/man-hour and 20 of 80 days fall below it. The 10 worst days are listed above; the single lowest was 2025-01-08 (Facade & Cladding on WT-OFF-SYD-02) at 0.23. |  |  | ANSWER: For Civil & Structure the best-performing crew band is Medium crew (11 to 15) at 4.16 units/man-hour (avg crew 13.0 workers) versus 2.68 for the weakest band. |  |  | ANSWER: WT-DC-MUM-01 consumes the most labour at 4,631 man-hours, then WT-HOS-AKL-03 (4,101), WT-ITP-BLR-04 (3,509) and WT-OFF-SYD-02 (3,201). Total across the four projects: 15,442 man-hours. |  |  | WT-DC-MUM-01 | 5730000
[9 empty] | WT-OFF-SYD-02 | 4155000
[9 empty] | WT-HOS-AKL-03 | 3075000
[9 empty] | WT-RES-MEL-05 | 3690000
[9 empty] | WT-MAL-DEL-06 | 5355000
H17 — P07 Q4 — collection-risk project-months
[9 empty] | Month · Project | Actual ÷ planned inflow
[9 empty] | 2024-01 · WT-DC-MUM-01 | 62.96%
[9 empty] | 2024-04 · WT-DC-MUM-01 | 68.79%
[9 empty] | 2024-07 · WT-DC-MUM-01 | 65.37%
[9 empty] | 2024-10 · WT-DC-MUM-01 | 65.63%
[9 empty] | 2024-01 · WT-OFF-SYD-02 | 68.77%
[9 empty] | 2024-03 · WT-OFF-SYD-02 | 64.77%
[9 empty] | 2024-04 · WT-OFF-SYD-02 | 60.34%
[9 empty] | 2024-08 · WT-OFF-SYD-02 | 67.99%
[9 empty] | 2024-03 · WT-HOS-AKL-03 | 64.09%
[9 empty] | 2024-04 · WT-HOS-AKL-03 | 63.91%
[9 empty] | 2024-06 · WT-HOS-AKL-03 | 67.49%
[9 empty] | 2024-07 · WT-HOS-AKL-03 | 65.81%
[9 empty] | 2024-08 · WT-HOS-AKL-03 | 64.55%
PROBLEM 05 — Tender Bid Comparison ¦ Source sheet: P05-TenderBid (40 bids, 5 packages, 13 contractors) | [8 empty] | 2024-10 · WT-HOS-AKL-03 | 62.89%
Q1. For each package, which contractor offers the lowest bid? Is the lowest bid always the best choice? |  |  | Q2. Weighted scoring model — 40% Price, 20% Time, 15% Experience, 15% Safety, 10% Defects (scores normalised within each package) |  |  | Q3. Which contractors appear in multiple packages? What is their average bid competitiveness? |  |  | H18 — P07 Q5 — cash surplus / deficit build-up
[9 empty] | Measure | Amount USD
ANSWER: The lowest bidder is listed in column B for each of the 5 packages. No — lowest is not always best: on 2 of 5 packages the highest-scored bidder is a different contractor, and buying the best-scored bid instead of the cheapest costs $15,86,411 more in total. Ultra-low bids in this set also carry weak safety ratings and higher defect rates (see Q4). |  |  | ANSWER: Scores are normalised within each package (best value = 1.0) and weighted 40/20/15/15/10. The strongest bid overall is Contractor-M on Interior Fit-out with 91.3/100; the weakest is Contractor-F on MEP Package with 34.3. Column K gives the rank inside each package — award recommendations are the Rank 1 rows. |  |  | ANSWER: 12 of 13 contractors bid for more than one package. On competitiveness (bid ÷ lowest bid in that package, 1.00 = cheapest), the sharpest pricing comes from Contractor-M at 1.37x and the most expensive is Contractor-L at 5.40x. Best average weighted score: Contractor-M (69.7/100). |  |  | Planned inflow | 55903347
[9 empty] | Actual inflow | 43006437
[9 empty] | Planned outflow | 49699767
[9 empty] | Actual outflow | 50322924
[9 empty] | Net surplus / (deficit) | -7316487
H19 — P07 Q6 — cash forecast accuracy
[9 empty] | Project | Forecast accuracy %
[9 empty] | WT-DC-MUM-01 | 77.72%
[9 empty] | WT-OFF-SYD-02 | 77.79%
[9 empty] | WT-HOS-AKL-03 | 74.34%
[9 empty] | WT-ITP-BLR-04 | 77.94%
[9 empty] | PORTFOLIO | 76.93%
H20 — P08 Q1 — approved vs total VO cost
[9 empty] | Project | Approved VO cost USD | All VO cost USD
[9 empty] | WT-DC-MUM-01 | 791101 | 2083172
[9 empty] | WT-OFF-SYD-02 | 583674 | 4884716
[9 empty] | WT-HOS-AKL-03 | 1919398 | 3608761
[9 empty] | WT-RES-MEL-05 | 892260 | 3770085
Q4. Contractors with Safety Rating < 3.5 AND Defect Rate > 8% — HIGH RISK flag |  |  | Q5. Total project cost — lowest bidder per package vs highest-scored bidder per package |  |  | Q6. Bid Amount vs Completion Days — are cheaper bids slower? (scatter chart to the right)
H21 — P08 Q5 — VO frequency per month
ANSWER: 4 of 40 bids breach both thresholds (Safety < 3.5 and Defect Rate > 8%) and are listed above as HIGH RISK. Separately, 21 bids have a safety rating below 3.5 and 9 have a defect rate above 8%. Exclude the HIGH RISK rows from award even where they price competitively. |  |  | ANSWER: Awarding every package to the cheapest bid totals $1,01,30,539 (avg score 76.0/100). Awarding to the highest-scored bid totals $1,17,16,950 (avg score 79.1) — $15,86,411 (15.7%) more. That premium buys better programme, safety and defect performance. |  |  | ANSWER: r = -0.254 between bid amount and completion days — a weak negative relationship, i.e. cheaper bids do tend to quote longer programmes. The fastest 10 bids average $50,63,624 against $39,25,205 for the slowest 10. |  |  | Project | VOs per active month
[9 empty] | WT-DC-MUM-01 | 0.8
[9 empty] | WT-OFF-SYD-02 | 1.1667
[9 empty] | WT-HOS-AKL-03 | 1.2
[9 empty] | WT-RES-MEL-05 | 0.84615
H22 — P09 Q3 — defects vs quality score (30 scorecards)
[9 empty] | Defect count | Quality score
[9 empty] | 10 | 3.2
[9 empty] | 7 | 2.9
[9 empty] | 5 | 4.1
[9 empty] | 15 | 2.9
[9 empty] | 12 | 3.4
[9 empty] | 10 | 3
[9 empty] | 15 | 2.9
[9 empty] | 18 | 3.1
[9 empty] | 25 | 4.3
[9 empty] | 13 | 4
[9 empty] | 22 | 3.3
[9 empty] | 2 | 4.4
[9 empty] | 20 | 4
PROBLEM 06 — Project Delay Root Cause Analysis ¦ Source sheet: P06-DelayRCA (60 delay events, 5 projects) | [8 empty] | 22 | 2.3
[9 empty] | 0 | 3.1
Q1. What is the most frequent delay cause category? (Pareto table + chart to the right) |  |  | Q2. Which responsible party causes the most total delay days? |  |  | Q3. Project WT-DC-MUM-01 — cumulative delay and dominant cause |  |  | 9 | 3.2
[9 empty] | 2 | 3.6
ANSWER: The most frequent delay cause is RFI Response Delay with 11 of 60 events (18.3%) and 266 delay days. The top 3 causes — RFI Response Delay, Permit Delay and Material Delay — account for 45.0% of all delay events (Pareto 80/20 point is reached at rank 7). |  |  | ANSWER: Consultant is responsible for the most delay — 339 days (23.1% of the 1,467 total) across 15 incidents. Lowest contributor: Client with 121 days. |  |  | ANSWER: WT-DC-MUM-01 has accumulated 382 delay days across 12 events (avg 31.8 days each). The dominant cause is Material Delay with 105 days (27.5% of the project's delay). |  |  | 23 | 2.3
[9 empty] | 20 | 3.7
[9 empty] | 13 | 4
[9 empty] | 25 | 2.6
[9 empty] | 20 | 3.1
[9 empty] | 21 | 3.8
[9 empty] | 11 | 3.8
[9 empty] | 17 | 3.2
[9 empty] | 11 | 2.5
[9 empty] | 15 | 2.6
[9 empty] | 7 | 2.5
[9 empty] | 18 | 4.3
[9 empty] | 17 | 4.5
H23 — P09 Q5 — blacklist candidates
[9 empty] | Subcontractor · Trade | Weighted score | Defect count
[9 empty] | Contractor-G · Facade & Cladding | 2.805 | 22
[9 empty] | Contractor-N · Elevator Installation | 2.99 | 20
H24 — P09 Q6 — subcontractor performance by project
Q4. Is there a seasonal pattern in delays? (by month of actual start; weather isolated) |  |  | Q5. Which activity is most delay-prone across all projects? |  |  | Q6. Estimated cost of delay per project at a daily burn rate of $15,000 |  |  | Project | Avg weighted score | Avg quality | Avg safety
[9 empty] | WT-DC-MUM-01 | 3.3905 | 3.54 | 3.14
ANSWER: Weather delays peak in Nov (45 days) and total 159 days, 10.8% of all delay days. Overall delay days peak in Jun. That concentration points to a genuine seasonal (monsoon/winter) effect worth programming for. |  |  | ANSWER: Testing & Commissioning is the most delay-prone activity with 291 delay days over 11 events (19.8% of all delay days). On a per-event basis the worst is MEP Rough-In at 33.5 days per event. |  |  | ANSWER: At $15,000/day the portfolio's 1,467 delay days cost roughly $2,20,05,000. The most exposed project is WT-DC-MUM-01 at $57,30,000 (382 days); the least is WT-HOS-AKL-03 at $30,75,000. |  |  | WT-OFF-SYD-02 | 3.4735 | 3.08 | 3.51
[9 empty] | WT-HOS-AKL-03 | 3.431 | 3.44 | 3.7
[9 empty] | PORTFOLIO | 3.4317 | 3.3533 | 3.45
H25 — P10 Q5 — outlier test result
[9 empty] | Measure | Projects
[9 empty] | Projects tested | 40
[9 empty] | Outliers above 1.5x benchmark | 0
H26 — P10 Q6 — 50,000 sqm Mumbai data centre budget
[9 empty] | Scenario | Budget USD
[9 empty] | Low case | 20350000
[9 empty] | Base case | 30720000
[9 empty] | High case | 39900000
H27 — P12 Q1 — schedule variance by month
[9 empty] | Month | Schedule variance USD (EV - PV)
[9 empty] | Month 1 | -130878
[9 empty] | Month 2 | -60661
[9 empty] | Month 3 | -148083
[9 empty] | Month 4 | 130720
PROBLEM 07 — Monthly Cash Flow Tracking ¦ Source sheet: P07-CashFlow (48 project-months, 4 projects, Jan–Dec 2024) | [8 empty] | Month 5 | -25402
[9 empty] | Month 6 | -31619
Q1. Which project had negative net cash flow for the most months? |  |  | Q2. Cumulative cash position for each project at end of December 2024 |  |  | Q3. Monthly net cash flow for all 4 projects (line chart to the right) |  |  | Month 7 | -1191915
[9 empty] | Month 8 | -180291
ANSWER: WT-HOS-AKL-03 ran negative in 9 of 12 months — the most in the portfolio. Its worst month was 2024-12 at -$9,92,486. Best cash discipline: WT-DC-MUM-01 with 6 negative months. |  |  | ANSWER: At 31-Dec-2024 the portfolio sits at -$73,16,487 cumulative cash. 3 of 4 projects are cash-negative. Best: WT-DC-MUM-01 at $8,39,758; worst: WT-HOS-AKL-03 at -$38,67,202. Collections came in $1,28,96,910 below plan. |  |  | ANSWER: The chart to the right plots all four projects month by month. Portfolio net cash flow is negative in 7 of 12 months, with the deepest trough in 2024-09 (-$21,19,106) and the strongest month 2024-05 ($13,63,658). |  |  | Month 9 | -753563
[9 empty] | Month 10 | -1210728
[9 empty] | Month 11 | -484743
[9 empty] | Month 12 | -848419
[9 empty] | Month 13 | -2015131
[9 empty] | Month 14 | -551661
[9 empty] | Month 15 | 489754
[9 empty] | Month 16 | -1430580
[9 empty] | Month 17 | -183433
[9 empty] | Month 18 | -1931582
[9 empty] | Month 19 | -890712
[9 empty] | Month 20 | -2373180
[9 empty] | Month 21 | -2076169
[9 empty] | Month 22 | -3005313
[9 empty] | Month 23 | -1398628
[9 empty] | Month 24 | -354631
[9 empty] | Month 25 | 783654
[9 empty] | Month 26 | 894258
[9 empty] | Month 27 | -2822359
[9 empty] | Month 28 | -1390414
Q4. Months where actual inflow fell below 70% of planned — collection risk |  |  | Q5. Total cash surplus / deficit across all projects |  |  | Q6. Cash flow forecast accuracy — (Actual Inflow ÷ Planned Inflow) × 100 |  |  | Month 29 | -1581355
[9 empty] | Month 30 | 21964
ANSWER: 17 of 48 project-months collected less than 70% of planned inflow (the first 14 are listed above). The single worst is WT-OFF-SYD-02 in 2024-04 at 60.3% of plan. Concentrate collection effort on the projects appearing most often in column C. |  |  | ANSWER: Across all four projects WT collected $4,30,06,437 and spent $5,03,22,924, a net DEFICIT of $73,16,487 for 2024. 3 of 4 projects are individually in deficit. |  |  | ANSWER: Portfolio forecast accuracy is 76.9% — collections are running 23.1% below the cash-flow forecast. Most accurate project: WT-ITP-BLR-04 (77.9%); least accurate: WT-HOS-AKL-03 (74.3%). Anything below ~90% means the forecast, not just the client, needs fixing. |  |  | Month 31 | -1969190
[9 empty] | Month 32 | -4941717
[9 empty] | Month 33 | -2325712
[9 empty] | Month 34 | -192630
[9 empty] | Month 35 | -218108
[9 empty] | Month 36 | -4915677
H28 — P12 Q2 — CPI trend
[9 empty] | Month | CPI
[9 empty] | Month 1 | 1.0423
[9 empty] | Month 2 | 0.84655
[9 empty] | Month 3 | 0.8509
[9 empty] | Month 4 | 1.0424
[9 empty] | Month 5 | 1.0781
[9 empty] | Month 6 | 1.0675
[9 empty] | Month 7 | 0.84944
[9 empty] | Month 8 | 0.95344
[9 empty] | Month 9 | 0.99386
[9 empty] | Month 10 | 0.9673
[9 empty] | Month 11 | 0.92158
[9 empty] | Month 12 | 0.85849
PROBLEM 08 — Change Order (VO) Impact Analysis ¦ Source sheet: P08-ChangeOrder (45 variation orders, 4 projects) | [8 empty] | Month 13 | 0.98531
[9 empty] | Month 14 | 0.87784
Q1. Total approved cost impact of all change orders per project |  |  | Q2. Who initiates the most change orders — Client, Consultant, Contractor or Architect? |  |  | Q3. What % of change orders are still Pending or Under Review? What is the cost exposure? |  |  | Month 15 | 0.94065
[9 empty] | Month 16 | 0.89766
ANSWER: Approved change orders add $41,86,433 across the four projects (13 of 45 VOs approved). The largest approved exposure is WT-HOS-AKL-03 at $19,19,398; the smallest is WT-OFF-SYD-02 at $5,83,674. |  |  | ANSWER: Consultant initiates the most change orders — 16 of 45 (35.6%). By value the biggest driver is Client at $52,97,017 of cost impact. |  |  | ANSWER: 15 of 45 change orders (33.3%) are still Pending or Under Review, carrying $32,97,152 of unquantified cost exposure (23.0% of all VO value). That is the number to put in the risk register until these are determined. |  |  | Month 17 | 0.9968
[9 empty] | Month 18 | 1.0192
[9 empty] | Month 19 | 1.1004
[9 empty] | Month 20 | 0.8752
[9 empty] | Month 21 | 0.93006
[9 empty] | Month 22 | 1.0263
[9 empty] | Month 23 | 0.87922
[9 empty] | Month 24 | 0.84435
[9 empty] | Month 25 | 0.98374
[9 empty] | Month 26 | 1.0503
[9 empty] | Month 27 | 0.89172
[9 empty] | Month 28 | 0.90006
[9 empty] | Month 29 | 1.0609
[9 empty] | Month 30 | 0.8748
[9 empty] | Month 31 | 1.0497
[9 empty] | Month 32 | 0.9255
[9 empty] | Month 33 | 1.0005
[9 empty] | Month 34 | 0.99778
[9 empty] | Month 35 | 0.86172
[9 empty] | Month 36 | 0.89976
Q4. Is there a correlation between cost impact and time impact of VOs? |  |  | Q5. Which project has the highest change order frequency per month? |  |  | Q6. Approved vs Pending vs Under Review vs Rejected VO cost per project (stacked bar chart to the right)
H29 — P12 Q3 — BAC vs EAC
ANSWER: r = 0.124 — there is effectively no linear relationship between the money and the time a VO costs; expensive variations are not necessarily the ones that delay the programme. Average VO: $3,18,816 and 13.0 days. |  |  | ANSWER: WT-HOS-AKL-03 has the highest change-order frequency at 1.20 VOs per active month (12 VOs over 10 months). Lowest churn: WT-DC-MUM-01 at 0.80 per month. |  |  | ANSWER: The stacked bar to the right splits VO value by status for each project. Portfolio-wide: $41,86,433 approved, $13,22,846 pending, $19,74,306 under review and $68,63,149 rejected, on a total VO book of $1,43,46,734. |  |  | Measure | USD
[9 empty] | BAC — budget at completion | 25000000
[9 empty] | EAC — forecast at completion | 27785221.4894
H30 — P12 Q5 — SPI trend
[9 empty] | Month | SPI
[9 empty] | Month 1 | 0.81669
[9 empty] | Month 2 | 0.95589
[9 empty] | Month 3 | 0.92584
[9 empty] | Month 4 | 1.0491
[9 empty] | Month 5 | 0.99279
[9 empty] | Month 6 | 0.99267
[9 empty] | Month 7 | 0.76519
[9 empty] | Month 8 | 0.96733
[9 empty] | Month 9 | 0.878
[9 empty] | Month 10 | 0.83249
[9 empty] | Month 11 | 0.93423
[9 empty] | Month 12 | 0.89967
[9 empty] | Month 13 | 0.77632
[9 empty] | Month 14 | 0.9428
[9 empty] | Month 15 | 1.0482
PROBLEM 09 — Subcontractor Performance Scorecard ¦ Source sheet: P09-SubconScore (30 scorecards, 13 subcontractors, 3 projects) | [8 empty] | Month 16 | 0.86475
[9 empty] | Month 17 | 0.98443
Q1. Rank all subcontractors by weighted score — top 3 and bottom 3 |  |  | Q2. Which trade has the lowest average quality score? |  |  | Q3. Is there a negative correlation between defect count and quality score? |  |  | Month 18 | 0.84648
[9 empty] | Month 19 | 0.92913
ANSWER: Top 3 — Contractor-C (3.86), Contractor-M (3.80) and Contractor-B (3.65). Bottom 3 — Contractor-N (3.15), Contractor-A (3.24) and Contractor-E (3.25). Portfolio average weighted score: 3.43. |  |  | ANSWER: Civil & Structure has the lowest average quality score at 2.45 (vs the best, Interior Fit-out, at 3.88). Quality on that trade also carries 48 recorded defects. |  |  | ANSWER: r = -0.087 between defect count and quality score — essentially no relationship, which suggests the quality score is not being driven by recorded defects and the scoring may need review. Defects vs overall weighted score: r = 0.083. |  |  | Month 20 | 0.83428
[9 empty] | Month 21 | 0.85723
[9 empty] | Month 22 | 0.79789
[9 empty] | Month 23 | 0.91011
[9 empty] | Month 24 | 0.97921
[9 empty] | Month 25 | 1.0448
[9 empty] | Month 26 | 1.0475
[9 empty] | Month 27 | 0.8454
[9 empty] | Month 28 | 0.92747
[9 empty] | Month 29 | 0.9203
[9 empty] | Month 30 | 1.001
[9 empty] | Month 31 | 0.91264
[9 empty] | Month 32 | 0.76685
[9 empty] | Month 33 | 0.8934
[9 empty] | Month 34 | 0.99193
[9 empty] | Month 35 | 0.99073
[9 empty] | Month 36 | 0.79431
H31 — P12 Q6 — cost recovery needed by Month 24
[9 empty] | Measure | USD
Q4. Five-dimension profile of the top-performing subcontractor (radar chart to the right) |  |  | Q5. Which subcontractors should be blacklisted? (weighted score < 3.0 AND defects > 15) |  |  | Q6. Subcontractor performance across the 3 projects — is any project a consistent outlier? |  |  | EV at Month 24 | 16707135
[9 empty] | AC at Month 24 | 19786940
ANSWER: The top performer is Contractor-C with an average weighted score of 3.86. Its strongest dimension is Cost (4.60) and its weakest is Time (3.20) — see the radar chart to the right. |  |  | ANSWER: 2 scorecard(s) breach both blacklist criteria and are listed above. Separately 4 score below 3.0 and 13 carry more than 15 defects. |  |  | ANSWER: WT-DC-MUM-01 is the weakest project for subcontractor performance (avg weighted score 3.39 vs portfolio 3.43), while WT-OFF-SYD-02 is the strongest at 3.47. The spread is 0.08 points, so no project is a consistent outlier — performance differences are marginal. |  |  | AC allowed for CPI 1.00 | 16707135
H32 — P13 Q2 — supplier on-time delivery
[9 empty] | Supplier | On-time delivery %
[9 empty] | Supplier-A | 33.33%
[9 empty] | Supplier-B | 0%
[9 empty] | Supplier-C | 40%
[9 empty] | Supplier-D | 40%
[9 empty] | Supplier-E | 28.57%
[9 empty] | Supplier-F | 37.5%
[9 empty] | Supplier-G | 16.67%
[9 empty] | Supplier-H | 0%
[9 empty] | Supplier-I | 14.29%
[9 empty] | Supplier-J | 42.86%
H33 — P13 Q3 — on-time vs late POs
[9 empty] | Delivery outcome | POs
[9 empty] | Delivered on time | 15
[9 empty] | Delivered late | 35
H34 — P13 Q4 — lead time by country
PROBLEM 10 — Construction Cost Benchmarking ¦ Source sheet: P10-Benchmark (40 completed projects, 3 countries, 2022–2025) | [8 empty] | Country | Avg lead time (days) | Avg delay (days)
[9 empty] | India | 35.8571 | 6.3333
Q1. Average cost per sqm by country (bar chart to the right) |  |  | Q2. Which project type has the highest and lowest cost per sqm globally? |  |  | Q3. Has cost per sqm increased year-over-year? Trend by country |  |  | Australia | 36.8462 | 6.6923
[9 empty] | New Zealand | 38.3125 | 4.625
ANSWER: Australia is the most expensive market at $3,677/sqm, India the cheapest at $670/sqm — a 448.5% premium. Global average: $2,430/sqm. |  |  | ANSWER: Highest cost per sqm globally is Hotel at $3,859/sqm; lowest is Data Centre at $1,732/sqm — a spread of $2,127/sqm (2.2x). |  |  | ANSWER: Global average cost per sqm moved from $2,416 in 2022 to $2,169 in 2025, -10.2% over the period. By country: Australia 7.9%, India 81.6%, New Zealand -9.4%. Costs are flat or falling on this sample, but yearly samples are small (see column F).
H35 — P13 Q5 — lead-time unpredictability by material
[9 empty] | Material | Std dev of lead time (days)
[9 empty] | Cement (OPC 53) | 13.1072
[9 empty] | TMT Steel (Fe500) | 15.4569
[9 empty] | Structural Steel | 20.1296
[9 empty] | Aluminium Facade | 1.4142
[9 empty] | Glass (DGU) | 25.4558
[9 empty] | RMC M30 | 28.0595
[9 empty] | Aggregate (20mm) | 15.1877
[9 empty] | Sand (River) | -
[9 empty] | Bricks (AAC) | 7
[9 empty] | Tiles (Vitrified) | 39.598
[9 empty] | Plywood (Marine) | 18.272
[9 empty] | Waterproofing Membrane | 12.3423
[9 empty] | PVC Conduits | 17.9536
[9 empty] | MS Pipes | 21.2132
[9 empty] | Copper Wiring | -
H36 — P14 Q1 — invoiced / paid / outstanding
Q4. Benchmark table — Project Type × Country, average cost per sqm (USD) |  |  | Q5. Outliers — projects where cost/sqm is more than 1.5× the average for that type in that country |  |  | Q6. Budget estimate for a 50,000 sqm Data Centre in Mumbai |  |  | Measure | Amount USD
[9 empty] | Invoiced | 41713158
ANSWER: The grid above is the benchmark table (blank = no project of that type in that country). The most expensive combination is $4,790/sqm and the cheapest is $440/sqm. Use the relevant cell as the rate base when pricing a new pursuit, then adjust for year (Q3) and specification. |  |  | ANSWER: No project exceeds 1.5x the average cost/sqm for its type and country — cost performance is consistent across the benchmark set. The highest ratio recorded is 1.39x. |  |  | ANSWER: Indian Data Centre benchmarks average $614/sqm across 5 project(s), so a 50,000 sqm data centre in Mumbai should be budgeted at roughly $3,07,20,000, with a range of $2,03,50,000 (low) to $3,99,00,000 (high). Add escalation — Indian cost/sqm has moved 81.6% between 2022 and 2025 — plus site-specific loadings for power, cooling and redundancy. |  |  | Paid | 29856300
[9 empty] | Outstanding | 11856858
H37 — P14 Q2 — client outstanding and paid-late
[9 empty] | Client | Outstanding USD | Paid after due date USD
[9 empty] | GPT Group | 725333 | 3341941
[9 empty] | Ascendas REIT | 1145957 | 4622054
[9 empty] | Goodman Group | 850225 | 2880469
[9 empty] | Tata Realty | 2912761 | 4145611
[9 empty] | Brookfield | 4135698 | 4423250
[9 empty] | Dexus | 189837 | 2364281
[9 empty] | Stockland | 0 | 1861221
[9 empty] | Embassy Group | 606457 | 0
[9 empty] | Mirvac | 603256 | 2280472
[9 empty] | Lendlease | 687334 | 1180273
H38 — P14 Q3 — aging buckets
[9 empty] | Aging bucket | Outstanding USD
[9 empty] | 0–30 days | 998469
[9 empty] | 31–60 days | 3071180
[9 empty] | 61–90 days | 0
PROBLEM 12 — Earned Value Management (EVM) ¦ Source sheet: P12-EVM (36 monthly periods, BAC $25m) | [8 empty] | 90+ days | 6831506
Q1. In which month does the project first show a negative Schedule Variance (SV)? |  |  | Q2. What is the CPI trend? Is the project getting more or less cost-efficient over time? |  |  | Q3. Based on EAC at Month 36, what is the projected cost overrun? |  |  | H39 — P14 Q4 — days to pay by client
[9 empty] | Client | Avg days to pay | Max days to pay
ANSWER: Schedule Variance first turns negative in Month 1 (SV = -$1,30,878, SPI 0.82). In total 31 of 36 months run a negative SV, and the deepest point is Month 32 at -$49,41,717. |  |  | ANSWER: CPI moves from 1.042 in Month 1 to 0.900 in Month 36, a trend of -0.0004 per month — the project is getting LESS cost-efficient over time. Average CPI is 0.954 and 25 of 36 months sit below 1.00, so cost performance is structurally over budget. |  |  | ANSWER: EAC at Month 36 is $2,77,85,221 against a BAC of $2,50,00,000 — a projected OVERRUN of $27,85,221 (11.1%). Variance at Completion is -$27,85,221. |  |  | GPT Group | 53.6667 | 67
[9 empty] | Ascendas REIT | 71 | 88
[9 empty] | Goodman Group | 57 | 76
[9 empty] | Tata Realty | 53 | 69
[9 empty] | Brookfield | 64.4286 | 89
[9 empty] | Dexus | 53 | 58
[9 empty] | Stockland | 38 | 47
[9 empty] | Embassy Group | 28 | 28
[9 empty] | Mirvac | 70 | 84
[9 empty] | Lendlease | 44 | 44
H40 — P14 Q5 — collection rate by project
[9 empty] | Project | Collection rate
[9 empty] | WT-DC-MUM-01 | 58.45%
[9 empty] | WT-OFF-SYD-02 | 80.68%
[9 empty] | WT-HOS-AKL-03 | 69.4%
[9 empty] | WT-ITP-BLR-04 | 92.46%
[9 empty] | WT-RES-MEL-05 | 71.87%
H41 — P14 Q6 — interest receivable by client
Q4. PV, EV and AC — the classic S-curve (line chart to the right) |  |  | Q5. At what month does SPI drop below 0.90 (critical schedule delay)? |  |  | Q6. If management wants CPI ≥ 1.0 by Month 24, how much cost needs to be recovered? |  |  | Client | Interest receivable USD
[9 empty] | GPT Group | 54399.975
ANSWER: The S-curve to the right plots PV, EV and AC over 36 months. At Month 36: PV $2,38,98,889, EV $1,89,83,212, AC $2,10,98,110. EV sits -$49,15,677 against plan and AC is $21,14,898 above value earned — the classic signature of a project that is both behind schedule and over cost. |  |  | ANSWER: SPI first falls below 0.90 in Month 1, and is below 0.90 in 15 of the 36 months. The low point is 0.765 in Month 7, and the project closes Month 36 at SPI 0.794 — schedule recovery has not happened. |  |  | ANSWER: At Month 24, EV is $1,67,07,135 against AC of $1,97,86,940 (CPI 0.844). To reach CPI = 1.00 the actual cost would have to be no more than $1,67,07,135, so $30,79,805 (15.6% of spend to date) must be recovered — through value engineering, claim recovery or productivity gains — or the target must be reset. |  |  | Ascendas REIT | 29900.2975
[9 empty] | Goodman Group | 25506.75
[9 empty] | Tata Realty | 270697.5525
[9 empty] | Brookfield | 378457.246
[9 empty] | Dexus | 13383.5085
[9 empty] | Stockland | 0
[9 empty] | Embassy Group | 0
[9 empty] | Mirvac | 7842.328
[9 empty] | Lendlease | 17527.017
H42 — P15 Q2 — budget / spent / remaining
[9 empty] | Measure | Amount USD
[9 empty] | Total budget | 1425725823
[9 empty] | Spent to date | 690772336
[9 empty] | Budget remaining | 734953487
H43 — P15 Q3 — red-zone projects
[9 empty] | Red-zone project | SPI | CPI
[9 empty] | IT Park Sydney | 0.78 | 0.86
[9 empty] | Shopping Mall Canberra | 0.88 | 0.83
[9 empty] | Hospital Bangalore | 0.78 | 0.89
PROBLEM 13 — Procurement Lead Time Analysis ¦ Source sheet: P13-LeadTime (50 purchase orders, 10 suppliers)
H44 — P15 Q5 — avg completion by country
Q1. Average lead time (order date to actual delivery) by material |  |  | Q2. Which supplier has the worst on-time delivery rate? |  |  | Q3. How many POs were delivered late? What is the average delay? |  |  | Country | Avg completion %
[9 empty] | India | 41.33%
ANSWER: Average lead time across all 50 POs is 36.9 days. The longest is Copper Wiring at 69.0 days and the shortest is Plywood (Marine) at 21.7 days — plan procurement call-offs accordingly. |  |  | ANSWER: Supplier-B has the worst on-time delivery rate at 0.0% (0 of 1 POs on time, average 12.0 days late). Best performer: Supplier-J at 42.9%. |  |  | ANSWER: 35 of 50 POs (70.0%) were delivered after the expected date. Late POs run 9.6 days late on average; across the whole book the average slippage is 5.9 days, with a worst case of 20 days. |  |  | Australia | 62.7%
[9 empty] | New Zealand | 40.33%
[9 empty] | PORTFOLIO | 49.76%
H45 — P15 Q6 — traffic-light counts
[9 empty] | Traffic light | Projects
[9 empty] | GREEN | 4
[9 empty] | RED | 3
[9 empty] | AMBER | 18
H46 — P15 Q7 — portfolio quadrant mix
[9 empty] | Quadrant | Projects
[9 empty] | Star | 4
[9 empty] | On time, over cost | 6
[9 empty] | Late, on cost | 4
[9 empty] | Late and over cost | 11
Q4. Is there a country-level difference in procurement lead times? |  |  | Q5. Which material has the longest and most unpredictable lead time? |  |  | Q6. Supplier reliability scorecard (ranked by on-time delivery %)
ANSWER: Lead times range from 35.9 days in India to 38.3 days in New Zealand — a 2.5 day spread. On-time performance is best in Australia (38.5%) and worst in India (19.0%). |  |  | ANSWER: Copper Wiring has the longest average lead time at 69.0 days. Tiles (Vitrified) is the most unpredictable, with a standard deviation of 39.6 days and deliveries ranging 18 – 74 days. Carry buffer stock or dual-source those two. |  |  | ANSWER: The scorecard above ranks all 10 suppliers. 0 rate A (90%+ on time), 0 rate B, 0 are watch-list and 10 should be replaced. Portfolio on-time performance is 30.0%.
PROBLEM 14 — Client Payment Aging Tracker ¦ Source sheet: P14-PaymentAging (40 invoices, 10 clients, 5 projects)
Q1. What is the total outstanding amount across all projects? |  |  | Q2. Which client has the highest overdue amount (paid after due date / still unpaid)? |  |  | Q3. Aging bucket analysis of outstanding balances
ANSWER: Total outstanding across all projects is $1,18,56,858 on $4,17,13,158 invoiced — a collection rate of 71.6%. 19 of 40 invoices carry a balance. |  |  | ANSWER: Ascendas REIT has the largest value paid after the due date — $46,22,054. On money still unpaid, the biggest exposure is Brookfield at $41,35,698 outstanding. |  |  | ANSWER: Of $1,18,56,858 outstanding, $1,09,01,155 is past due and splits as: $9,98,469 (9.2%) 0–30 days, $30,71,180 (28.2%) 31–60 days, $0 (0.0%) 61–90 days and $68,31,506 (62.7%) 90+ days. The remaining $9,55,703 is not yet due. Average age of past-due debt: 80 days.
Q4. Average days-to-pay by client (payment date minus invoice date) |  |  | Q5. Which project has the worst collection rate (Paid ÷ Invoiced)? |  |  | Q6. Interest receivable on overdue amounts at 1.5% per month
ANSWER: The slowest payer is Ascendas REIT at 71 days from invoice to payment; the fastest is Embassy Group at 28 days. Portfolio average: 58 days against payment terms of roughly 30 days. |  |  | ANSWER: WT-DC-MUM-01 has the worst collection rate at 58.4% ($46,25,307 outstanding); the best is WT-ITP-BLR-04 at 92.5%. Portfolio collection rate: 71.6%. |  |  | ANSWER: At 1.5% per month, the $1,09,01,155 of overdue balances (average 96 days past due) carries $7,97,715 of interest receivable. The largest single claim is against Brookfield at $3,78,457. Aging is measured to 23-May-2025 (latest payment date in the data).
PROBLEM 15 — Multi-Project Portfolio Dashboard ¦ Source sheet: P15-Portfolio (25 projects, 3 countries)
Q1. How many projects are In Progress, On Hold, Completed and Planning? (pie chart to the right) |  |  | Q2. Total portfolio budget and spend, and overall budget variance |  |  | Q3. Red-zone projects — CPI < 0.90 AND SPI < 0.90
ANSWER: The portfolio splits 4 In Progress, 8 On Hold, 8 Completed and 5 in Planning (25 projects total). On Hold is the largest group at 32.0% of projects. On-hold projects alone tie up $50,58,48,491 of budget. |  |  | ANSWER: Portfolio budget is $1,42,57,25,823 and spend to date is $69,07,72,336 — 48.5% of budget drawn against 49.8% average completion, leaving $73,49,53,487 unspent. On the source sheet's own Budget_Variance column the portfolio is $3,61,50,438 adrift, and 12 of 25 projects show an adverse variance. |  |  | ANSWER: 3 of 25 projects are in the red zone (both CPI and SPI below 0.90) and are listed above. Separately 11 projects have CPI below 0.90 and 9 have SPI below 0.90. These need recovery plans before any new work is taken on.
Q4. Bubble view — X = SPI, Y = CPI, bubble size = Budget (chart to the right) |  |  | Q5. Average completion % by country |  |  | Q6. Traffic-light summary — Green (CPI≥1 and SPI≥1), Red (both < 0.9), Amber (everything else)
ANSWER: The busiest quadrant is "Late and over cost" with 11 of 25 projects (44.0%) and $63,55,84,316 of budget. Only 4 projects are true stars (both indices at or above 1.00). |  |  | ANSWER: Australia is furthest advanced at 62.7% average completion, while New Zealand trails at 40.3%. Portfolio average completion is 49.8%. |  |  | ANSWER: 4 projects are GREEN (16.0%), 18 AMBER (72.0%) and 3 RED (12.0%). Red projects carry $8,75,29,465 of budget — that is the portion of the portfolio needing intervention now.
Q7. Three-line executive summary for the board
ANSWER: The three lines above are the board summary — scale, performance and the action required.